## Portfolio
				Audit
Type	UID	Parent	Order	Name	Status	State	Wf Stage	Size	Start	Finish	Health	Hours	Cost	ExSponsor	PM	Phase	Updated From Which Sheet	When last updated
Portfolio	A002	A000	17	Business Continuity					22-Dec-2020	24-May-2021		5997.9	80720				Timebars	2021-01-12 08:37:24
Project	A008	A002	86	Centralized Billing and Receivables	Active	Spawned	NA	Large	23-Dec-2020	12-May-2021	Red	405.6	7920	Sydney Sp	Jim Pm	NA	Timebars	2021-01-12 08:37:25
Sub-Project	A017	A008	137	Billing Strategy and Policy Review	Cancelled	Approved	1 Proposed	Small	30-Dec-2020	03-Apr-2021	Yellow	106.8	5840	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Task	A047	A017	185	Bottom Up Estimate (Class A)					03-Jan-2021	05-Mar-2021		0	0				Timebars	2021-01-12 08:37:25
Task	A048	A017	224	Phase 1 Design and Procurement					20-Jan-2021	15-Mar-2021		106.8	5840				Timebars	2021-01-12 08:37:25
Allocation	A136	A048	266	Jill Road					24-Feb-2021	08-Apr-2021		28.2	0				Timebars	2021-01-12 08:37:25
Allocation	A137	A048	269	Jim Azure					22-Jan-2021	20-Feb-2021		20.2	0				Timebars	2021-01-12 08:37:25
Sub-Project	A020	A008	438	ERP Procurement Module Renewal	On-Hold	Awaiting Approval	1 Proposed	Small	21-Jan-2021	27-Mar-2021	Yellow	298.8	2080	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Allocation	A135	A048	315	Jean Radio					24-Jan-2021	28-Feb-2021		20	2000				Timebars	2021-01-12 08:37:25
Allocation	A134	A048	317	Jay Script					06-Mar-2021	31-Mar-2021		14.4	1440				Timebars	2021-01-12 08:37:25
Task	A059	A020	479	Judgement Estimate (Class C)					26-Jan-2021	28-Mar-2021		298.8	2080				Timebars	2021-01-12 08:37:25
Allocation	A133	A048	369	Jack Project					04-Feb-2021	17-Mar-2021		24	2400				Timebars	2021-01-12 08:37:25
Allocation	A241	A059	536	SME HR					26-Jan-2021	13-Feb-2021		33.6	0				Timebars	2021-01-12 08:37:25
Project	A013	A002	1102	HR Service Delivery	Active	Awaiting Review	1 Proposed	Medium	16-Jan-2021	01-May-2021	Yellow	265.5	24120	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Allocation	A243	A059	538	SME PM					13-Mar-2021	28-Mar-2021		32	0				Timebars	2021-01-12 08:37:25
Allocation	A242	A059	539	SME IT Platforms and Datacenter					16-Feb-2021	11-Mar-2021		28.8	0				Timebars	2021-01-12 08:37:25
Sub-Project	A023	A013	1157	HR Policy Update	Active	Awaiting Approval	1 Proposed	Small	22-Jan-2021	06-Apr-2021	Yellow	128.4	12840	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Allocation	A244	A059	602	SME Purchasing					28-Jan-2021	14-Feb-2021		19.2	0				Timebars	2021-01-12 08:37:25
Allocation	A245	A059	608	SME Solution Architecture					18-Feb-2021	08-Mar-2021		20.8	2080				Timebars	2021-01-12 08:37:25
Task	A054	A023	1215	Judgement Estimate (Class C)					31-Jan-2021	31-Mar-2021		128.4	12840				Timebars	2021-01-12 08:37:25
Allocation	A246	A059	655	Tester New Software					06-Feb-2021	25-Feb-2021		23.5	0				Timebars	2021-01-12 08:37:25
Allocation	A240	A059	663	SME Finance					28-Feb-2021	23-Mar-2021		54.4	0				Timebars	2021-01-12 08:37:25
Allocation	A192	A054	1257	SME Finance					02-Feb-2021	24-Feb-2021		34	3400				Timebars	2021-01-12 08:37:25
Allocation	A193	A054	1258	SME HR					25-Feb-2021	31-Mar-2021		20	2000				Timebars	2021-01-12 08:37:25
Allocation	A239	A059	710	Developer General					27-Jan-2021	01-Apr-2021		86.5	0				Timebars	2021-01-12 08:37:25
Allocation	A194	A054	1303	SME IT Platforms and Datacenter					02-Feb-2021	09-Mar-2021		20.8	2080				Timebars	2021-01-12 08:37:25
Sub-Project	A024	A013	1437	HR SAP Envisioning	Active	Requested Approval	1 Proposed	Medium	24-Jan-2021	20-Apr-2021	Yellow	137.1	11280	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Allocation	A196	A054	1346	SME Solution Architecture					02-Feb-2021	11-Mar-2021		22.4	2240				Timebars	2021-01-12 08:37:25
Task	A046	A024	1485	Judgement Estimate (Class C)					28-Jan-2021	24-Mar-2021		137.1	11280				Timebars	2021-01-12 08:37:25
Allocation	A191	A054	1390	Developer General					27-Feb-2021	31-Mar-2021		18.4	1840				Timebars	2021-01-12 08:37:25
Allocation	A197	A054	1390	Tester New Software					04-Feb-2021	25-Feb-2021		12.8	1280				Timebars	2021-01-12 08:37:25
Allocation	A126	A046	1520	Developer General					28-Jan-2021	04-Feb-2021		4.8	480				Timebars	2021-01-12 08:37:25
Allocation	A128	A046	1520	SME HR					17-Feb-2021	12-Mar-2021		17.3	0				Timebars	2021-01-12 08:37:25
Allocation	A127	A046	1523	SME Finance					05-Feb-2021	16-Feb-2021		7	0				Timebars	2021-01-12 08:37:25
Project	A026	A002	793	IM Policy and Guidelines	Active	Requested Approval	1 Proposed	Medium	23-Dec-2020	27-May-2021	Yellow	89.6	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:25
Allocation	A129	A046	1569	SME IT Platforms and Datacenter					29-Jan-2021	15-Feb-2021		48	4800				Timebars	2021-01-12 08:37:25
Allocation	A130	A046	1572	SME PM					16-Feb-2021	08-Mar-2021		12	1200				Timebars	2021-01-12 08:37:25
Allocation	A132	A046	1612	Tester New Software					29-Jan-2021	15-Feb-2021		9.6	960				Timebars	2021-01-12 08:37:25
Allocation	A131	A046	1617	SME Solution Architecture					16-Feb-2021	19-Mar-2021		38.4	3840				Timebars	2021-01-12 08:37:25
Sub-Project	A018	A026	844	Classified data in Public Cloud	Active	Requested Approval	1 Proposed	Medium	26-Dec-2020	17-Apr-2021	Yellow	0	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Task	A068	A018	886	Judgement Estimate (Class C)					30-Dec-2020	11-Mar-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A327	A068	932	SME Finance					03-Jan-2021	26-Jan-2021		13.6	1360				Timebars	2021-01-12 08:37:26
Allocation	A329	A068	940	SME IT Platforms and Datacenter					10-Feb-2021	15-Mar-2021		21.1	0				Timebars	2021-01-12 08:37:26
Allocation	A332	A068	995	Tester New Software					02-Jan-2021	30-Jan-2021		16	1600				Timebars	2021-01-12 08:37:26
Portfolio	A003	A000	1672	Core Product Delivery Portfolio	Active	Awaiting Approval	NA	Small	21-Dec-2020	16-Jul-2022	Yellow	Accounting	Customer Support Department	Sydney Sp	Jim Pm	NA	Timebars	2020-12-31 16:32:17
Allocation	A330	A068	1001	SME PM					10-Feb-2021	10-Mar-2021		33.6	3360				Timebars	2021-01-12 08:37:26
Allocation	A331	A068	1058	SME Solution Architecture					13-Jan-2021	15-Feb-2021		19.2	1920				Timebars	2021-01-12 08:37:26
Project	A009	A002	1727	Continuous Improvement Transformation	Active	Spawned	1 Proposed	Large	28-Dec-2020	09-May-2021	Yellow	562	31360	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A328	A068	1071	SME HR					17-Feb-2021	16-Mar-2021		16	1600				Timebars	2021-01-12 08:37:26
Sub-Project	A019	A009	1780	Database Upgrade Market Datamart	On-Hold	Awaiting Input	1 Proposed	Large	01-Jan-2021	06-Feb-2021	Yellow	102.2	5040	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Task	A061	A019	1830	Judgement Estimate (Class C)					03-Jan-2021	08-Feb-2021		102.2	5040				Timebars	2021-01-12 08:37:26
Allocation	A264	A061	1881	Developer ERP System					04-Jan-2021	31-Jan-2021		35.2	0				Timebars	2021-01-12 08:37:26
Sub-Project	A010	A009	2060	Constant Internal Delivery Enablement	Active	NA	1 Proposed	Large	05-Jan-2021	30-Mar-2021	Yellow	459.8	26320	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A266	A061	1923	Developer SQL					06-Feb-2021	17-Feb-2021		16	1600				Timebars	2021-01-12 08:37:26
Allocation	A268	A061	1923	Tester Platforms and Datacenter					04-Jan-2021	20-Jan-2021		10.4	1040				Timebars	2021-01-12 08:37:26
Task	A062	A010	2111	Judgement Estimate (Class C)					07-Jan-2021	01-Apr-2021		459.8	26320				Timebars	2021-01-12 08:37:26
Allocation	A265	A061	1982	Developer General					03-Feb-2021	15-Feb-2021		16.6	0				Timebars	2021-01-12 08:37:26
Allocation	A267	A061	1982	SME Solution Architecture					05-Jan-2021	20-Jan-2021		24	2400				Timebars	2021-01-12 08:37:26
Project	A011	A002	2795	Core Operations Program	Active	Approved	1 Proposed	Small	05-Jan-2021	11-May-2021	Yellow	4531.2	0	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A269	A062	2226	Developer ERP System					12-Feb-2021	23-Mar-2021		44.8	4480				Timebars	2021-01-12 08:37:26
Allocation	A277	A062	2228	SME Cloud Technologies					08-Jan-2021	31-Jan-2021		25.6	2560				Timebars	2021-01-12 08:37:26
Allocation	A285	A062	2271	Tester Platforms and Datacenter					07-Jan-2021	29-Jan-2021		13.6	1360				Timebars	2021-01-12 08:37:26
Allocation	A282	A062	2273	SME Purchasing					11-Feb-2021	03-Mar-2021		12	1200				Timebars	2021-01-12 08:37:26
Allocation	A270	A062	2279	Developer General					06-Mar-2021	09-Apr-2021		40	4000				Timebars	2021-01-12 08:37:26
Sub-Project	A021	A011	2864	Extend WWT to support AI	On-Hold	Awaiting Review	1 Proposed	Medium	09-Jan-2021	03-Mar-2021	Yellow	1126.4	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A279	A062	2322	SME HR					02-Mar-2021	02-Apr-2021		42.2	0				Timebars	2021-01-12 08:37:26
Allocation	A281	A062	2324	SME PM					06-Jan-2021	29-Jan-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A284	A062	2324	Tester New Software					05-Feb-2021	23-Feb-2021		20.8	2080				Timebars	2021-01-12 08:37:26
Task	A049	A021	2858	Judgement Estimate (Class C)					08-Mar-2021	27-Apr-2021		1126.4	0				Timebars	2021-01-12 08:37:26
Allocation	A278	A062	2377	SME Finance					02-Mar-2021	07-Apr-2021		45.4	0				Timebars	2021-01-12 08:37:26
Allocation	A283	A062	2378	SME Solution Architecture					04-Feb-2021	25-Feb-2021		12.8	1280				Timebars	2021-01-12 08:37:26
Allocation	A138	A049	2904	Developer ERP System					08-Mar-2021	04-Apr-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A139	A049	2935	Developer General					30-Mar-2021	22-Apr-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A124	A045	1586	Jack Project					20-Aug-2020	28-Sep-2020		0	0				Timebars	2021-01-12 08:37:26
Allocation	A141	A049	2943	SME Solution Architecture					08-Mar-2021	26-Mar-2021		480	0				Timebars	2021-01-12 08:37:26
Allocation	A276	A062	2431	Product Owner/Sponsor					04-Jan-2021	27-Jan-2021		28.8	2880				Timebars	2021-01-12 08:37:26
Allocation	A280	A062	2449	SME IT Platforms and Datacenter					07-Feb-2021	06-Mar-2021		36.8	0				Timebars	2021-01-12 08:37:26
Allocation	A271	A062	2452	Developer SQL					08-Mar-2021	06-Apr-2021		37	0				Timebars	2021-01-12 08:37:26
Allocation	A140	A049	2984	Developer SQL					27-Mar-2021	17-Apr-2021		480	0				Timebars	2021-01-12 08:37:26
Allocation	A142	A049	2984	Tester Platforms and Datacenter					09-Mar-2021	25-Mar-2021		166.4	0				Timebars	2021-01-12 08:37:26
Allocation	A123	A045	1631	Chris Java					21-Aug-2020	29-Sep-2020		0	0				Timebars	2021-01-12 08:37:26
Sub-Project	A022	A011	3123	Google Maps Integration	Active	Approved	1 Proposed	Small	08-Jan-2021	05-Mar-2021	Yellow	3404.8	0	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A274	A062	2489	Engineer Hardware					31-Jan-2021	16-Feb-2021		24	2400				Timebars	2021-01-12 08:37:26
Allocation	A275	A062	2490	Engineer RF					04-Jan-2021	18-Jan-2021		8.8	880				Timebars	2021-01-12 08:37:26
Allocation	A273	A062	2494	Engineer Antennas					18-Feb-2021	11-Mar-2021		32	3200				Timebars	2021-01-12 08:37:26
Allocation	A272	A062	2497	Developer Web					14-Mar-2021	09-Apr-2021		35.2	0				Timebars	2021-01-12 08:37:26
Allocation	A122	A045	1670	Cathy Test					21-Aug-2020	29-Sep-2020		0	0				Timebars	2021-01-12 08:37:26
Task	A065	A022	3178	Judgement Estimate (Class C)					17-Jan-2021	13-Mar-2021		3404.8	0				Timebars	2021-01-12 08:37:26
Allocation	A121	A045	1707	Ally HR					07-Sep-2020	16-Oct-2020		0	0				Timebars	2021-01-12 08:37:26
Allocation	A308	A065	3248	Developer General					18-Jan-2021	13-Mar-2021		512	0				Timebars	2021-01-12 08:37:26
Sub-Project	A033	A026	1823	TBS Compliance	Active	Awaiting Approval	1 Proposed	Small	27-Mar-2021	19-May-2021	Yellow	60.8	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:26
Allocation	A125	A045	1775	Jay Script					06-Sep-2020	15-Oct-2020		0	0				Timebars	2021-01-12 08:37:26
Allocation	A310	A065	3290	SME Solution Architecture					18-Jan-2021	21-Feb-2021		320	0				Timebars	2021-01-12 08:37:26
Task	A041	A033	1868	Judgement Estimate (Class C)					03-Apr-2021	22-May-2021		28	0				Timebars	2021-01-12 08:37:26
Allocation	A311	A065	3337	Tester Platforms and Datacenter					19-Jan-2021	23-Feb-2021		332.8	0				Timebars	2021-01-12 08:37:26
Allocation	A111	A041	1940	SME PM					18-Apr-2021	23-Feb-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A113	A041	1941	Tester New Software					26-Apr-2021	13-Mar-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A112	A041	1942	SME Solution Architecture					09-May-2021	13-Apr-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A107	A041	1943	Developer General					04-Apr-2021	23-Feb-2021		0	0				Timebars	2021-01-12 08:37:26
Allocation	A309	A065	3395	Developer SQL					16-Jan-2021	19-Feb-2021		320	0				Timebars	2021-01-12 08:37:26
Sub-Project	A036	A009	2566	Upgrade Ticketing System	Active	Requested Approval	1 Proposed	Medium	01-Jan-2021	12-Feb-2021	Yellow	0	0	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Allocation	A110	A041	2002	SME IT Platforms and Datacenter					05-May-2021	22-Mar-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A108	A041	2004	SME Finance					24-Apr-2021	09-Mar-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A307	A065	3443	Developer ERP System					26-Jan-2021	08-Mar-2021		1920	0				Timebars	2021-01-12 08:37:27
Task	A044	A036	2624	Bottom Up Estimate (Class A)					03-Jan-2021	19-Jan-2021		0	0				Timebars	2021-01-12 08:37:27
Task	A045	A044	2624	Plan and Execute Upgrade					02-Feb-2021	18-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Sub-Project	A027	A026	2608	Internal IM Policy Modernization	On-Hold	Awaiting Input	1 Proposed	Large	31-Dec-2020	24-Mar-2021	Yellow	48	0	Sydney Sp	Jim Pm	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Task	A058	A027	2659	Judgement Estimate (Class C)					02-Jan-2021	19-Mar-2021		44	0				Timebars	2021-01-12 08:37:27
Allocation	A236	A058	2710	SME PM					03-Jan-2021	16-Jan-2021		16	1600				Timebars	2021-01-12 08:37:27
Allocation	A234	A058	2714	SME HR					18-Feb-2021	07-Mar-2021		9.6	960				Timebars	2021-01-12 08:37:27
Allocation	A235	A058	2721	SME IT Platforms and Datacenter					28-Jan-2021	16-Feb-2021		22.4	2240				Timebars	2021-01-12 08:37:27
Portfolio	A004	A000	3594	IT Platform Portfolio	Active	Requested Approval	NA	Medium	02-Jan-2021	24-Apr-2021	Yellow	Finance	Customer Support Department	Sydney Sp	Jim Pm	NA	Timebars	2020-12-31 16:32:19
Allocation	A238	A058	2772	Tester New Software					03-Jan-2021	13-Jan-2021		14.1	0				Timebars	2021-01-12 08:37:27
Allocation	A237	A058	2781	SME Solution Architecture					26-Jan-2021	14-Feb-2021		23.5	0				Timebars	2021-01-12 08:37:27
Allocation	A233	A058	2785	SME Finance					23-Feb-2021	13-Mar-2021		28	2800				Timebars	2021-01-12 08:37:27
Project	A007	A004	3660	Business Continuity Management	Active	Awaiting Input	NA	Large	02-Jan-2021	08-Mar-2021	Green	1830.4	61440	Sydney Sp	Jim Pm	NA	Timebars	2021-01-12 08:37:27
Sub-Project	A031	A007	3721	SAP Platform Upgrade	Active	Approved	1 Proposed	Small	04-Jan-2021	04-Mar-2021	Yellow	1830.4	61440	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Task	A069	A031	3761	Judgement Estimate (Class C)					05-Jan-2021	04-Mar-2021		1830.4	61440				Timebars	2021-01-12 08:37:27
Allocation	A333	A069	3812	Developer General					16-Jan-2021	12-Mar-2021		0	0				Timebars	2021-01-12 08:37:27
Project	A012	A004	4052	Digital Workplace - Transformation	Active	Approved	1 Proposed	Small	09-Jan-2021	18-Apr-2021	Yellow	5766.4	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Allocation	A335	A069	3867	SME HR					08-Feb-2021	08-Mar-2021		268.8	0				Timebars	2021-01-12 08:37:27
Sub-Project	A030	A012	4103	Public Cloud Phase 1	On-Hold	Awaiting Review	1 Proposed	Medium	12-Jan-2021	06-Apr-2021	Yellow	2585.6	0	Marsha Sp	PM011	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Allocation	A336	A069	3879	SME IT Platforms and Datacenter					05-Jan-2021	27-Jan-2021		217.6	21760				Timebars	2021-01-12 08:37:27
Task	A064	A030	4153	Judgement Estimate (Class C)					13-Jan-2021	06-Apr-2021		2585.6	0				Timebars	2021-01-12 08:37:27
Allocation	A338	A069	3927	SME Purchasing					05-Jan-2021	26-Jan-2021		204.8	20480				Timebars	2021-01-12 08:37:27
Allocation	A337	A069	3928	SME PM					05-Feb-2021	25-Feb-2021		192	0				Timebars	2021-01-12 08:37:27
Allocation	A334	A069	3935	SME Finance					27-Feb-2021	11-Mar-2021		576	0				Timebars	2021-01-12 08:37:27
Allocation	A296	A064	4203	Developer General					21-Mar-2021	03-Apr-2021		128	0				Timebars	2021-01-12 08:37:27
Allocation	A303	A064	4204	SME Purchasing					14-Feb-2021	19-Mar-2021		320	0				Timebars	2021-01-12 08:37:27
Allocation	A304	A064	4204	SME Solution Architecture					13-Jan-2021	11-Feb-2021		563.2	0				Timebars	2021-01-12 08:37:27
Allocation	A339	A069	3988	SME Solution Architecture					02-Feb-2021	19-Feb-2021		179.2	0				Timebars	2021-01-12 08:37:27
Allocation	A340	A069	3989	Tester New Software					04-Jan-2021	22-Jan-2021		192	19200				Timebars	2021-01-12 08:37:27
Sub-Project	A029	A012	4485	Private Cloud Phase 1	On-Hold	Awaiting Approval	1 Proposed	Small	16-Jan-2021	08-Apr-2021	Yellow	3180.8	0	Colin Sp	Al PM	1 Pre-execution (evaluation and selection)	Timebars	2021-01-12 08:37:27
Allocation	A297	A064	4252	Product Owner/Sponsor					02-Mar-2021	22-Mar-2021		576	0				Timebars	2021-01-12 08:37:27
Allocation	A305	A064	4252	Tester New Software					16-Jan-2021	07-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A298	A064	4253	SME Cloud Technologies					10-Feb-2021	02-Mar-2021		192	0				Timebars	2021-01-12 08:37:27
Task	A055	A029	4549	Judgement Estimate (Class C)					17-Jan-2021	07-Apr-2021		3180.8	0				Timebars	2021-01-12 08:37:27
Allocation	A301	A064	4300	SME IT Platforms and Datacenter					01-Feb-2021	19-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A300	A064	4301	SME HR					14-Jan-2021	03-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A299	A064	4304	SME Finance					22-Feb-2021	14-Mar-2021		192	0				Timebars	2021-01-12 08:37:27
Allocation	A198	A055	4600	Developer General					20-Feb-2021	13-Mar-2021		384	0				Timebars	2021-01-12 08:37:27
Allocation	A200	A055	4601	SME Cloud Technologies					13-Mar-2021	06-Apr-2021		217.6	0				Timebars	2021-01-12 08:37:27
Allocation	A205	A055	4601	SME Solution Architecture					18-Jan-2021	19-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A302	A064	4353	SME PM					13-Jan-2021	19-Mar-2021		614.4	0				Timebars	2021-01-12 08:37:27
Allocation	A206	A055	4638	Tester New Software					18-Jan-2021	25-Feb-2021		0	0				Timebars	2021-01-12 08:37:27
Allocation	A207	A055	4650	Tester Platforms and Datacenter					02-Mar-2021	29-Mar-2021		640	0				Timebars	2021-01-12 08:37:27
Allocation	A199	A055	4685	Product Owner/Sponsor					21-Jan-2021	18-Feb-2021		268.8	0				Timebars	2021-01-12 08:37:27
Allocation	A202	A055	4701	SME HR					22-Feb-2021	21-Mar-2021		256	0				Timebars	2021-01-12 08:37:27
Allocation	A204	A055	4719	SME PM					19-Jan-2021	05-Feb-2021		358.4	0				Timebars	2021-01-12 08:37:27
Allocation	A201	A055	4741	SME Finance					11-Mar-2021	03-Apr-2021		544	0				Timebars	2021-01-12 08:37:27
Allocation	A203	A055	4749	SME IT Platforms and Datacenter					06-Feb-2021	06-Mar-2021		512	0				Timebars	2021-01-12 08:37:27
Allocation	A109	A041	2050	SME HR					06-May-2021	01-Apr-2021		0	0				Timebars	2021-01-12 08:37:27
Get Data

## Timebars
tbID	tbSelfKey2	tbPredecessor	tbTaskParent	tbCoordTop	tbHierarchyOrder	tbName	tbType	tbL1	tbL2	tbL3	tbL4	tbL5	tbStatus	tbState	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbPriority	tbPhase	tbStart	tbFinish	tbDuration	tbOwner	tbRemainingDuration	tbAStart	tbAFinish	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStage	tbPine	tbBalsam	tbFir	tbSpruce	tbArea	tbSize	tbPercent2	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	tbExpHoursPerWeek	tbCostID	tbCost	tbCostRemaining	tbACost	tbPayRate	tbCostType	canvasNo	tbAzureID	kbCoordTop	kbCoordLeft	tbHierarchyOrder	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbCoordLeft	tbMetaDataID	tbBLID	tbVolume	tbAWork	tbWorkRemaining	tbPercentComplete	tbCost	tbAcost	tbCostRemaining	tbResID	tbCalendar	tbPercentTimeOn	tbCustomerID
NWI Project Data				Mandatory		Mandatory	Mandatory	Mandatory	Mandatory	Mandatory	Mandatory	Mandatory	Mandatory
UID	Parent	Predecessor	TaskParent	Top Pos	HierarchyOrder	Name	Type	Portfolio	Project	Sub-Project	Task	Allocation	Status	State	Step	StepStatus	WfReasonNote	Stage	Priority	Phase	Start	Finish	Duration	Owner	Rem Dur	Astart	Afinish	Hours	Awork	Work Rem	% Compl	Stage	Pine	Balsam	Fir	Spruce	Area	Sizexxx	%Pulp	Constr Type	Constr Date	Float	FreeFloat	Exp Hours Per Week	Cost ID	Cost	Cost Rem	Acost	Pay Rate	Cost Type	Cavas No	CloudID	KB Top PX	KB Left PX	Hierarchy Order	focdItemCoordLeft	focdItemCoordTop	Bar Color	Text Color	LeftPX	MDID	BLID	Vol/HA	AWork	WorkRemaining	PercentComplete	Cost	Acost	CostRemaining	ResID	Calendar	PercentTimeOn	CustID
A002		0		17		Business Continuity	Portfolio														22-Dec-2020	24-May-2021	110	spadmin	98	22-Dec-2020		5997.9	33.8	5828.5	0															80720	78400	2320												68												0	44
A003				1672		Core Product Delivery Portfolio	Portfolio														22-Dec-2020	24-May-2021	110	spadmin	98	22-Dec-2020																																		69													44
A004				3594		IT Platform Portfolio	Portfolio														22-Dec-2020	24-May-2021	110	spadmin	98	22-Dec-2020																																		70													44
A007	A004	0		3660		Business Continuity Management	Project														02-Jan-2021	08-Mar-2021	46	spadmin	43	02-Jan-2021		1830.4	89.6	1216	0															61440	52480	8960												4696													44
A008	A002	0		86		Centralized Billing and Receivables	Project														23-Dec-2020	12-May-2021	101	spadmin	90	23-Dec-2020		405.6	0	405.6	0															7920	7920	0												4580													44
A009	A003	0		1727		Continuous Improvement Transformation	Project														28-Dec-2020	09-May-2021	95	spadmin	87	28-Dec-2020		562	18.9	454.8	0															31360	30000	1360												3750													44
A010	A009	0		2060		Constant Internal Delivery Enablement	Sub-Project														05-Jan-2021	30-Mar-2021	61	spadmin	59	05-Jan-2021		459.8	7.2	422.2	0															26320	25600	720												3958													44
A011	A003	0		2795		Core Operations Program	Project														05-Jan-2021	11-May-2021	91	spadmin	89	05-Jan-2021		4531.2	0	4531.2	0															0	0	0												3706													44
A012	A004	0		4052		Digital Workplace - Transformation	Project														09-Jan-2021	18-Apr-2021	70	spadmin	70			5766.4	0	5766.4	0															0	0	0												4158													44
A013	A002	0		1102		HR Service Delivery	Project														16-Jan-2021	01-May-2021	75	spadmin	75			265.5	0	265.5	0															24120	24120	0												3828													44
A017	A008	0		137		Billing Strategy and Policy Review	Sub-Project														30-Dec-2020	03-Apr-2021	68	spadmin	62	30-Dec-2020		106.8	0	106.8	0															5840	5840	0												6430													44
A018	A026	0		844		Classified data in Public Cloud	Sub-Project														26-Dec-2020	17-Apr-2021	80	spadmin	72	26-Dec-2020		0	0	0	0															0	0	0												6582													44
A019	A009	0		1780		Database Upgrade Market Datamart	Sub-Project														01-Jan-2021	06-Feb-2021	26	spadmin	22	01-Jan-2021		102.2	11.7	32.6	0															5040	4400	640												3886													44
A020	A008	0		438		ERP Procurement Module Renewal	Sub-Project														21-Jan-2021	27-Mar-2021	47	spadmin	47			298.8	0	298.8	0															2080	2080	0												4332													44
A021	A011	0		2864		Extend WWT to support AI	Sub-Project														09-Jan-2021	03-Mar-2021	38	spadmin	38			1126.4	0	1126.4	0															0	0	0												3830													44
A022	A011	0		3123		Google Maps Integration	Sub-Project														08-Jan-2021	05-Mar-2021	41	spadmin	41			3404.8	0	3404.8	0															0	0	0												4086													44
A023	A013	0		1157		HR Policy Update	Sub-Project														22-Jan-2021	06-Apr-2021	53	spadmin	53			128.4	0	128.4	0															12840	12840	0												4552													44
A024	A013	0		1437		HR SAP Envisioning	Sub-Project														24-Jan-2021	20-Apr-2021	62	spadmin	62			137.1	0	137.1	0															11280	11280	0												4116													44
A026	A002	0		793		IM Policy and Guidelines	Project														23-Dec-2020	27-May-2021	112	spadmin	101	23-Dec-2020		89.6	8.8	0	100															0	0	0												4176													44
A027	A026	0		2608		Internal IM Policy Modernization	Sub-Project														31-Dec-2020	24-Mar-2021	60	spadmin	55	31-Dec-2020		48	4	0	100															0	0	0												4288													44
A029	A012	0		4485		Private Cloud Phase 1	Sub-Project														16-Jan-2021	08-Apr-2021	59	spadmin	59			3180.8	0	3180.8	0															0	0	0												3970													44
A030	A012	0		4103		Public Cloud Phase 1	Sub-Project														12-Jan-2021	06-Apr-2021	61	spadmin	61			2585.6	0	2585.6	0															0	0	0												5374													44
A031	A007	0		3721		SAP Platform Upgrade	Sub-Project														04-Jan-2021	04-Mar-2021	44	spadmin	41	04-Jan-2021		1830.4	89.6	1216	0															61440	52480	8960												5246													44
A033	A026	0		1823		TBS Compliance	Sub-Project														27-Mar-2021	19-May-2021	38	spadmin	38			60.8	0	60.8	0															0	0	0												4951													44
A036	A009	0		2566		Upgrade Ticketing System	Sub-Project														01-Jan-2021	12-Feb-2021	31	spadmin	27	01-Jan-2021		0	0	0	0															0	0	0												3860													44
A041	A033	0		1868		Judgement Estimate (Class C)	Task														03-Apr-2021	22-May-2021	35	spadmin	35			28	0	28	0															0	0	0					100	1						5005										801	8	10	44
A044	A036	0		2624		Bottom Up Estimate (Class A)	Task														03-Jan-2021	19-Jan-2021	12	spadmin	9	03-Jan-2021		0	0	0	0															0	0	0					150	1						3876										805	8	20	44
A045	A044	0		2624		Plan and Execute Upgrade	Task														02-Feb-2021	18-Feb-2021	13	spadmin	13			0	136.8	0	0															0	0	13680					200	1						3886										807	8	20	44
A046	A024	0		1485		Judgement Estimate (Class C)	Task														28-Jan-2021	24-Mar-2021	40	spadmin	40			137.1	0	137.1	0															11280	11280	0					250	1						4096										812	8	20	44
A047	A017	0		185		Bottom Up Estimate (Class A)	Task														03-Jan-2021	05-Mar-2021	45	spadmin	42	03-Jan-2021		0	0	0	0															0	0	0					300	1						4212										0	8	0	44
A048	A017	0		224		Phase 1 Design and Procurement	Task														20-Jan-2021	15-Mar-2021	39	spadmin	39			106.8	0	106.8	0															5840	5840	0					350	1						4250										0	8	0	44
A049	A021	0		2858		Judgement Estimate (Class C)	Task														08-Mar-2021	27-Apr-2021	37	spadmin	37			1126.4	0	1126.4	0															0	0	0					400	1						4300										808	8	50	44
A054	A023	0		1215		Judgement Estimate (Class C)	Task														31-Jan-2021	31-Mar-2021	43	spadmin	43			128.4	0	128.4	0															12840	12840	0					450	1						4098										802	8	10	44
A055	A029	0		4549		Judgement Estimate (Class C)	Task														17-Jan-2021	07-Apr-2021	58	spadmin	58			3180.8	0	3180.8	0															0	0	0					500	1						4104										801	8	10	44
A058	A027	0		2659		Judgement Estimate (Class C)	Task														02-Jan-2021	19-Mar-2021	55	spadmin	52	02-Jan-2021		44	2.4	0	100															0	0	0					550	1						4040										805	8	10	44
A059	A020	0		479		Judgement Estimate (Class C)	Task														26-Jan-2021	28-Mar-2021	44	spadmin	44			298.8	0	298.8	0															2080	2080	0					600	1						4134										804	8	10	44
A061	A019	0		1830		Judgement Estimate (Class C)	Task														03-Jan-2021	08-Feb-2021	26	spadmin	23	03-Jan-2021		102.2	11.7	32.6	0															5040	4400	640					650	1						3992										807	8	20	44
A062	A010	0		2111		Judgement Estimate (Class C)	Task														07-Jan-2021	01-Apr-2021	61	spadmin	61			459.8	7.2	422.2	0															26320	25600	720					700	1						3584										812	8	20	44
A064	A030	0		4153		Judgement Estimate (Class C)	Task														13-Jan-2021	06-Apr-2021	60	spadmin	60			2585.6	0	2585.6	0															0	0	0					750	1						11882										0	8	0	44
A065	A022	0		3178		Judgement Estimate (Class C)	Task														17-Jan-2021	13-Mar-2021	40	spadmin	40			3404.8	0	3404.8	0															0	0	0					800	1						10824										0	8	0	44
A068	A018	0		886		Judgement Estimate (Class C)	Task														30-Dec-2020	11-Mar-2021	52	spadmin	46	30-Dec-2020		0	0	0	0															0	0	0					850	1						10916										0	8	0	44
A069	A031	0		3761		Judgement Estimate (Class C)	Task														05-Jan-2021	04-Mar-2021	43	spadmin	41	05-Jan-2021		1830.4	89.6	1216	0															61440	52480	8960					900	1						4100										802	8	10	44
A107	A041	0		1943		Developer General	Allocation														04-Apr-2021	23-Feb-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	0	0	1									5525										801	8	10	44
A108	A041	0		2004		SME Finance	Allocation														24-Apr-2021	09-Mar-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	100	0	1									5445										805	8	10	44
A109	A041	0		2050		SME HR	Allocation														06-May-2021	01-Apr-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	100	0	1									5237										804	8	10	44
A110	A041	0		2002		SME IT Platforms and Datacenter	Allocation														05-May-2021	22-Mar-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	100	0	1									5173										807	8	10	44
A111	A041	0		1940		SME PM	Allocation														18-Apr-2021	23-Feb-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	100	0	1									5133										812	8	10	44
A112	A041	0		1942		SME Solution Architecture	Allocation														09-May-2021	13-Apr-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	0	0	1									8863										800	8	11	44
A113	A041	0		1941		Tester New Software	Allocation														26-Apr-2021	13-Mar-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	0	0	1									8947										800	8	12	44
A121	A045	0		1707		Ally HR	Allocation														07-Sep-2020	16-Oct-2020	30	spadmin	0	07-Sep-2020	16-Oct-2020	0	24	0	100													0	0	0	0	2400	100	0	1									4732										802	8	10	44
A122	A045	0		1670		Cathy Test	Allocation														21-Aug-2020	29-Sep-2020	28	spadmin	0	21-Aug-2020	29-Sep-2020	0	44.8	0	100													0	0	0	0	4480	100	0	1									4686										801	8	20	44
A123	A045	0		1631		Chris Java	Allocation														21-Aug-2020	29-Sep-2020	28	spadmin	0	21-Aug-2020	29-Sep-2020	0	22.4	0	100													0	0	0	0	2240	100	0	1									4480										805	8	10	44
A124	A045	0		1586		Jack Project	Allocation														20-Aug-2020	28-Sep-2020	28	spadmin	0	20-Aug-2020	28-Sep-2020	0	22.4	0	100													0	0	0	0	2240	100	0	1									4262										804	8	10	44
A125	A045	0		1775		Jay Script	Allocation														06-Sep-2020	15-Oct-2020	29	spadmin	0	06-Sep-2020	15-Oct-2020	0	23.2	0	100													0	0	0	0	2320	100	0	1									4446										807	8	10	44
A126	A046	0		1520		Developer General	Allocation														28-Jan-2021	04-Feb-2021	6	spadmin	6			4.8	0	4.8	0													0	0	480	480	0	100	0	1									4434										812	8	10	44
A127	A046	0		1523		SME Finance	Allocation														05-Feb-2021	16-Feb-2021	8	spadmin	8			7	0	7	0													0	0	0	0	0	0	0	1									13954										800	8	11	44
A128	A046	0		1520		SME HR	Allocation														17-Feb-2021	12-Mar-2021	18	spadmin	18			17.3	0	17.3	0													0	0	0	0	0	0	0	1									14006										800	8	12	44
A129	A046	0		1569		SME IT Platforms and Datacenter	Allocation														29-Jan-2021	15-Feb-2021	12	spadmin	12			48	0	48	0													0	0	4800	4800	0	100	0	1									4466										808	8	50	44
A130	A046	0		1572		SME PM	Allocation														16-Feb-2021	08-Mar-2021	15	spadmin	15			12	0	12	0													0	0	1200	1200	0	100	0	1									4666										802	8	10	44
A131	A046	0		1617		SME Solution Architecture	Allocation														16-Feb-2021	19-Mar-2021	24	spadmin	24			38.4	0	38.4	0													0	0	3840	3840	0	100	0	1									0										801	8	20	44
A132	A046	0		1612		Tester New Software	Allocation														29-Jan-2021	15-Feb-2021	12	spadmin	12			9.6	0	9.6	0													0	0	960	960	0	100	0	1									4766										805	8	10	44
A133	A048	0		369		Jack Project	Allocation														04-Feb-2021	17-Mar-2021	30	spadmin	30			24	0	24	0													0	0	2400	2400	0	100	0	1									4352										804	8	10	44
A134	A048	0		317		Jay Script	Allocation														06-Mar-2021	31-Mar-2021	18	spadmin	18			14.4	0	14.4	0													0	0	1440	1440	0	100	0	1									4568										807	8	10	44
A135	A048	0		315		Jean Radio	Allocation														24-Jan-2021	28-Feb-2021	25	spadmin	25			20	0	20	0													0	0	2000	2000	0	100	0	1									4430										812	8	10	44
A136	A048	0		266		Jill Road	Allocation														24-Feb-2021	08-Apr-2021	32	spadmin	32			28.2	0	28.2	0													0	0	0	0	0	0	0	1									4211										800	8	11	44
A137	A048	0		269		Jim Azure	Allocation														22-Jan-2021	20-Feb-2021	21	spadmin	21			20.2	0	20.2	0													0	0	0	0	0	0	0	1									12897										800	8	12	44
A138	A049	0		2904		Developer ERP System	Allocation														08-Mar-2021	04-Apr-2021	20	spadmin	20			0	0	0	0													0	0	0	0	0	0	0	1									8783										800	8	13	44
A139	A049	0		2935		Developer General	Allocation														30-Mar-2021	22-Apr-2021	18	spadmin	18			0	0	0	0													0	0	0	0	0	0	0	1									8817										800	8	14	44
A140	A049	0		2984		Developer SQL	Allocation														27-Mar-2021	17-Apr-2021	15	spadmin	15			480	0	480	0													0	0	0	0	0	100	0	1									4595										811	8	25	44
A141	A049	0		2943		SME Solution Architecture	Allocation														08-Mar-2021	26-Mar-2021	15	spadmin	15			480	0	480	0													0	0	0	0	0	100	0	1									4819										808	8	25	44
A142	A049	0		2984		Tester Platforms and Datacenter	Allocation														09-Mar-2021	25-Mar-2021	13	spadmin	13			166.4	0	166.4	0													0	0	0	0	0	100	0	1									4837										810	8	10	44
A191	A054	0		1390		Developer General	Allocation														27-Feb-2021	31-Mar-2021	23	spadmin	23			18.4	0	18.4	0													0	0	1840	1840	0	100	0	1									4609										809	8	10	44
A192	A054	0		1257		SME Finance	Allocation														02-Feb-2021	24-Feb-2021	17	spadmin	17			34	0	34	0													0	0	3400	3400	0	100	0	1									4375										816	8	25	44
A193	A054	0		1258		SME HR	Allocation														25-Feb-2021	31-Mar-2021	25	spadmin	25			20	0	20	0													0	0	2000	2000	0	100	0	1									4191										815	8	10	44
A194	A054	0		1303		SME IT Platforms and Datacenter	Allocation														02-Feb-2021	09-Mar-2021	26	spadmin	26			20.8	0	20.8	0													0	0	2080	2080	0	100	0	1									4027										814	8	10	44
A196	A054	0		1346		SME Solution Architecture	Allocation														02-Feb-2021	11-Mar-2021	28	spadmin	28			22.4	0	22.4	0													0	0	2240	2240	0	100	0	1									4019										800	8	10	44
A197	A054	0		1390		Tester New Software	Allocation														04-Feb-2021	25-Feb-2021	16	spadmin	16			12.8	0	12.8	0													0	0	1280	1280	0	100	0	1									4061										806	8	10	44
A198	A055	0		4600		Developer General	Allocation														20-Feb-2021	13-Mar-2021	15	spadmin	15			384	0	384	0													0	0	0	0	0	100	0	1									4375										802	8	20	44
A199	A055	0		4685		Product Owner/Sponsor	Allocation														21-Jan-2021	18-Feb-2021	21	spadmin	21			268.8	0	268.8	0													0	0	0	0	0	100	0	1									4377										801	8	10	44
A200	A055	0		4601		SME Cloud Technologies	Allocation														13-Mar-2021	06-Apr-2021	17	spadmin	17			217.6	0	217.6	0													0	0	0	0	0	100	0	1									4149										805	8	10	44
A201	A055	0		4741		SME Finance	Allocation														11-Mar-2021	03-Apr-2021	17	spadmin	17			544	0	544	0													0	0	0	0	0	100	0	1									3927										804	8	25	44
A202	A055	0		4701		SME HR	Allocation														22-Feb-2021	21-Mar-2021	20	spadmin	20			256	0	256	0													0	0	0	0	0	100	0	1									4189										803	8	10	44
A203	A055	0		4749		SME IT Platforms and Datacenter	Allocation														06-Feb-2021	06-Mar-2021	20	spadmin	20			512	0	512	0													0	0	0	0	0	100	0	1									4115										807	8	20	44
A204	A055	0		4719		SME PM	Allocation														19-Jan-2021	05-Feb-2021	14	spadmin	14			358.4	0	358.4	0													0	0	0	0	0	100	0	1									4121										812	8	21	44
A205	A055	0		4601		SME Solution Architecture	Allocation														18-Jan-2021	19-Feb-2021	25	spadmin	25			0	0	0	0													0	0	0	0	0	0	0	1									7671										800	8	22	44
A206	A055	0		4638		Tester New Software	Allocation														18-Jan-2021	25-Feb-2021	29	spadmin	29			0	0	0	0													0	0	0	0	0	0	0	1									7699										800	8	23	44
A207	A055	0		4650		Tester Platforms and Datacenter	Allocation														02-Mar-2021	29-Mar-2021	20	spadmin	20			640	0	640	0													0	0	0	0	0	100	0	1									3513										811	8	25	44
A233	A058	0		2785		SME Finance	Allocation														23-Feb-2021	13-Mar-2021	14	spadmin	14			28	0	28	0													0	0	2800	2800	0	100	0	1									3845										808	8	25	44
A234	A058	0		2714		SME HR	Allocation														18-Feb-2021	07-Mar-2021	12	spadmin	12			9.6	0	9.6	0													0	0	960	960	0	100	0	1									3877										810	8	10	44
A235	A058	0		2721		SME IT Platforms and Datacenter	Allocation														28-Jan-2021	16-Feb-2021	14	spadmin	14			22.4	0	22.4	0													0	0	2240	2240	0	100	0	1									3651										807	8	20	44
A236	A058	0		2710		SME PM	Allocation														03-Jan-2021	16-Jan-2021	10	spadmin	7	03-Jan-2021		16	4.8	0	100													0	0	1600	1120	480	100	0	1									3643										813	8	20	44
A237	A058	0		2781		SME Solution Architecture	Allocation														26-Jan-2021	14-Feb-2021	14	spadmin	14			23.5	0	23.5	0													0	0	0	0	0	0	0	1									14185										800	8	21	44
A238	A058	0		2772		Tester New Software	Allocation														03-Jan-2021	13-Jan-2021	8	spadmin	5	03-Jan-2021		14.1	5.3	0	100													0	0	0	0	0	0	0	1									14223										800	8	22	44
A239	A059	0		710		Developer General	Allocation														27-Jan-2021	01-Apr-2021	47	spadmin	47			86.5	0	86.5	0													0	0	0	0	0	0	0	1									14531										800	8	23	44
A240	A059	0		663		SME Finance	Allocation														28-Feb-2021	23-Mar-2021	17	spadmin	17			54.4	0	54.4	0													0	0	0	0	0	0	0	1									3832										701	8	40	44
A241	A059	0		536		SME HR	Allocation														26-Jan-2021	13-Feb-2021	14	spadmin	14			33.6	0	33.6	0													0	0	0	0	0	0	0	1									3708										712	8	30	44
A242	A059	0		539		SME IT Platforms and Datacenter	Allocation														16-Feb-2021	11-Mar-2021	18	spadmin	18			28.8	0	28.8	0													0	0	0	0	0	0	0	1									3750										719	8	20	44
A243	A059	0		538		SME PM	Allocation														13-Mar-2021	28-Mar-2021	10	spadmin	10			32	0	32	0													0	0	0	0	0	0	0	1									3782										704	8	40	44
A244	A059	0		602		SME Purchasing	Allocation														28-Jan-2021	14-Feb-2021	12	spadmin	12			19.2	0	19.2	0													0	0	0	0	0	0	0	1									3788										709	8	20	44
A245	A059	0		608		SME Solution Architecture	Allocation														18-Feb-2021	08-Mar-2021	13	spadmin	13			20.8	0	20.8	0													0	0	2080	2080	0	100	0	1									3977										813	8	20	44
A246	A059	0		655		Tester New Software	Allocation														06-Feb-2021	25-Feb-2021	14	spadmin	14			23.5	0	23.5	0													0	0	0	0	0	0	0	1									12279										800	8	21	44
A264	A061	0		1881		Developer ERP System	Allocation														04-Jan-2021	31-Jan-2021	20	spadmin	17	04-Jan-2021		35.2	5.3	0	100													0	0	0	0	0	0	0	1									12929										800	8	22	44
A265	A061	0		1982		Developer General	Allocation														03-Feb-2021	15-Feb-2021	9	spadmin	9			16.6	0	16.6	0													0	0	0	0	0	0	0	1									12975										800	8	23	44
A266	A061	0		1923		Developer SQL	Allocation														06-Feb-2021	17-Feb-2021	8	spadmin	8			16	0	16	0													0	0	1600	1600	0	100	0	1									3737										811	8	25	44
A267	A061	0		1982		SME Solution Architecture	Allocation														05-Jan-2021	20-Jan-2021	12	spadmin	10	05-Jan-2021		24	4	0	100													0	0	2400	2000	400	100	0	1									3959										808	8	25	44
A268	A061	0		1923		Tester Platforms and Datacenter	Allocation														04-Jan-2021	20-Jan-2021	13	spadmin	10	04-Jan-2021		10.4	2.4	0	100													0	0	1040	800	240	100	0	1									3931										810	8	10	44
A269	A062	0		2226		Developer ERP System	Allocation														12-Feb-2021	23-Mar-2021	28	spadmin	28			44.8	0	44.8	0													0	0	4480	4480	0	100	0	1									3523										807	8	20	44
A270	A062	0		2279		Developer General	Allocation														06-Mar-2021	09-Apr-2021	25	spadmin	25			40	0	40	0													0	0	4000	4000	0	100	0	1									3527										813	8	20	44
A271	A062	0		2452		Developer SQL	Allocation														08-Mar-2021	06-Apr-2021	22	spadmin	22			37	0	37	0													0	0	0	0	0	0	0	1									10897										800	8	21	44
A272	A062	0		2497		Developer Web	Allocation														14-Mar-2021	09-Apr-2021	20	spadmin	20			35.2	0	35.2	0													0	0	0	0	0	0	0	1									10931										800	8	22	44
A273	A062	0		2494		Engineer Antennas	Allocation														18-Feb-2021	11-Mar-2021	16	spadmin	16			32	0	32	0													0	0	3200	3200	0	100	0	1									3585										811	8	25	44
A274	A062	0		2489		Engineer Hardware	Allocation														31-Jan-2021	16-Feb-2021	12	spadmin	12			24	0	24	0													0	0	2400	2400	0	100	0	1									3499										808	8	25	44
A275	A062	0		2490		Engineer RF	Allocation														04-Jan-2021	18-Jan-2021	11	spadmin	8	04-Jan-2021		8.8	2.4	0	100													0	0	880	640	240	100	0	1									3483										810	8	10	44
A276	A062	0		2431		Product Owner/Sponsor	Allocation														04-Jan-2021	27-Jan-2021	18	spadmin	15	04-Jan-2021		28.8	4.8	0	100													0	0	2880	2400	480	100	0	1									3499										807	8	20	44
A277	A062	0		2228		SME Cloud Technologies	Allocation														08-Jan-2021	31-Jan-2021	16	spadmin	16			25.6	0	25.6	0													0	0	2560	2560	0	100	0	1									3517										813	8	20	44
A278	A062	0		2377		SME Finance	Allocation														02-Mar-2021	07-Apr-2021	27	spadmin	27			45.4	0	45.4	0													0	0	0	0	0	0	0	1									3938										800	8	21	44
A279	A062	0		2322		SME HR	Allocation														02-Mar-2021	02-Apr-2021	24	spadmin	24			42.2	0	42.2	0													0	0	0	0	0	0	0	1									8438										800	8	22	44
A280	A062	0		2449		SME IT Platforms and Datacenter	Allocation														07-Feb-2021	06-Mar-2021	20	spadmin	20			36.8	0	36.8	0													0	0	0	0	0	0	0	1									10256										800	8	23	44
A281	A062	0		2324		SME PM	Allocation														06-Jan-2021	29-Jan-2021	0	spadmin	0			0	0	0	0													0	0	0	0	0	0	0	1									10296										800	8	24	44
A282	A062	0		2273		SME Purchasing	Allocation														11-Feb-2021	03-Mar-2021	15	spadmin	15			12	0	12	0													0	0	1200	1200	0	100	0	1									3274										808	8	10	44
A283	A062	0		2378		SME Solution Architecture	Allocation														04-Feb-2021	25-Feb-2021	16	spadmin	16			12.8	0	12.8	0													0	0	1280	1280	0	100	0	1									3694										802	8	10	44
A284	A062	0		2324		Tester New Software	Allocation														05-Feb-2021	23-Feb-2021	13	spadmin	13			20.8	0	20.8	0													0	0	2080	2080	0	100	0	1									3510										801	8	20	44
A285	A062	0		2271		Tester Platforms and Datacenter	Allocation														07-Jan-2021	29-Jan-2021	17	spadmin	17			13.6	0	13.6	0													0	0	1360	1360	0	100	0	1									3258										805	8	10	44
A296	A064	0		4203		Developer General	Allocation														21-Mar-2021	03-Apr-2021	10	spadmin	10			128	0	128	0													0	0	0	0	0	100	0	1									3808										804	8	10	44
A297	A064	0		4252		Product Owner/Sponsor	Allocation														02-Mar-2021	22-Mar-2021	15	spadmin	15			576	0	576	0													0	0	0	0	0	100	0	1									3588										803	8	30	44
A298	A064	0		4253		SME Cloud Technologies	Allocation														10-Feb-2021	02-Mar-2021	15	spadmin	15			192	0	192	0													0	0	0	0	0	100	0	1									3780										807	8	10	44
A299	A064	0		4304		SME Finance	Allocation														22-Feb-2021	14-Mar-2021	15	spadmin	15			192	0	192	0													0	0	0	0	0	100	0	1									3580										812	8	10	44
A300	A064	0		4301		SME HR	Allocation														14-Jan-2021	03-Feb-2021	15	spadmin	15			0	0	0	0													0	0	0	0	0	0	0	1									6752										800	8	11	44
A301	A064	0		4300		SME IT Platforms and Datacenter	Allocation														01-Feb-2021	19-Feb-2021	15	spadmin	15			0	0	0	0													0	0	0	0	0	0	0	1									9894										800	8	12	44
A302	A064	0		4353		SME PM	Allocation														13-Jan-2021	19-Mar-2021	48	spadmin	48			614.4	0	614.4	0													0	0	0	0	0	100	0	1									3738										807	8	10	44
A303	A064	0		4204		SME Purchasing	Allocation														14-Feb-2021	19-Mar-2021	25	spadmin	25			320	0	320	0													0	0	0	0	0	100	0	1									3738										812	8	10	44
A304	A064	0		4204		SME Solution Architecture	Allocation														13-Jan-2021	11-Feb-2021	22	spadmin	22			563.2	0	563.2	0													0	0	0	0	0	100	0	1									4164										813	8	20	44
A305	A064	0		4252		Tester New Software	Allocation														16-Jan-2021	07-Feb-2021	15	spadmin	15			0	0	0	0													0	0	0	0	0	0	0	1									9930										800	8	21	44
A307	A065	0		3443		Developer ERP System	Allocation														26-Jan-2021	08-Mar-2021	30	spadmin	30			1920	0	1920	0													0	0	0	0	0	100	0	1									4012										808	8	50	44
A308	A065	0		3248		Developer General	Allocation														18-Jan-2021	13-Mar-2021	40	spadmin	40			512	0	512	0													0	0	0	0	0	100	0	1									3716										800	8	10	44
A309	A065	0		3395		Developer SQL	Allocation														16-Jan-2021	19-Feb-2021	25	spadmin	25			320	0	320	0													0	0	0	0	0	100	0	1									4228										806	8	10	44
A310	A065	0		3290		SME Solution Architecture	Allocation														18-Jan-2021	21-Feb-2021	25	spadmin	25			320	0	320	0													0	0	0	0	0	100	0	1									4208										802	8	10	44
A311	A065	0		3337		Tester Platforms and Datacenter	Allocation														19-Jan-2021	23-Feb-2021	26	spadmin	26			332.8	0	332.8	0													0	0	0	0	0	100	0	1									4034										801	8	10	44
A327	A068	0		932		SME Finance	Allocation														03-Jan-2021	26-Jan-2021	17	spadmin	14	03-Jan-2021		13.6	2.4	0	100													0	0	1360	1120	240	100	0	1									3880										805	8	10	44
A328	A068	0		1071		SME HR	Allocation														17-Feb-2021	16-Mar-2021	20	spadmin	20			16	0	16	0													0	0	1600	1600	0	100	0	1									3686										804	8	10	44
A329	A068	0		940		SME IT Platforms and Datacenter	Allocation														10-Feb-2021	15-Mar-2021	24	spadmin	24			21.1	0	21.1	0													0	0	0	0	0	0	0	1									9346										800	8	11	44
A330	A068	0		1001		SME PM	Allocation														10-Feb-2021	10-Mar-2021	21	spadmin	21			33.6	0	33.6	0													0	0	3360	3360	0	100	0	1									3986										803	8	20	44
A331	A068	0		1058		SME Solution Architecture	Allocation														13-Jan-2021	15-Feb-2021	24	spadmin	24			19.2	0	19.2	0													0	0	1920	1920	0	100	0	1									3656										807	8	10	44
A332	A068	0		995		Tester New Software	Allocation														02-Jan-2021	30-Jan-2021	20	spadmin	17	02-Jan-2021		16	2.4	0	100													0	0	1600	1360	240	100	0	1									3696										812	8	10	44
A333	A069	0		3812		Developer General	Allocation														16-Jan-2021	12-Mar-2021	40	spadmin	40			0	0	0	0													0	0	0	0	0	0	0	1									9220										800	8	11	44
A334	A069	0		3935		SME Finance	Allocation														27-Feb-2021	11-Mar-2021	9	spadmin	9			576	0	576	0													0	0	0	0	0	100	0	1									4166										808	8	50	44
A335	A069	0		3867		SME HR	Allocation														08-Feb-2021	08-Mar-2021	21	spadmin	21			268.8	0	268.8	0													0	0	0	0	0	100	0	1									3978										800	8	10	44
A336	A069	0		3879		SME IT Platforms and Datacenter	Allocation														05-Jan-2021	27-Jan-2021	17	spadmin	15	05-Jan-2021		217.6	25.6	0	100													0	0	21760	19200	2560	100	0	1									3776										806	8	10	44
A337	A069	0		3928		SME PM	Allocation														05-Feb-2021	25-Feb-2021	15	spadmin	15			192	0	192	0													0	0	0	0	0	100	0	1									3892										802	8	10	44
A338	A069	0		3927		SME Purchasing	Allocation														05-Jan-2021	26-Jan-2021	16	spadmin	14	05-Jan-2021		204.8	25.6	0	100													0	0	20480	17920	2560	100	0	1									3508										801	8	10	44
A339	A069	0		3988		SME Solution Architecture	Allocation														02-Feb-2021	19-Feb-2021	14	spadmin	14			179.2	0	179.2	0													0	0	0	0	0	100	0	1									3696										805	8	10	44
A340	A069	0		3989		Tester New Software	Allocation														04-Jan-2021	22-Jan-2021	15	spadmin	12	04-Jan-2021		192	38.4	0	100													0	0	19200	15360	3840	100	0	1									3496										804	8	10	44
Import Data

## MetaData
tbMDID	tbMDName	tbMDSeverity	tbMDProjectNumber	tbMDDescription	tbMDNotes	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDResponsibility	tbMDDepartment	tbMDExSponsor	tbMDHealth	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDROMEstimate	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSize	tbMDStageApprover	tbMDWrittenBy	tbMDBusinessAdvisor	tbMDBusinessOwner	tbMDDeliveryManager	tbMDOrgManager	tbMDPriorityStrategic	tbMDSponsoringDepartment	tbMDPrimaryContact	tbMDBenefitCostRatio	tbMDContactNumber	tbMDResponsibleTeam	tbMDRiskVsSizeAndComplexity	tbMDEcnomicValueAdded	tbMDEstimationClass	tbMDInternalRateOfReturn	tbMDSprintName	tbMDSunkCosts	tbMDSyncNotes	tbMDNotesProject	tbMDContractNumber	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDPrimaryLineOfBusiness	tbMDBackgroundInfo	tbMDCapabilitiesNeeded	tbMDConsequence	tbMDExpectedBenfits	tbMDProblemOpportunity	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommittment	tbMDStakeholderDescription	tbMDNotesWorkflow	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDSortOrder	tbMDtbLastModified	tbMDPM	tbMDProjectType	tbMDShowIn	tbMDYesNoSelector	tbMDProduct	tbMDContact	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDPrimarySkill	tbMDPrimaryRole	tbMDOther2	tbMDOther3	tbMDOther4	tbMDExtLink1	tbMDExtSystemID1	canvasNo	tbMDRefID
NWI Metdata																														Not Used	Not Used																												No manual entery	No manual entery	No manual entery	No manual entery	No manual entery	No manual entery	No manual entery	No manual entery
MDUID	MDName	tbType	Project Number	Description	Notes	Executive Summary	Priority	Status	State	Wf Stage	Phase	Gate	Category	Responsibility	Department	ExSponsor	Health	Heath OA	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	ROM Estimate	MD Portfolio	Program	Prog Activity Alignment	Size	Stage Approver	Written By	Business Advisor	Business Owner	Delivery Manager	Org Manager	Priority Strategic	Sponsoring Department	Primary Contact	Benefit Cost Ratio	Contact Number	Responsible Team	Risk Vs Size And Complexity	Ecnomic Value Added	Estimation Class	Internal Rate Of Return	Sprint Name	Sunk Costs	Sync Notes	Notes Project	Contract Number	Net Present Value	Opportunity Cost	Payback Period	Primary Line Of Business	BackgroundInfo	Capabilities Needed	Consequence	Expected Benfits	Problem Opportunity	Constraints Assumptions	Cost Benefit Analysis	Senior Level Committment	Stakeholder Description	Notes Workflow	Other5	Other6	Other7	Other8	Other9	Other10	Other11	Other12	Customer ID	AzureID	Name Short	Sort Order	Last Modified	PM	Project Type	ShowIn	YesNo Selector	Product	Contact	WBS	Weighting	Location	Primary Skill	Primary Role	Other2	Other3	Other4	ExtLink1	ExtSystemID1	canvasNo	RefID
A002	Business Continuity	Portfolio						Active						Information Technology	Customer Support Department	Sydney Sp	Red																																																												44
A003	Core Product Delivery Portfolio	Portfolio						Active						Procurement	Presidents Office	Colin Sp	Yellow																																																												44
A004	IT Platform Portfolio	Portfolio						Active						Procurement	Customer Support Department	Sydney Sp	Yellow																																																												44
A007	Business Continuity Management	Project						Active						Information Technology	Customer Support Department	Sydney Sp	Yellow																																																												44
A008	R&D New Technology Portfolio	Project	PF 05	This is my Brief Description	Enter project notes here		Critical	Active	Spawned	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Information Technology	Customer Support Department	Sydney Sp	Red	Red	Green	Red	Green	Green	Red	Red	Business Systems	Improve productivity	Transform	Increase share of market	501K to750K				Large	Erica Stg Apvr	Joe Who	Joe Ba	Sam bo	Al dm	Kent Om	High						Large		Class C		Not a Sprint	130							Business Technology Solutions																			44					Jim Pm				Display URT	Sam Pc
A009	Billing Strategy and Policy Review	Project	PJ 004	Review and report on findings	Enter project notes here		Low	Active	Spawned	1 Proposed	1 Pre-execution (evaluation and selection)	3 Approved to Implement	Cat 1	Procurement	Presidents Office	Colin Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow	Yellow	Business Support	Source Cloud services for our Core products	Run	Improve and maintain workplace safety	251K to 500K				Large	Erica Stg Apvr	Joe Who	Sally Ba	Julia bo	Jim Dm	Kent Om	High						Large		Class C		Not a Sprint	30							Business Development																			44					Al PM				Display URT	Dave Pc
A010	Building and Office Modernization Program	Sub-Project	PG 001	This program shall roll up all investments regarding our buildings and office space.	Enter project notes here		Medium	Active	Spawned	1 Proposed	1 Pre-execution (evaluation and selection)	2 Approved to Develop	Cat 1	Procurement	Customer Support Department	Sydney Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow	Yellow	Office Environment	Improve productivity	Grow the Business	Best in market core products	101K to250K				Large	Erica Stg Apvr	Joe Who	Joe Ba	Sam bo	Al dm	Kent Om	Medium						Large		Class C		Not a Sprint	30							Business Technology Solutions																			44					Jim Pm				SIT 5000	Sam Pc
A011	Business Continuity Management Program	Project	PG 016	This is my Brief Description	Enter project notes here			Active	Approved	1 Proposed	1 Pre-execution (evaluation and selection)	2 Approved to Develop	Cat 1	Information Technology	Customer Support Department	Sydney Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow	Yellow	Information Technology	Source Cloud services for our Core products	Run	Ensure compliance	750K Plus				Small	Julia Stg Apvr	Jim Cox	Joe Ba	Sam bo	Al dm	Perry Om	Medium						Medium		Class C		Not a Sprint	130							Corporate Affairs																			44					Jim Pm				SAP Financial System	Sam Pc
A012	Upgrade Ticketing System	Project	PJ 024	Enabling an employee experience that is simple, relevant and caring.	Enter project notes here		High	Active	Approved	1 Proposed	1 Pre-execution (evaluation and selection)	1 Approved to Design	Cat 1	Finance	IT Department	Marsha Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow	Yellow	Business Support	Support moden digital workplace	Run	Reduce waste	0 to 100K				Small	Julia Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Al dm	Perry Om	High						Medium		Class C		Not a Sprint	50							Research and Development																			44					PM011				SAP Financial System	Ben Pc
A013	Centralized Billing and Receivables Program	Project	PG 002	The objective of this initiative is to be able to apply life cycle management of unstructured content by providing an enterprise document and records management platform.	Enter project notes here		Medium	Active	Awaiting Review	1 Proposed	1 Pre-execution (evaluation and selection)	2 Approved to Develop	Cat 1	Finance	Customer Support Department	Sydney Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Faster response to new business opportunities	Run	Improve customer service	101K to250K				Medium	Ben Stg Apvr	Jim Cox	Joe Ba	Sam bo	Al dm	Perry Om	Medium						Small		Class C		Not a Sprint	130							Research and Development																			44					Jim Pm				FAM 6000	Sam Pc
A017	Classified data in Public Cloud	Sub-Project	PJ 012	A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	Enter project notes here			Cancelled	Approved	1 Proposed	1 Pre-execution (evaluation and selection)	2 Approved to Develop	Cat 1	Procurement	Customer Support Department	Sydney Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Source Cloud services for our Core products	Run	Become more Agile, less process	750K Plus				Small	Julia Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	Low						Medium		Class C		Not a Sprint	50							Business Development																			44					Jim Pm				FAM 6000	Sam Pc
A018	Continuous Improvement Transformation Program	Sub-Project	PG 017	This is my Brief Description	Enter project notes here		High	Active	Requested Approval	1 Proposed	1 Pre-execution (evaluation and selection)	1 Approved to Design	Cat 1	Product Engineering	IT Department	Marsha Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Information Technology	Support moden digital workplace	Run	Attract and retain the best people	0 to 100K				Medium	Ben Stg Apvr	Joe Who	Mike Ba	Joe Bo	Al dm	Kent Om	Low						Small		Class C		Not a Sprint	130							Engineering and Product Delivery																			44					PM011				SIT 5000	Ben Pc
A019	Continuous Internal Delivery Enablement Program	Sub-Project	PG 008	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Enter project notes here		Low	On-Hold	Awaiting Input	1 Proposed	1 Pre-execution (evaluation and selection)	2 Approved to Develop	Cat 1	Information Technology	Customer Support Department	Sydney Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Building Services	Cross-sell our Network Device products	Grow	Increase revenue	251K to 500K				Large	Erica Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	High						Large		Class C		Not a Sprint	30							Business Technology Solutions																			44					Jim Pm				FAM 6000	Sam Pc
A020	Core Operations Program	Sub-Project	PG 009	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	Enter project notes here		Critical	On-Hold	Awaiting Approval	1 Proposed	1 Pre-execution (evaluation and selection)	3 Approved to Implement	Cat 1	Accounting	Presidents Office	Colin Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Business Systems	Engineering Tool Innovation	Transform	Increase share of market	501K to750K				Small	Julia Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Medium						Medium		Class C		Not a Sprint	50							Corporate Affairs																			44					Al PM				Display URT	Dave Pc
A021	Automate selection system	Sub-Project	PJ 005	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here			On-Hold	Awaiting Review	1 Proposed	1 Pre-execution (evaluation and selection)	1 Approved to Design	Cat 1	Procurement	IT Department	Marsha Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Business Systems	Faster response to new business opportunities	Transform	Ensure compliance	750K Plus				Medium	Ben Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Jim Dm	Perry Om	Medium						Small		Class C		Not a Sprint	130							Engineering and Product Delivery																			44					PM011				SAP Financial System	Ben Pc
A022	Database Upgrade Market Datamart	Sub-Project	PJ 020	Study and make recommendations.	Enter project notes here		Low	Active	Approved	1 Proposed	1 Pre-execution (evaluation and selection)	3 Approved to Implement	Cat 1	Procurement	Presidents Office	Colin Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Information Technology	Source Cloud services for our Core products	Run	Attract and retain the best people	251K to 500K				Small	Julia Stg Apvr	Jim Cox	Sally Ba	Julia bo	Al dm	Perry Om	High						Medium		Class C		Not a Sprint	50							Finance																			44					Al PM				SAP Financial System	Dave Pc
A023	Digital Workplace - Transformation Program	Sub-Project	PG 012	Upgrade the collaboration sites in conjunction with business owners.	Enter project notes here		High	Active	Awaiting Approval	1 Proposed	1 Pre-execution (evaluation and selection)	1 Approved to Design	Cat 1	Product Engineering	IT Department	Marsha Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Building Services	Faster response to new business opportunities	Grow	Attract and retain the best people	0 to 100K				Small	Julia Stg Apvr	Joe Who	Mike Ba	Joe Bo	Jim Dm	Kent Om	Medium						Medium		Class C		Not a Sprint	50							Business Development																			44					PM011				Display URT	Ben Pc
A024	ERP Procurement Module Renewal	Sub-Project	PJ 009	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here			Active	Requested Approval	1 Proposed	1 Pre-execution (evaluation and selection)	3 Approved to Implement	Cat 1	Information Technology	Presidents Office	Colin Sp	Yellow	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Support moden digital workplace	Run	Server more customers	750K Plus				Medium	Ben Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Low						Small		Class C		Not a Sprint	130							Corporate Affairs																			44					Al PM				SIT 5000	Dave Pc
A026	Continuous Improvement Transformation Program	Project	PG 017	This is my Brief Description	Enter project notes here		High	Active	Requested Approval	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Product Engineering	IT Department	Marsha Sp	Yellow																Medium	Ben Stg Apvr	Joe Who	Mike Ba	Joe Bo	Al dm	Kent Om	Low						Small		Class C		Not a Sprint	130							Engineering and Product Delivery																			44					PM011				SIT 5000	Ben Pc
A027	Continuous Internal Delivery Enablement Program	Sub-Project	PG 008	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Enter project notes here		Low	On-Hold	Awaiting Input	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Information Technology	Customer Support Department	Sydney Sp	Yellow																Large	Erica Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	High						Large		Class C		Not a Sprint	30							Business Technology Solutions																			44					Jim Pm				FAM 6000	Sam Pc
A029	Core Operations Program	Sub-Project	PG 009	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	Enter project notes here		Critical	On-Hold	Awaiting Approval	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Accounting	Presidents Office	Colin Sp	Yellow																Small	Julia Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Medium						Medium		Class C		Not a Sprint	50							Corporate Affairs																			44					Al PM				Display URT	Dave Pc
A030	Automate selection system	Sub-Project	PJ 005	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here			On-Hold	Awaiting Review	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Procurement	IT Department	Marsha Sp	Yellow																Medium	Ben Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Jim Dm	Perry Om	Medium						Small		Class C		Not a Sprint	130							Engineering and Product Delivery																			44					PM011				SAP Financial System	Ben Pc
A031	Database Upgrade Market Datamart	Sub-Project	PJ 020	Study and make recommendations.	Enter project notes here		Low	Active	Approved	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Procurement	Presidents Office	Colin Sp	Yellow																Small	Julia Stg Apvr	Jim Cox	Sally Ba	Julia bo	Al dm	Perry Om	High						Medium		Class C		Not a Sprint	50							Finance																			44					Al PM				SAP Financial System	Dave Pc
A033	Digital Workplace - Transformation Program	Sub-Project	PG 012	Upgrade the collaboration sites in conjunction with business owners.	Enter project notes here		High	Active	Awaiting Approval	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Product Engineering	IT Department	Marsha Sp	Yellow																Small	Julia Stg Apvr	Joe Who	Mike Ba	Joe Bo	Jim Dm	Kent Om	Medium						Medium		Class C		Not a Sprint	50							Business Development																			44					PM011				Display URT	Ben Pc
A036	ERP Procurement Module Renewal	Sub-Project	PJ 009	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here			Active	Requested Approval	1 Proposed	1 Pre-execution (evaluation and selection)		Cat 1	Information Technology	Presidents Office	Colin Sp	Yellow																Medium	Ben Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Low						Small		Class C		Not a Sprint	130							Corporate Affairs																			44					Al PM				SIT 5000	Dave Pc
A041	Judgement Estimate (Class C)	Task																																																																											44
A044	Bottom Up Estimate (Class A)	Task																																																																											44
A045	Plan and Execute Upgrade	Task																																																																											44
A046	Judgement Estimate (Class C)	Task																																																																											44
A047	Bottom Up Estimate (Class A)	Task																																																																											44
A048	Phase 1 Design and Procurement	Task																																																																											44
A049	Judgement Estimate (Class C)	Task																																																																											44
A054	Judgement Estimate (Class C)	Task																																																																											44
A055	Judgement Estimate (Class C)	Task																																																																											44
A058	Judgement Estimate (Class C)	Task																																																																											44
A059	Judgement Estimate (Class C)	Task																																																																											44
A061	Judgement Estimate (Class C)	Task																																																																											44
A062	Judgement Estimate (Class C)	Task																																																																											44
A064	Judgement Estimate (Class C)	Task																																																																											44
A065	Judgement Estimate (Class C)	Task																																																																											44
A068	Judgement Estimate (Class C)	Task																																																																											44
A069	Judgement Estimate (Class C)	Task																																																																											44
A107	Developer General	Allocation																																																																											44
A108	SME Finance	Allocation																																																																											44
A109	SME HR	Allocation																																																																											44
A110	SME IT Platforms and Datacenter	Allocation																																																																											44
A111	SME PM	Allocation																																																																											44
A112	SME Solution Architecture	Allocation																																																																											44
A113	Tester New Software	Allocation																																																																											44
A121	Ally HR	Allocation																																																																											44
A122	Cathy Test	Allocation																																																																											44
A123	Chris Java	Allocation																																																																											44
A124	Jack Project	Allocation																																																																											44
A125	Jay Script	Allocation																																																																											44
A126	Developer General	Allocation																																																																											44
A127	SME Finance	Allocation																																																																											44
A128	SME HR	Allocation																																																																											44
A129	SME IT Platforms and Datacenter	Allocation																																																																											44
A130	SME PM	Allocation																																																																											44
A131	SME Solution Architecture	Allocation																																																																											44
A132	Tester New Software	Allocation																																																																											44
A133	Jack Project	Allocation																																																																											44
A134	Jay Script	Allocation																																																																											44
A135	Jean Radio	Allocation																																																																											44
A136	Jill Road	Allocation																																																																											44
A137	Jim Azure	Allocation																																																																											44
A138	Developer ERP System	Allocation																																																																											44
A139	Developer General	Allocation																																																																											44
A140	Developer SQL	Allocation																																																																											44
A141	SME Solution Architecture	Allocation																																																																											44
A142	Tester Platforms and Datacenter	Allocation																																																																											44
A191	Developer General	Allocation																																																																											44
A192	SME Finance	Allocation																																																																											44
A193	SME HR	Allocation																																																																											44
A194	SME IT Platforms and Datacenter	Allocation																																																																											44
A196	SME Solution Architecture	Allocation																																																																											44
A197	Tester New Software	Allocation																																																																											44
A198	Developer General	Allocation																																																																											44
A199	Product Owner/Sponsor	Allocation																																																																											44
A200	SME Cloud Technologies	Allocation																																																																											44
A201	SME Finance	Allocation																																																																											44
A202	SME HR	Allocation																																																																											44
A203	SME IT Platforms and Datacenter	Allocation																																																																											44
A204	SME PM	Allocation																																																																											44
A205	SME Solution Architecture	Allocation																																																																											44
A206	Tester New Software	Allocation																																																																											44
A207	Tester Platforms and Datacenter	Allocation																																																																											44
A233	SME Finance	Allocation																																																																											44
A234	SME HR	Allocation																																																																											44
A235	SME IT Platforms and Datacenter	Allocation																																																																											44
A236	SME PM	Allocation																																																																											44
A237	SME Solution Architecture	Allocation																																																																											44
A238	Tester New Software	Allocation																																																																											44
A239	Developer General	Allocation																																																																											44
A240	SME Finance	Allocation																																																																											44
A241	SME HR	Allocation																																																																											44
A242	SME IT Platforms and Datacenter	Allocation																																																																											44
A243	SME PM	Allocation																																																																											44
A244	SME Purchasing	Allocation																																																																											44
A245	SME Solution Architecture	Allocation																																																																											44
A246	Tester New Software	Allocation																																																																											44
A264	Developer ERP System	Allocation																																																																											44
A265	Developer General	Allocation																																																																											44
A266	Developer SQL	Allocation																																																																											44
A267	SME Solution Architecture	Allocation																																																																											44
A268	Tester Platforms and Datacenter	Allocation																																																																											44
A269	Developer ERP System	Allocation																																																																											44
A270	Developer General	Allocation																																																																											44
A271	Developer SQL	Allocation																																																																											44
A272	Developer Web	Allocation																																																																											44
A273	Engineer Antennas	Allocation																																																																											44
A274	Engineer Hardware	Allocation																																																																											44
A275	Engineer RF	Allocation																																																																											44
A276	Product Owner/Sponsor	Allocation																																																																											44
A277	SME Cloud Technologies	Allocation																																																																											44
A278	SME Finance	Allocation																																																																											44
A279	SME HR	Allocation																																																																											44
A280	SME IT Platforms and Datacenter	Allocation																																																																											44
A281	SME PM	Allocation																																																																											44
A282	SME Purchasing	Allocation																																																																											44
A283	SME Solution Architecture	Allocation																																																																											44
A284	Tester New Software	Allocation																																																																											44
A285	Tester Platforms and Datacenter	Allocation																																																																											44
A296	Developer General	Allocation																																																																											44
A297	Product Owner/Sponsor	Allocation																																																																											44
A298	SME Cloud Technologies	Allocation																																																																											44
A299	SME Finance	Allocation																																																																											44
A300	SME HR	Allocation																																																																											44
A301	SME IT Platforms and Datacenter	Allocation																																																																											44
A302	SME PM	Allocation																																																																											44
A303	SME Purchasing	Allocation																																																																											44
A304	SME Solution Architecture	Allocation																																																																											44
A305	Tester New Software	Allocation																																																																											44
A307	Developer ERP System	Allocation																																																																											44
A308	Developer General	Allocation																																																																											44
A309	Developer SQL	Allocation																																																																											44
A310	SME Solution Architecture	Allocation																																																																											44
A311	Tester Platforms and Datacenter	Allocation																																																																											44
A327	SME Finance	Allocation																																																																											44
A328	SME HR	Allocation																																																																											44
A329	SME IT Platforms and Datacenter	Allocation																																																																											44
A330	SME PM	Allocation																																																																											44
A331	SME Solution Architecture	Allocation																																																																											44
A332	Tester New Software	Allocation																																																																											44
A333	Developer General	Allocation																																																																											44
A334	SME Finance	Allocation																																																																											44
A335	SME HR	Allocation																																																																											44
A336	SME IT Platforms and Datacenter	Allocation																																																																											44
A337	SME PM	Allocation																																																																											44
A338	SME Purchasing	Allocation																																																																											44
A339	SME Solution Architecture	Allocation																																																																											44
A340	Tester New Software	Allocation																																																																											44
Import Data

## AdminPanel
apID	ap_name	apCustomerID	apFilteredFrom	apAzureID	apTS_WeeklyOrMonthly	apTS_WeeklyPxFactor	apTS_Start	apTS_Finish	apHelpCoordTop	apHelpCoordLeft	apTS_MonthlyPxFactor	apStatusDate	apFilteredFromTbID	ap_HolidayDate	ap_HolidayName	apSchMethod	apTbVisibleLevel	totalNumberOfPeople	numberOfPeoplePerLine	pxPerPerson	apHideCompletedBarsYN	showGhostBarsYN	showBaselineBarsYN
Timebar Application Settings
ID	Name	Customer ID	Filtered From	Azure ID	TS Weekly Or Monthly	TS Weekly Px Factor	TS Start	TSFinish	Help Coord Top	Help Coord Left	TS Monthly Px Factor	StatusDate	Filtered From Tb ID	Holiday Date	Holiday Name	Sch Method	Tb Visible Level	Total Number Of People	Number Of People Per Line	Px Per Person	Hide Completed Bars YN	Show Ghost Bars YN	Show Baseline Bars YN
1	Standard Config Settings	44	Canvas		Weekly	10	14-Dec-20		50	400	2	6-Jan-2021	NA			Standard	L5				false	No	No
2	Bar Graph Settings	44	Canvas															30	10	7
3	Standard Holidays	44	Canvas											25-Dec-2021	Christmas

## Setup
Importing					Validation and Formatting
Target Sheet	Location	File Name	Import	Setting		Target Sheet	Validate YN	ReFormat YN
Timebars	/media/jcox/JcoxSSD/Data_2020/Timebars Technical/Testing	tbTimebars.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Timebars	Yes	No
MetaData	/media/jcox/JcoxSSD/Data_2020/Timebars Technical/Testing	tbMetaData.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		MetaData	No	No
				Go!

Exporting
Target Sheet	Location	File Name	Export	Setting
Timebars	/media/jcox/JcoxSSD/Data_2020/Timebars Technical/Tb Training Manual/datafiles	tbTimebarsExportDec21.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
MetaData	/media/jcox/JcoxSSD/Data_2020/Timebars Technical/Tb Training Manual/datafiles	tbMetaDataExportDec21.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Portfolio	/media/jcox/JcoxSSD/Data_2020/Timebars Technical/Tb Training Manual/datafiles	tbPortfolioExportDec21.csv	No	59/44,34,76,1,,0,false,false,true,false,false

Export

	Mandatory Rules for Timebars and MetaData Sheets
	Must have Title in cell A2 – Enter any text to suit your needs to identify this data
	Must have the text: “UID” in cell A3

## Format for Fields
ID	MD Sheet	DataType	ID	TBCore Sht	DataType
0	tbMDID	text	0	tbID	text
1	tbMDName	text	1	tbSelfKey2	text
2	tbMDProjectType	text	2	tbCoordTop	number
3	tbMDPortfolio	text	3	tbCoordLeft	number
4	tbMDProgram	text	4	tbHierarchyOrder	number
5	tbMDExecutiveSummary	text	5	tbName	text
6	tbMDGate	date	6	tbType	text
7	tbMDDeliveryManager	text	7	tbL1	text
8	tbMDBusinessAdvisor	text	8	tbL2	text
9	tbMDBusinessOwner	text	9	tbL3	text
10	tbMDEstimationClass	text	10	tbL4	text
11	tbMDROMEstimate	text	11	tbL5	text
12	tbMDInvestmentCategory	text	12	tbOwner	text
13	tbMDInvestmentInitiative	text	13	tbStart	text
14	tbMDInvestmentObjective	text	14	tbFinish	date
15	tbMDInvestmentStrategy	text	15	tbDuration	text
16	tbMDPriorityStrategic	text	16	tbAStart	text
17	tbMDCustomerID	text	17	tbAFinish	text
18	tbMDAzureID	text	18	tbRemainingDuration	number
19	tbMDNameShort	text	19	tbResID	text
20	tbMDProjectNumber	text	20	tbCalendar	number
21	tbMDDescription	text	21	tbPercentTimeOn	number
22	tbMDNotes	text	22	tbWork	number
23	tbMDExtLink1	text	23	tbAWork	number
24	tbMDExtSystemID1	text	24	tbWorkRemaining	number
25	tbMDSortOrder	number	25	tbPercentComplete	number
26	tbMDtbLastModified	date	26	tbCost	number
27	tbMDPriority	text	27	tbAcost	number
28	tbMDStatus	text	28	tbCostRemaining	number
29	tbMDState	text	29	tbPayRate	number
30	tbMDSeverity	text	30	tbCostType	text
31	tbMDStage	text	31	tbCostID	text
32	tbMDPhase	text	32	tbConstraintType	text
33	tbMDCategory	text	33	tbConstraintDate	date
34	tbMDHealth	text	34	tbFloat	number
35	tbMDResponsibility	text	35	tbFreeFloat	number
36	tbMDDepartment	text	36	tbExpHoursPerWeek	number
37	tbMDExSponsor	text	37	canvasNo	number
38	tbMDPM	text	38	tbCustomerID	text
39	tbMDShowIn	text	39	tbMetaDataID	text
40	tbMDYesNoSelector	text	40	tbBLID	text
41	tbMDProduct	text	41	tbPredecessor	text
42	tbMDContact	text	42	tbAzureID	text
43	tbMDWBS	text	43	tbCoordRight	text
44	tbMDWeighting	number	44	tbBarColor	text
45	tbMDLocation	text	45	tbTextColor	text
46	tbMDPrimarySkill	text	46	kbCoordLeft	number
47	tbMDPrimaryRole	text	47	kbCoordTop	number
48	tbMDOther2	text	48	focdItemCoordLeft	number
49	tbMDOther3	text	49	focdItemCoordTop	number
50	tbMDOther4	text	50	tbCountry	text
51	canvasNo	number	51	tbCompany	text
52	tbMDProgActivityAlignment	text	52	tbLanguage	text
53	tbMDBackgroundInfo	text	53	tbPriority	text
54	tbMDConsequence	text	54	tbStatus	text
55	tbMDExpectedBenfits	text	55	tbStep	text
56	tbMDProblemOpportunity	text	56	tbStepStatus	text
57	tbMDCapabilitiesNeeded	text	57	tbState	text
58	tbMDSeniorLevelCommittment	text	58	tbWfReasonNote	text
59	tbMDSprintName	text	59	tbStage	text
60	tbMDStakeholderDescription	text	60	tbPhase	text
61	tbMDHealthCost	text	61	tbPine	number
62	tbMDHealthHours	text	62	tbBalsam	number
63	tbMDHealthIssues	text	63	tbFir	number
64	tbMDHealthOverall	text	64	tbSpruce	number
65	tbMDHealthRisk	text	65	tbArea	number
66	tbMDHealthSchedule	text	66	tbSize	number
67	tbMDHealthScope	text	67	tbPercent2	number
68	tbMDBenefitCostRatio	number	68	tbVolume	number
69	tbMDConstraintsAssumptions	text	69	tbT1	text
70	tbMDContractNumber	text	70	tbT2	text
71	tbMDCostBenefitAnalysis	text	71	tbT3	text
72	tbMDEcnomicValueAdded	number	72	tbT4	text
73	tbMDInternalRateOfReturn	number	73	tbT5	text
74	tbMDNetPresentValue	number	74	tbTaskParent	text
75	tbMDOpportunityCost	number
76	tbMDOrgManager	text
77	tbMDPaybackPeriod	number
78	tbMDRiskVsSizeAndComplexity	text
79	tbMDSize	text
80	tbMDStageApprover	text
81	tbMDSunkCosts	number
82	tbMDWrittenBy	text
83	tbMDPrimaryLineOfBusiness	text
84	tbMDNotesWorkflow	text
85	tbMDSyncNotes	text
86	tbMDSponsoringDepartment	text
87	tbMDPrimaryContact	text
88	tbMDContactNumber	text
89	tbMDResponsibleTeam	text
90	tbMDNotesProject	text
91	tbMDOther5	text
92	tbMDOther6	text
93	tbMDOther7	text
94	tbMDOther8	text
95	tbMDOther9	text
96	tbMDOther10	text
97	tbMDOther11	text
98	tbMDOther12	text
99	tbMDRefID	text

## Log
2020-12-22 08:54:33	Merge Operation Started!
2020-12-22 08:54:34	The record with UID '2' added as a new record!
2020-12-22 08:54:34	The record with UID '2' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '44'
2020-12-22 08:54:34	The record with UID '2' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-May-2022'
2020-12-22 08:54:34	The record with UID '3' added as a new record!
2020-12-22 08:54:34	The record with UID '3' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '45'
2020-12-22 08:54:34	The record with UID '3' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jul-2022'
2020-12-22 08:54:34	The record with UID '4' added as a new record!
2020-12-22 08:54:34	The record with UID '4' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '46'
2020-12-22 08:54:34	The record with UID '4' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Apr-2021'
2020-12-22 08:54:34	The record with UID '7' added as a new record!
2020-12-22 08:54:34	The record with UID '7' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '47'
2020-12-22 08:54:34	The record with UID '7' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Mar-2021'
2020-12-22 08:54:34	The record with UID '8' added as a new record!
2020-12-22 08:54:34	The record with UID '8' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '48'
2020-12-22 08:54:34	The record with UID '8' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-May-2021'
2020-12-22 08:54:34	The record with UID '9' added as a new record!
2020-12-22 08:54:34	The record with UID '9' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '49'
2020-12-22 08:54:34	The record with UID '9' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-May-2021'
2020-12-22 08:54:34	The record with UID '10' added as a new record!
2020-12-22 08:54:34	The record with UID '10' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '50'
2020-12-22 08:54:34	The record with UID '10' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-May-2021'
2020-12-22 08:54:34	The record with UID '11' added as a new record!
2020-12-22 08:54:34	The record with UID '11' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '51'
2020-12-22 08:54:34	The record with UID '11' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-May-2021'
2020-12-22 08:54:34	The record with UID '12' added as a new record!
2020-12-22 08:54:34	The record with UID '12' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '52'
2020-12-22 08:54:35	The record with UID '12' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Apr-2021'
2020-12-22 08:54:35	The record with UID '13' added as a new record!
2020-12-22 08:54:35	The record with UID '13' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '53'
2020-12-22 08:54:35	The record with UID '13' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Apr-2021'
2020-12-22 08:54:35	The record with UID '17' added as a new record!
2020-12-22 08:54:35	The record with UID '17' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '54'
2020-12-22 08:54:35	The record with UID '17' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Mar-2021'
2020-12-22 08:54:35	The record with UID '18' added as a new record!
2020-12-22 08:54:35	The record with UID '18' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 08:54:35	The record with UID '18' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Apr-2021'
2020-12-22 08:54:35	The record with UID '19' added as a new record!
2020-12-22 08:54:35	The record with UID '19' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 08:54:35	The record with UID '19' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 08:54:35	The record with UID '20' added as a new record!
2020-12-22 08:54:35	The record with UID '20' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 08:54:35	The record with UID '20' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Mar-2021'
2020-12-22 08:54:35	The record with UID '21' added as a new record!
2020-12-22 08:54:35	The record with UID '21' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 08:54:35	The record with UID '21' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Mar-2021'
2020-12-22 08:54:35	The record with UID '22' added as a new record!
2020-12-22 08:54:35	The record with UID '22' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 08:54:35	The record with UID '22' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 08:54:35	The record with UID '23' added as a new record!
2020-12-22 08:54:35	The record with UID '23' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 08:54:35	The record with UID '23' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 08:54:35	The record with UID '24' added as a new record!
2020-12-22 08:54:35	The record with UID '24' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 08:54:35	The record with UID '24' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Mar-2021'
2020-12-22 08:54:35	The record with UID '26' added as a new record!
2020-12-22 08:54:35	The record with UID '26' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 08:54:35	The record with UID '26' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-May-2021'
2020-12-22 08:54:35	The record with UID '27' added as a new record!
2020-12-22 08:54:35	The record with UID '27' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 08:54:35	The record with UID '27' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Mar-2021'
2020-12-22 08:54:35	The record with UID '29' added as a new record!
2020-12-22 08:54:35	The record with UID '29' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 08:54:35	The record with UID '29' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Apr-2021'
2020-12-22 08:54:35	The record with UID '30' added as a new record!
2020-12-22 08:54:35	The record with UID '30' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 08:54:35	The record with UID '30' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 08:54:35	The record with UID '31' added as a new record!
2020-12-22 08:54:35	The record with UID '31' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 08:54:35	The record with UID '31' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Mar-2021'
2020-12-22 08:54:35	The record with UID '33' added as a new record!
2020-12-22 08:54:35	The record with UID '33' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 08:54:35	The record with UID '33' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 08:54:35	The record with UID '36' added as a new record!
2020-12-22 08:54:35	The record with UID '36' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 08:54:35	The record with UID '36' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 08:54:36	The record with UID '41' added as a new record!
2020-12-22 08:54:36	The record with UID '41' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 08:54:36	The record with UID '44' added as a new record!
2020-12-22 08:54:36	The record with UID '44' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Feb-2021'
2020-12-22 08:54:36	The record with UID '45' added as a new record!
2020-12-22 08:54:36	The record with UID '45' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 08:54:36	The record with UID '46' added as a new record!
2020-12-22 08:54:36	The record with UID '46' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Feb-2021'
2020-12-22 08:54:36	The record with UID '47' added as a new record!
2020-12-22 08:54:36	The record with UID '47' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 08:54:36	The record with UID '48' added as a new record!
2020-12-22 08:54:36	The record with UID '48' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Mar-2021'
2020-12-22 08:54:36	The record with UID '49' added as a new record!
2020-12-22 08:54:36	The record with UID '49' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 08:54:36	The record with UID '54' added as a new record!
2020-12-22 08:54:36	The record with UID '54' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:36	The record with UID '55' added as a new record!
2020-12-22 08:54:36	The record with UID '55' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Mar-2021'
2020-12-22 08:54:36	The record with UID '58' added as a new record!
2020-12-22 08:54:36	The record with UID '58' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 08:54:36	The record with UID '59' added as a new record!
2020-12-22 08:54:36	The record with UID '59' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 08:54:36	The record with UID '61' added as a new record!
2020-12-22 08:54:36	The record with UID '61' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 08:54:36	The record with UID '62' added as a new record!
2020-12-22 08:54:36	The record with UID '62' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-May-2021'
2020-12-22 08:54:36	The record with UID '64' added as a new record!
2020-12-22 08:54:36	The record with UID '64' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 08:54:36	The record with UID '65' added as a new record!
2020-12-22 08:54:36	The record with UID '65' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 08:54:36	The record with UID '68' added as a new record!
2020-12-22 08:54:36	The record with UID '68' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 08:54:36	The record with UID '69' added as a new record!
2020-12-22 08:54:36	The record with UID '69' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Mar-2021'
2020-12-22 08:54:36	The record with UID '107' added as a new record!
2020-12-22 08:54:36	The record with UID '107' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Nov-2020'
2020-12-22 08:54:36	The record with UID '108' added as a new record!
2020-12-22 08:54:36	The record with UID '108' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Dec-2020'
2020-12-22 08:54:36	The record with UID '109' added as a new record!
2020-12-22 08:54:36	The record with UID '109' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 08:54:36	The record with UID '110' added as a new record!
2020-12-22 08:54:36	The record with UID '110' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Dec-2020'
2020-12-22 08:54:36	The record with UID '111' added as a new record!
2020-12-22 08:54:36	The record with UID '111' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Nov-2020'
2020-12-22 08:54:36	The record with UID '112' added as a new record!
2020-12-22 08:54:36	The record with UID '112' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 08:54:36	The record with UID '113' added as a new record!
2020-12-22 08:54:36	The record with UID '113' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Dec-2020'
2020-12-22 08:54:36	The record with UID '121' added as a new record!
2020-12-22 08:54:36	The record with UID '121' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Sep-2020'
2020-12-22 08:54:36	The record with UID '122' added as a new record!
2020-12-22 08:54:36	The record with UID '122' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Sep-2020'
2020-12-22 08:54:36	The record with UID '123' added as a new record!
2020-12-22 08:54:36	The record with UID '123' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Sep-2020'
2020-12-22 08:54:36	The record with UID '124' added as a new record!
2020-12-22 08:54:36	The record with UID '124' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Sep-2020'
2020-12-22 08:54:36	The record with UID '125' added as a new record!
2020-12-22 08:54:36	The record with UID '125' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Sep-2020'
2020-12-22 08:54:37	The record with UID '126' added as a new record!
2020-12-22 08:54:37	The record with UID '126' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Jan-2021'
2020-12-22 08:54:37	The record with UID '127' added as a new record!
2020-12-22 08:54:37	The record with UID '127' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Jan-2021'
2020-12-22 08:54:37	The record with UID '128' added as a new record!
2020-12-22 08:54:37	The record with UID '128' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:37	The record with UID '129' added as a new record!
2020-12-22 08:54:37	The record with UID '129' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 08:54:37	The record with UID '130' added as a new record!
2020-12-22 08:54:37	The record with UID '130' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Feb-2021'
2020-12-22 08:54:37	The record with UID '131' added as a new record!
2020-12-22 08:54:37	The record with UID '131' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Feb-2021'
2020-12-22 08:54:37	The record with UID '132' added as a new record!
2020-12-22 08:54:37	The record with UID '132' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 08:54:37	The record with UID '133' added as a new record!
2020-12-22 08:54:37	The record with UID '133' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Feb-2021'
2020-12-22 08:54:37	The record with UID '134' added as a new record!
2020-12-22 08:54:37	The record with UID '134' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 08:54:37	The record with UID '135' added as a new record!
2020-12-22 08:54:37	The record with UID '135' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Feb-2021'
2020-12-22 08:54:37	The record with UID '136' added as a new record!
2020-12-22 08:54:37	The record with UID '136' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 08:54:37	The record with UID '137' added as a new record!
2020-12-22 08:54:37	The record with UID '137' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 08:54:37	The record with UID '138' added as a new record!
2020-12-22 08:54:37	The record with UID '138' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 08:54:37	The record with UID '139' added as a new record!
2020-12-22 08:54:37	The record with UID '139' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 08:54:37	The record with UID '140' added as a new record!
2020-12-22 08:54:37	The record with UID '140' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 08:54:37	The record with UID '141' added as a new record!
2020-12-22 08:54:37	The record with UID '141' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 08:54:37	The record with UID '142' added as a new record!
2020-12-22 08:54:37	The record with UID '142' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:37	The record with UID '191' added as a new record!
2020-12-22 08:54:37	The record with UID '191' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:37	The record with UID '192' added as a new record!
2020-12-22 08:54:37	The record with UID '192' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Jan-2021'
2020-12-22 08:54:37	The record with UID '193' added as a new record!
2020-12-22 08:54:37	The record with UID '193' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:37	The record with UID '194' added as a new record!
2020-12-22 08:54:37	The record with UID '194' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Feb-2021'
2020-12-22 08:54:37	The record with UID '196' added as a new record!
2020-12-22 08:54:37	The record with UID '196' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 08:54:37	The record with UID '197' added as a new record!
2020-12-22 08:54:37	The record with UID '197' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Jan-2021'
2020-12-22 08:54:37	The record with UID '198' added as a new record!
2020-12-22 08:54:37	The record with UID '198' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 08:54:37	The record with UID '199' added as a new record!
2020-12-22 08:54:37	The record with UID '199' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:37	The record with UID '200' added as a new record!
2020-12-22 08:54:37	The record with UID '200' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Mar-2021'
2020-12-22 08:54:37	The record with UID '201' added as a new record!
2020-12-22 08:54:37	The record with UID '201' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Mar-2021'
2020-12-22 08:54:37	The record with UID '202' added as a new record!
2020-12-22 08:54:37	The record with UID '202' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 08:54:37	The record with UID '203' added as a new record!
2020-12-22 08:54:37	The record with UID '203' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 08:54:37	The record with UID '204' added as a new record!
2020-12-22 08:54:37	The record with UID '204' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Jan-2021'
2020-12-22 08:54:37	The record with UID '205' added as a new record!
2020-12-22 08:54:37	The record with UID '205' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 08:54:37	The record with UID '206' added as a new record!
2020-12-22 08:54:37	The record with UID '206' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Feb-2021'
2020-12-22 08:54:37	The record with UID '207' added as a new record!
2020-12-22 08:54:37	The record with UID '207' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 08:54:37	The record with UID '233' added as a new record!
2020-12-22 08:54:37	The record with UID '233' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 08:54:37	The record with UID '234' added as a new record!
2020-12-22 08:54:37	The record with UID '234' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:37	The record with UID '235' added as a new record!
2020-12-22 08:54:37	The record with UID '235' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Feb-2021'
2020-12-22 08:54:37	The record with UID '236' added as a new record!
2020-12-22 08:54:37	The record with UID '236' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 08:54:37	The record with UID '237' added as a new record!
2020-12-22 08:54:37	The record with UID '237' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:37	The record with UID '238' added as a new record!
2020-12-22 08:54:37	The record with UID '238' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Jan-2021'
2020-12-22 08:54:37	The record with UID '239' added as a new record!
2020-12-22 08:54:37	The record with UID '239' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Mar-2021'
2020-12-22 08:54:37	The record with UID '240' added as a new record!
2020-12-22 08:54:37	The record with UID '240' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 08:54:37	The record with UID '241' added as a new record!
2020-12-22 08:54:37	The record with UID '241' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Jan-2021'
2020-12-22 08:54:37	The record with UID '242' added as a new record!
2020-12-22 08:54:37	The record with UID '242' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Feb-2021'
2020-12-22 08:54:37	The record with UID '243' added as a new record!
2020-12-22 08:54:37	The record with UID '243' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Mar-2021'
2020-12-22 08:54:37	The record with UID '244' added as a new record!
2020-12-22 08:54:37	The record with UID '244' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 08:54:37	The record with UID '245' added as a new record!
2020-12-22 08:54:37	The record with UID '245' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:37	The record with UID '246' added as a new record!
2020-12-22 08:54:37	The record with UID '246' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 08:54:37	The record with UID '264' added as a new record!
2020-12-22 08:54:37	The record with UID '264' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Jan-2021'
2020-12-22 08:54:37	The record with UID '265' added as a new record!
2020-12-22 08:54:37	The record with UID '265' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 08:54:37	The record with UID '266' added as a new record!
2020-12-22 08:54:37	The record with UID '266' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 08:54:37	The record with UID '267' added as a new record!
2020-12-22 08:54:37	The record with UID '267' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 08:54:38	The record with UID '268' added as a new record!
2020-12-22 08:54:38	The record with UID '268' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 08:54:38	The record with UID '269' added as a new record!
2020-12-22 08:54:38	The record with UID '269' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Apr-2021'
2020-12-22 08:54:38	The record with UID '270' added as a new record!
2020-12-22 08:54:38	The record with UID '270' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-May-2021'
2020-12-22 08:54:38	The record with UID '271' added as a new record!
2020-12-22 08:54:38	The record with UID '271' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Apr-2021'
2020-12-22 08:54:38	The record with UID '272' added as a new record!
2020-12-22 08:54:38	The record with UID '272' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-May-2021'
2020-12-22 08:54:38	The record with UID '273' added as a new record!
2020-12-22 08:54:38	The record with UID '273' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Apr-2021'
2020-12-22 08:54:38	The record with UID '274' added as a new record!
2020-12-22 08:54:38	The record with UID '274' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 08:54:38	The record with UID '275' added as a new record!
2020-12-22 08:54:38	The record with UID '275' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Feb-2021'
2020-12-22 08:54:38	The record with UID '276' added as a new record!
2020-12-22 08:54:38	The record with UID '276' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 08:54:38	The record with UID '277' added as a new record!
2020-12-22 08:54:38	The record with UID '277' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:38	The record with UID '278' added as a new record!
2020-12-22 08:54:38	The record with UID '278' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Apr-2021'
2020-12-22 08:54:38	The record with UID '279' added as a new record!
2020-12-22 08:54:38	The record with UID '279' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Apr-2021'
2020-12-22 08:54:38	The record with UID '280' added as a new record!
2020-12-22 08:54:38	The record with UID '280' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Mar-2021'
2020-12-22 08:54:38	The record with UID '281' added as a new record!
2020-12-22 08:54:38	The record with UID '281' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 08:54:38	The record with UID '282' added as a new record!
2020-12-22 08:54:38	The record with UID '282' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Mar-2021'
2020-12-22 08:54:38	The record with UID '283' added as a new record!
2020-12-22 08:54:38	The record with UID '283' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 08:54:38	The record with UID '284' added as a new record!
2020-12-22 08:54:38	The record with UID '284' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 08:54:38	The record with UID '285' added as a new record!
2020-12-22 08:54:38	The record with UID '285' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 08:54:38	The record with UID '296' added as a new record!
2020-12-22 08:54:38	The record with UID '296' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Apr-2021'
2020-12-22 08:54:38	The record with UID '297' added as a new record!
2020-12-22 08:54:38	The record with UID '297' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 08:54:38	The record with UID '298' added as a new record!
2020-12-22 08:54:38	The record with UID '298' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 08:54:38	The record with UID '299' added as a new record!
2020-12-22 08:54:38	The record with UID '299' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 08:54:38	The record with UID '300' added as a new record!
2020-12-22 08:54:38	The record with UID '300' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 08:54:38	The record with UID '301' added as a new record!
2020-12-22 08:54:38	The record with UID '301' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Feb-2021'
2020-12-22 08:54:38	The record with UID '302' added as a new record!
2020-12-22 08:54:38	The record with UID '302' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 08:54:38	The record with UID '303' added as a new record!
2020-12-22 08:54:38	The record with UID '303' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 08:54:38	The record with UID '304' added as a new record!
2020-12-22 08:54:38	The record with UID '304' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Feb-2021'
2020-12-22 08:54:38	The record with UID '305' added as a new record!
2020-12-22 08:54:38	The record with UID '305' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '05-Feb-2021'
2020-12-22 08:54:38	The record with UID '307' added as a new record!
2020-12-22 08:54:38	The record with UID '307' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 08:54:38	The record with UID '308' added as a new record!
2020-12-22 08:54:38	The record with UID '308' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 08:54:38	The record with UID '309' added as a new record!
2020-12-22 08:54:38	The record with UID '309' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 08:54:38	The record with UID '310' added as a new record!
2020-12-22 08:54:38	The record with UID '310' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 08:54:38	The record with UID '311' added as a new record!
2020-12-22 08:54:38	The record with UID '311' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 08:54:38	The record with UID '327' added as a new record!
2020-12-22 08:54:38	The record with UID '327' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Jan-2021'
2020-12-22 08:54:38	The record with UID '328' added as a new record!
2020-12-22 08:54:38	The record with UID '328' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 08:54:38	The record with UID '329' added as a new record!
2020-12-22 08:54:38	The record with UID '329' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 08:54:38	The record with UID '330' added as a new record!
2020-12-22 08:54:38	The record with UID '330' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 08:54:38	The record with UID '331' added as a new record!
2020-12-22 08:54:38	The record with UID '331' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 08:54:38	The record with UID '332' added as a new record!
2020-12-22 08:54:38	The record with UID '332' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 08:54:38	The record with UID '333' added as a new record!
2020-12-22 08:54:38	The record with UID '333' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Mar-2021'
2020-12-22 08:54:38	The record with UID '334' added as a new record!
2020-12-22 08:54:38	The record with UID '334' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Mar-2021'
2020-12-22 08:54:38	The record with UID '335' added as a new record!
2020-12-22 08:54:38	The record with UID '335' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 08:54:38	The record with UID '336' added as a new record!
2020-12-22 08:54:38	The record with UID '336' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 08:54:38	The record with UID '337' added as a new record!
2020-12-22 08:54:38	The record with UID '337' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 08:54:38	The record with UID '338' added as a new record!
2020-12-22 08:54:38	The record with UID '338' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 08:54:38	The record with UID '339' added as a new record!
2020-12-22 08:54:38	The record with UID '339' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 08:54:38	The record with UID '340' added as a new record!
2020-12-22 08:54:38	The record with UID '340' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Jan-2021'
2020-12-22 08:54:38	Merge Operation Finished!
2020-12-22 09:02:41	Merge Operation Started!
2020-12-22 09:02:42	The record with UID '7' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '4'
2020-12-22 09:02:42	The record with UID '8' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '2'
2020-12-22 09:02:42	The record with UID '9' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '3'
2020-12-22 09:02:42	The record with UID '10' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '9'
2020-12-22 09:02:42	The record with UID '11' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '3'
2020-12-22 09:02:42	The record with UID '12' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '4'
2020-12-22 09:02:42	The record with UID '13' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '2'
2020-12-22 09:02:42	The record with UID '17' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '8'
2020-12-22 09:02:42	The record with UID '18' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '26'
2020-12-22 09:02:42	The record with UID '19' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '9'
2020-12-22 09:02:42	The record with UID '20' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '8'
2020-12-22 09:02:42	The record with UID '21' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '11'
2020-12-22 09:02:42	The record with UID '22' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '11'
2020-12-22 09:02:42	The record with UID '23' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '13'
2020-12-22 09:02:42	The record with UID '24' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '13'
2020-12-22 09:02:42	The record with UID '26' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '2'
2020-12-22 09:02:42	The record with UID '27' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '26'
2020-12-22 09:02:42	The record with UID '29' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '12'
2020-12-22 09:02:42	The record with UID '30' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '12'
2020-12-22 09:02:42	The record with UID '31' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '7'
2020-12-22 09:02:42	The record with UID '33' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '26'
2020-12-22 09:02:42	The record with UID '36' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '9'
2020-12-22 09:02:42	The record with UID '41' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '33'
2020-12-22 09:02:42	The record with UID '44' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '36'
2020-12-22 09:02:42	The record with UID '45' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '44'
2020-12-22 09:02:42	The record with UID '46' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '24'
2020-12-22 09:02:42	The record with UID '47' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '17'
2020-12-22 09:02:42	The record with UID '48' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '17'
2020-12-22 09:02:42	The record with UID '49' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '21'
2020-12-22 09:02:42	The record with UID '54' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '23'
2020-12-22 09:02:42	The record with UID '55' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '29'
2020-12-22 09:02:42	The record with UID '58' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '27'
2020-12-22 09:02:42	The record with UID '59' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '20'
2020-12-22 09:02:42	The record with UID '61' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '19'
2020-12-22 09:02:42	The record with UID '62' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '10'
2020-12-22 09:02:42	The record with UID '64' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '30'
2020-12-22 09:02:42	The record with UID '65' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '22'
2020-12-22 09:02:43	The record with UID '68' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '18'
2020-12-22 09:02:43	The record with UID '69' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '31'
2020-12-22 09:02:43	The record with UID '107' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '108' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '109' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '110' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '111' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '112' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '113' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '41'
2020-12-22 09:02:43	The record with UID '121' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '45'
2020-12-22 09:02:43	The record with UID '122' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '45'
2020-12-22 09:02:43	The record with UID '123' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '45'
2020-12-22 09:02:43	The record with UID '124' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '45'
2020-12-22 09:02:43	The record with UID '125' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '45'
2020-12-22 09:02:43	The record with UID '126' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '127' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '128' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '129' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '130' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '131' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '132' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '46'
2020-12-22 09:02:43	The record with UID '133' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '48'
2020-12-22 09:02:43	The record with UID '134' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '48'
2020-12-22 09:02:43	The record with UID '135' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '48'
2020-12-22 09:02:43	The record with UID '136' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '48'
2020-12-22 09:02:43	The record with UID '137' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '48'
2020-12-22 09:02:43	The record with UID '138' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '49'
2020-12-22 09:02:43	The record with UID '139' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '49'
2020-12-22 09:02:43	The record with UID '140' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '49'
2020-12-22 09:02:43	The record with UID '141' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '49'
2020-12-22 09:02:43	The record with UID '142' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '49'
2020-12-22 09:02:43	The record with UID '191' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '192' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '193' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '194' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '196' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '197' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '54'
2020-12-22 09:02:43	The record with UID '198' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '199' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '200' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '201' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '202' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '203' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '204' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '205' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '206' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '207' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '55'
2020-12-22 09:02:43	The record with UID '233' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '234' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '235' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '236' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '237' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '238' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '58'
2020-12-22 09:02:43	The record with UID '239' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '240' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '241' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '242' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '243' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '244' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '245' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '246' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '59'
2020-12-22 09:02:43	The record with UID '264' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '61'
2020-12-22 09:02:43	The record with UID '265' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '61'
2020-12-22 09:02:43	The record with UID '266' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '61'
2020-12-22 09:02:43	The record with UID '267' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '61'
2020-12-22 09:02:43	The record with UID '268' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '61'
2020-12-22 09:02:43	The record with UID '269' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:43	The record with UID '270' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:43	The record with UID '271' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:43	The record with UID '272' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:43	The record with UID '273' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '274' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '275' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '276' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '277' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '278' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '279' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '280' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '281' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '282' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '283' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '284' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '285' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '62'
2020-12-22 09:02:44	The record with UID '296' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '297' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '298' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '299' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '300' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '301' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '302' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '303' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '304' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '305' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '64'
2020-12-22 09:02:44	The record with UID '307' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '65'
2020-12-22 09:02:44	The record with UID '308' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '65'
2020-12-22 09:02:44	The record with UID '309' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '65'
2020-12-22 09:02:44	The record with UID '310' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '65'
2020-12-22 09:02:44	The record with UID '311' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '65'
2020-12-22 09:02:44	The record with UID '327' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '328' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '329' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '330' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '331' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '332' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '68'
2020-12-22 09:02:44	The record with UID '333' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '334' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '335' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '336' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '337' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '338' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '339' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	The record with UID '340' updated from 'Timebars'! Details: Field['Parent'] :: '' ----> '69'
2020-12-22 09:02:44	Merge Operation Finished!
2020-12-22 09:07:07	Merge Operation Started!
2020-12-22 09:07:07	The record with UID '10' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '951'
2020-12-22 09:07:07	The record with UID '107' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1359'
2020-12-22 09:07:07	The record with UID '108' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1420'
2020-12-22 09:07:07	The record with UID '109' updated from 'Timebars'! Details: Field['Order'] :: '' ----> 'NaN'
2020-12-22 09:07:07	The record with UID '11' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1097'
2020-12-22 09:07:07	The record with UID '110' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1418'
2020-12-22 09:07:07	The record with UID '111' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1356'
2020-12-22 09:07:07	The record with UID '112' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1358'
2020-12-22 09:07:07	The record with UID '113' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1357'
2020-12-22 09:07:07	The record with UID '12' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1707'
2020-12-22 09:07:07	The record with UID '121' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1347'
2020-12-22 09:07:07	The record with UID '122' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1310'
2020-12-22 09:07:07	The record with UID '123' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1271'
2020-12-22 09:07:07	The record with UID '124' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1226'
2020-12-22 09:07:07	The record with UID '125' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1415'
2020-12-22 09:07:07	The record with UID '126' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '787'
2020-12-22 09:07:07	The record with UID '127' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '790'
2020-12-22 09:07:07	The record with UID '128' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '787'
2020-12-22 09:07:07	The record with UID '129' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '836'
2020-12-22 09:07:07	The record with UID '13' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '299'
2020-12-22 09:07:07	The record with UID '130' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '839'
2020-12-22 09:07:07	The record with UID '131' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '884'
2020-12-22 09:07:07	The record with UID '132' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '879'
2020-12-22 09:07:08	The record with UID '133' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '415'
2020-12-22 09:07:08	The record with UID '134' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '363'
2020-12-22 09:07:08	The record with UID '135' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '361'
2020-12-22 09:07:08	The record with UID '136' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '312'
2020-12-22 09:07:08	The record with UID '137' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '315'
2020-12-22 09:07:08	The record with UID '138' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1236'
2020-12-22 09:07:08	The record with UID '139' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1267'
2020-12-22 09:07:08	The record with UID '140' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1316'
2020-12-22 09:07:08	The record with UID '141' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1275'
2020-12-22 09:07:08	The record with UID '142' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1316'
2020-12-22 09:07:08	The record with UID '17' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '161'
2020-12-22 09:07:08	The record with UID '18' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '487'
2020-12-22 09:07:08	The record with UID '19' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '949'
2020-12-22 09:07:08	The record with UID '191' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '589'
2020-12-22 09:07:08	The record with UID '192' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '456'
2020-12-22 09:07:08	The record with UID '193' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '457'
2020-12-22 09:07:08	The record with UID '194' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '502'
2020-12-22 09:07:08	The record with UID '196' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '545'
2020-12-22 09:07:08	The record with UID '197' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '589'
2020-12-22 09:07:08	The record with UID '198' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1995'
2020-12-22 09:07:08	The record with UID '199' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2080'
2020-12-22 09:07:08	The record with UID '2' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '69'
2020-12-22 09:07:08	The record with UID '20' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '470'
2020-12-22 09:07:08	The record with UID '200' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1996'
2020-12-22 09:07:08	The record with UID '201' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2136'
2020-12-22 09:07:08	The record with UID '202' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2096'
2020-12-22 09:07:08	The record with UID '203' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2144'
2020-12-22 09:07:08	The record with UID '204' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2114'
2020-12-22 09:07:08	The record with UID '205' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1996'
2020-12-22 09:07:08	The record with UID '206' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2033'
2020-12-22 09:07:08	The record with UID '207' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2045'
2020-12-22 09:07:08	The record with UID '21' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1146'
2020-12-22 09:07:08	The record with UID '22' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1229'
2020-12-22 09:07:08	The record with UID '23' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '354'
2020-12-22 09:07:08	The record with UID '233' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1073'
2020-12-22 09:07:08	The record with UID '234' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1002'
2020-12-22 09:07:08	The record with UID '235' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1009'
2020-12-22 09:07:08	The record with UID '236' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '998'
2020-12-22 09:07:08	The record with UID '237' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1069'
2020-12-22 09:07:08	The record with UID '238' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1060'
2020-12-22 09:07:08	The record with UID '239' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '746'
2020-12-22 09:07:08	The record with UID '24' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '704'
2020-12-22 09:07:08	The record with UID '240' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '699'
2020-12-22 09:07:08	The record with UID '241' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '572'
2020-12-22 09:07:08	The record with UID '242' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '575'
2020-12-22 09:07:08	The record with UID '243' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '574'
2020-12-22 09:07:08	The record with UID '244' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '638'
2020-12-22 09:07:08	The record with UID '245' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '644'
2020-12-22 09:07:08	The record with UID '246' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '691'
2020-12-22 09:07:09	The record with UID '26' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '428'
2020-12-22 09:07:09	The record with UID '264' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1050'
2020-12-22 09:07:09	The record with UID '265' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1151'
2020-12-22 09:07:09	The record with UID '266' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1092'
2020-12-22 09:07:09	The record with UID '267' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1151'
2020-12-22 09:07:09	The record with UID '268' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1092'
2020-12-22 09:07:09	The record with UID '269' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1117'
2020-12-22 09:07:09	The record with UID '27' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '887'
2020-12-22 09:07:09	The record with UID '270' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1170'
2020-12-22 09:07:09	The record with UID '271' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1343'
2020-12-22 09:07:09	The record with UID '272' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1388'
2020-12-22 09:07:09	The record with UID '273' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1385'
2020-12-22 09:07:09	The record with UID '274' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1380'
2020-12-22 09:07:09	The record with UID '275' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1381'
2020-12-22 09:07:09	The record with UID '276' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1322'
2020-12-22 09:07:09	The record with UID '277' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1119'
2020-12-22 09:07:09	The record with UID '278' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1268'
2020-12-22 09:07:09	The record with UID '279' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1213'
2020-12-22 09:07:09	The record with UID '280' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1340'
2020-12-22 09:07:09	The record with UID '281' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1215'
2020-12-22 09:07:09	The record with UID '282' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1164'
2020-12-22 09:07:09	The record with UID '283' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1269'
2020-12-22 09:07:09	The record with UID '284' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1215'
2020-12-22 09:07:09	The record with UID '285' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1162'
2020-12-22 09:07:09	The record with UID '29' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1880'
2020-12-22 09:07:09	The record with UID '296' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1858'
2020-12-22 09:07:09	The record with UID '297' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1907'
2020-12-22 09:07:09	The record with UID '298' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1908'
2020-12-22 09:07:09	The record with UID '299' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1959'
2020-12-22 09:07:09	The record with UID '3' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '818'
2020-12-22 09:07:09	The record with UID '30' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1758'
2020-12-22 09:07:09	The record with UID '300' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1956'
2020-12-22 09:07:09	The record with UID '301' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1955'
2020-12-22 09:07:09	The record with UID '302' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2008'
2020-12-22 09:07:09	The record with UID '303' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1859'
2020-12-22 09:07:09	The record with UID '304' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1859'
2020-12-22 09:07:09	The record with UID '305' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1907'
2020-12-22 09:07:09	The record with UID '307' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1543'
2020-12-22 09:07:09	The record with UID '308' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1348'
2020-12-22 09:07:09	The record with UID '309' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1495'
2020-12-22 09:07:09	The record with UID '31' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1610'
2020-12-22 09:07:09	The record with UID '310' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1390'
2020-12-22 09:07:09	The record with UID '311' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1437'
2020-12-22 09:07:09	The record with UID '327' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '597'
2020-12-22 09:07:09	The record with UID '328' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '736'
2020-12-22 09:07:09	The record with UID '329' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '605'
2020-12-22 09:07:09	The record with UID '33' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1225'
2020-12-22 09:07:09	The record with UID '330' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '666'
2020-12-22 09:07:09	The record with UID '331' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '723'
2020-12-22 09:07:09	The record with UID '332' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '660'
2020-12-22 09:07:09	The record with UID '333' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1701'
2020-12-22 09:07:09	The record with UID '334' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1824'
2020-12-22 09:07:09	The record with UID '335' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1756'
2020-12-22 09:07:09	The record with UID '336' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1768'
2020-12-22 09:07:09	The record with UID '337' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1817'
2020-12-22 09:07:09	The record with UID '338' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1816'
2020-12-22 09:07:09	The record with UID '339' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1877'
2020-12-22 09:07:09	The record with UID '340' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1878'
2020-12-22 09:07:09	The record with UID '36' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1331'
2020-12-22 09:07:09	The record with UID '4' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1513'
2020-12-22 09:07:09	The record with UID '41' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1284'
2020-12-22 09:07:09	The record with UID '44' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1389'
2020-12-22 09:07:09	The record with UID '45' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1389'
2020-12-22 09:07:09	The record with UID '46' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '752'
2020-12-22 09:07:09	The record with UID '47' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '221'
2020-12-22 09:07:09	The record with UID '48' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '270'
2020-12-22 09:07:09	The record with UID '49' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1190'
2020-12-22 09:07:09	The record with UID '54' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '414'
2020-12-22 09:07:09	The record with UID '55' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1944'
2020-12-22 09:07:09	The record with UID '58' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '947'
2020-12-22 09:07:09	The record with UID '59' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '515'
2020-12-22 09:07:09	The record with UID '61' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '999'
2020-12-22 09:07:09	The record with UID '62' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1002'
2020-12-22 09:07:09	The record with UID '64' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1808'
2020-12-22 09:07:10	The record with UID '65' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1278'
2020-12-22 09:07:10	The record with UID '68' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '551'
2020-12-22 09:07:10	The record with UID '69' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1650'
2020-12-22 09:07:10	The record with UID '7' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1549'
2020-12-22 09:07:10	The record with UID '8' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '106'
2020-12-22 09:07:10	The record with UID '9' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '852'
2020-12-22 09:07:10	Merge Operation Finished!
2020-12-22 09:19:30	Merge Operation Started!
2020-12-22 09:19:32	Merge Operation Finished!
2020-12-22 09:26:47	Merge Operation Started!
2020-12-22 09:26:47	The record with UID '10' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:47	The record with UID '107' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '108' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '109' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '11' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:47	The record with UID '110' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '111' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '112' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '113' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:47	The record with UID '12' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:48	The record with UID '121' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '122' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '123' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '124' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '125' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '126' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '127' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '128' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '129' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '13' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:48	The record with UID '130' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '131' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '132' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '133' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '134' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '135' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '136' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '137' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '138' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '139' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '140' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '141' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '142' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '17' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:48	The record with UID '18' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:48	The record with UID '19' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:48	The record with UID '191' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '192' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '193' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '194' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '196' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '197' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '198' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '199' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '2' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Portfolio'
2020-12-22 09:26:48	The record with UID '20' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:48	The record with UID '200' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '201' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '202' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '203' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '204' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:48	The record with UID '205' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '206' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '207' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '21' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '22' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '23' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '233' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '234' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '235' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '236' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '237' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '238' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '239' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '24' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '240' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '241' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '242' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '243' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '244' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '245' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '246' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '26' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:49	The record with UID '264' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '265' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '266' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '267' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '268' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '269' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '27' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '270' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '271' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '272' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '273' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '274' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '275' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '276' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '277' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '278' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '279' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '280' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '281' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '282' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '283' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '284' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '285' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '29' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '296' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '297' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '298' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '299' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '3' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Portfolio'
2020-12-22 09:26:49	The record with UID '30' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '300' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '301' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '302' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '303' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '304' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '305' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '307' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '308' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '309' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '31' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:49	The record with UID '310' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '311' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '327' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '328' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '329' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:49	The record with UID '33' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:50	The record with UID '330' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '331' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '332' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '333' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '334' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '335' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '336' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '337' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '338' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '339' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '340' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Allocation'
2020-12-22 09:26:50	The record with UID '36' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Sub-Project'
2020-12-22 09:26:50	The record with UID '4' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Portfolio'
2020-12-22 09:26:50	The record with UID '41' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '44' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '45' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '46' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '47' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '48' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '49' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '54' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '55' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '58' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '59' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '61' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '62' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '64' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '65' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '68' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '69' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Task'
2020-12-22 09:26:50	The record with UID '7' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:50	The record with UID '8' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:50	The record with UID '9' updated from 'Timebars'! Details: Field['Type'] :: '' ----> 'Project'
2020-12-22 09:26:50	Merge Operation Finished!
2020-12-22 09:52:06	Merge Operation Started!
2020-12-22 09:52:07	The record with UID 'A002' added as a new record!
2020-12-22 09:52:07	The record with UID 'A002' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '44'
2020-12-22 09:52:07	The record with UID 'A002' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-May-2022'
2020-12-22 09:52:07	The record with UID 'A003' added as a new record!
2020-12-22 09:52:07	The record with UID 'A003' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '45'
2020-12-22 09:52:07	The record with UID 'A003' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jul-2022'
2020-12-22 09:52:07	The record with UID 'A004' added as a new record!
2020-12-22 09:52:07	The record with UID 'A004' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '46'
2020-12-22 09:52:07	The record with UID 'A004' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Apr-2021'
2020-12-22 09:52:07	The record with UID 'A007' added as a new record!
2020-12-22 09:52:07	The record with UID 'A007' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '47'
2020-12-22 09:52:07	The record with UID 'A007' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Mar-2021'
2020-12-22 09:52:07	The record with UID 'A008' added as a new record!
2020-12-22 09:52:07	The record with UID 'A008' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '48'
2020-12-22 09:52:08	The record with UID 'A008' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-May-2021'
2020-12-22 09:52:08	The record with UID 'A009' added as a new record!
2020-12-22 09:52:08	The record with UID 'A009' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '49'
2020-12-22 09:52:08	The record with UID 'A009' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-May-2021'
2020-12-22 09:52:08	The record with UID 'A010' added as a new record!
2020-12-22 09:52:08	The record with UID 'A010' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '50'
2020-12-22 09:52:08	The record with UID 'A010' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-May-2021'
2020-12-22 09:52:08	The record with UID 'A011' added as a new record!
2020-12-22 09:52:08	The record with UID 'A011' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '51'
2020-12-22 09:52:08	The record with UID 'A011' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-May-2021'
2020-12-22 09:52:08	The record with UID 'A012' added as a new record!
2020-12-22 09:52:08	The record with UID 'A012' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '52'
2020-12-22 09:52:08	The record with UID 'A012' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Apr-2021'
2020-12-22 09:52:08	The record with UID 'A013' added as a new record!
2020-12-22 09:52:08	The record with UID 'A013' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '53'
2020-12-22 09:52:08	The record with UID 'A013' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Apr-2021'
2020-12-22 09:52:08	The record with UID 'A017' added as a new record!
2020-12-22 09:52:08	The record with UID 'A017' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '54'
2020-12-22 09:52:08	The record with UID 'A017' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A018' added as a new record!
2020-12-22 09:52:08	The record with UID 'A018' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 09:52:08	The record with UID 'A018' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Apr-2021'
2020-12-22 09:52:08	The record with UID 'A019' added as a new record!
2020-12-22 09:52:08	The record with UID 'A019' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 09:52:08	The record with UID 'A019' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 09:52:08	The record with UID 'A020' added as a new record!
2020-12-22 09:52:08	The record with UID 'A020' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 09:52:08	The record with UID 'A020' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A021' added as a new record!
2020-12-22 09:52:08	The record with UID 'A021' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 09:52:08	The record with UID 'A021' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A022' added as a new record!
2020-12-22 09:52:08	The record with UID 'A022' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 09:52:08	The record with UID 'A022' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A023' added as a new record!
2020-12-22 09:52:08	The record with UID 'A023' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 09:52:08	The record with UID 'A023' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A024' added as a new record!
2020-12-22 09:52:08	The record with UID 'A024' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 09:52:08	The record with UID 'A024' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Mar-2021'
2020-12-22 09:52:08	The record with UID 'A026' added as a new record!
2020-12-22 09:52:08	The record with UID 'A026' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 09:52:08	The record with UID 'A026' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-May-2021'
2020-12-22 09:52:09	The record with UID 'A027' added as a new record!
2020-12-22 09:52:09	The record with UID 'A027' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 09:52:09	The record with UID 'A027' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A029' added as a new record!
2020-12-22 09:52:09	The record with UID 'A029' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 09:52:09	The record with UID 'A029' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Apr-2021'
2020-12-22 09:52:09	The record with UID 'A030' added as a new record!
2020-12-22 09:52:09	The record with UID 'A030' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 09:52:09	The record with UID 'A030' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 09:52:09	The record with UID 'A031' added as a new record!
2020-12-22 09:52:09	The record with UID 'A031' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 09:52:09	The record with UID 'A031' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A033' added as a new record!
2020-12-22 09:52:09	The record with UID 'A033' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 09:52:09	The record with UID 'A033' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A036' added as a new record!
2020-12-22 09:52:09	The record with UID 'A036' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 09:52:09	The record with UID 'A036' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A062' added as a new record!
2020-12-22 09:52:09	The record with UID 'A062' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-May-2021'
2020-12-22 09:52:09	The record with UID 'A047' added as a new record!
2020-12-22 09:52:09	The record with UID 'A047' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A048' added as a new record!
2020-12-22 09:52:09	The record with UID 'A048' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A068' added as a new record!
2020-12-22 09:52:09	The record with UID 'A068' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A061' added as a new record!
2020-12-22 09:52:09	The record with UID 'A061' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 09:52:09	The record with UID 'A059' added as a new record!
2020-12-22 09:52:09	The record with UID 'A059' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A049' added as a new record!
2020-12-22 09:52:09	The record with UID 'A049' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A065' added as a new record!
2020-12-22 09:52:09	The record with UID 'A065' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A054' added as a new record!
2020-12-22 09:52:09	The record with UID 'A054' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A046' added as a new record!
2020-12-22 09:52:09	The record with UID 'A046' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Feb-2021'
2020-12-22 09:52:09	The record with UID 'A058' added as a new record!
2020-12-22 09:52:09	The record with UID 'A058' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A055' added as a new record!
2020-12-22 09:52:09	The record with UID 'A055' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Mar-2021'
2020-12-22 09:52:09	The record with UID 'A064' added as a new record!
2020-12-22 09:52:09	The record with UID 'A064' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 09:52:10	The record with UID 'A069' added as a new record!
2020-12-22 09:52:10	The record with UID 'A069' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Mar-2021'
2020-12-22 09:52:10	The record with UID 'A041' added as a new record!
2020-12-22 09:52:10	The record with UID 'A041' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 09:52:10	The record with UID 'A044' added as a new record!
2020-12-22 09:52:10	The record with UID 'A044' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A107' added as a new record!
2020-12-22 09:52:10	The record with UID 'A107' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Nov-2020'
2020-12-22 09:52:10	The record with UID 'A108' added as a new record!
2020-12-22 09:52:10	The record with UID 'A108' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Dec-2020'
2020-12-22 09:52:10	The record with UID 'A109' added as a new record!
2020-12-22 09:52:10	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A110' added as a new record!
2020-12-22 09:52:10	The record with UID 'A110' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Dec-2020'
2020-12-22 09:52:10	The record with UID 'A111' added as a new record!
2020-12-22 09:52:10	The record with UID 'A111' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Nov-2020'
2020-12-22 09:52:10	The record with UID 'A112' added as a new record!
2020-12-22 09:52:10	The record with UID 'A112' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A113' added as a new record!
2020-12-22 09:52:10	The record with UID 'A113' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Dec-2020'
2020-12-22 09:52:10	The record with UID 'A045' added as a new record!
2020-12-22 09:52:10	The record with UID 'A045' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A121' added as a new record!
2020-12-22 09:52:10	The record with UID 'A121' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Sep-2020'
2020-12-22 09:52:10	The record with UID 'A122' added as a new record!
2020-12-22 09:52:10	The record with UID 'A122' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Sep-2020'
2020-12-22 09:52:10	The record with UID 'A123' added as a new record!
2020-12-22 09:52:10	The record with UID 'A123' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Sep-2020'
2020-12-22 09:52:10	The record with UID 'A124' added as a new record!
2020-12-22 09:52:10	The record with UID 'A124' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Sep-2020'
2020-12-22 09:52:10	The record with UID 'A125' added as a new record!
2020-12-22 09:52:10	The record with UID 'A125' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Sep-2020'
2020-12-22 09:52:10	The record with UID 'A126' added as a new record!
2020-12-22 09:52:10	The record with UID 'A126' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A127' added as a new record!
2020-12-22 09:52:10	The record with UID 'A127' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A128' added as a new record!
2020-12-22 09:52:10	The record with UID 'A128' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A129' added as a new record!
2020-12-22 09:52:10	The record with UID 'A129' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A130' added as a new record!
2020-12-22 09:52:10	The record with UID 'A130' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A131' added as a new record!
2020-12-22 09:52:10	The record with UID 'A131' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A132' added as a new record!
2020-12-22 09:52:10	The record with UID 'A132' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 09:52:10	The record with UID 'A133' added as a new record!
2020-12-22 09:52:10	The record with UID 'A133' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Feb-2021'
2020-12-22 09:52:10	The record with UID 'A134' added as a new record!
2020-12-22 09:52:10	The record with UID 'A134' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 09:52:10	The record with UID 'A135' added as a new record!
2020-12-22 09:52:11	The record with UID 'A135' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A136' added as a new record!
2020-12-22 09:52:11	The record with UID 'A136' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A137' added as a new record!
2020-12-22 09:52:11	The record with UID 'A137' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A138' added as a new record!
2020-12-22 09:52:11	The record with UID 'A138' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A139' added as a new record!
2020-12-22 09:52:11	The record with UID 'A139' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A140' added as a new record!
2020-12-22 09:52:11	The record with UID 'A140' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A141' added as a new record!
2020-12-22 09:52:11	The record with UID 'A141' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A142' added as a new record!
2020-12-22 09:52:11	The record with UID 'A142' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A191' added as a new record!
2020-12-22 09:52:11	The record with UID 'A191' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A192' added as a new record!
2020-12-22 09:52:11	The record with UID 'A192' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A193' added as a new record!
2020-12-22 09:52:11	The record with UID 'A193' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A194' added as a new record!
2020-12-22 09:52:11	The record with UID 'A194' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A196' added as a new record!
2020-12-22 09:52:11	The record with UID 'A196' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A197' added as a new record!
2020-12-22 09:52:11	The record with UID 'A197' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A198' added as a new record!
2020-12-22 09:52:11	The record with UID 'A198' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A199' added as a new record!
2020-12-22 09:52:11	The record with UID 'A199' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A200' added as a new record!
2020-12-22 09:52:11	The record with UID 'A200' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A201' added as a new record!
2020-12-22 09:52:11	The record with UID 'A201' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A202' added as a new record!
2020-12-22 09:52:11	The record with UID 'A202' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A203' added as a new record!
2020-12-22 09:52:11	The record with UID 'A203' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A204' added as a new record!
2020-12-22 09:52:11	The record with UID 'A204' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A205' added as a new record!
2020-12-22 09:52:11	The record with UID 'A205' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A206' added as a new record!
2020-12-22 09:52:11	The record with UID 'A206' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A207' added as a new record!
2020-12-22 09:52:11	The record with UID 'A207' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A233' added as a new record!
2020-12-22 09:52:11	The record with UID 'A233' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A234' added as a new record!
2020-12-22 09:52:11	The record with UID 'A234' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A235' added as a new record!
2020-12-22 09:52:11	The record with UID 'A235' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A236' added as a new record!
2020-12-22 09:52:11	The record with UID 'A236' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A237' added as a new record!
2020-12-22 09:52:11	The record with UID 'A237' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A238' added as a new record!
2020-12-22 09:52:11	The record with UID 'A238' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A239' added as a new record!
2020-12-22 09:52:11	The record with UID 'A239' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A240' added as a new record!
2020-12-22 09:52:11	The record with UID 'A240' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A241' added as a new record!
2020-12-22 09:52:11	The record with UID 'A241' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A242' added as a new record!
2020-12-22 09:52:11	The record with UID 'A242' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A243' added as a new record!
2020-12-22 09:52:11	The record with UID 'A243' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Mar-2021'
2020-12-22 09:52:11	The record with UID 'A244' added as a new record!
2020-12-22 09:52:11	The record with UID 'A244' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A245' added as a new record!
2020-12-22 09:52:11	The record with UID 'A245' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A246' added as a new record!
2020-12-22 09:52:11	The record with UID 'A246' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A264' added as a new record!
2020-12-22 09:52:11	The record with UID 'A264' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A265' added as a new record!
2020-12-22 09:52:11	The record with UID 'A265' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A266' added as a new record!
2020-12-22 09:52:11	The record with UID 'A266' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 09:52:11	The record with UID 'A267' added as a new record!
2020-12-22 09:52:11	The record with UID 'A267' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 09:52:11	The record with UID 'A268' added as a new record!
2020-12-22 09:52:11	The record with UID 'A268' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Jan-2021'
2020-12-22 09:52:12	The record with UID 'A269' added as a new record!
2020-12-22 09:52:12	The record with UID 'A269' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A270' added as a new record!
2020-12-22 09:52:12	The record with UID 'A270' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-May-2021'
2020-12-22 09:52:12	The record with UID 'A271' added as a new record!
2020-12-22 09:52:12	The record with UID 'A271' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A272' added as a new record!
2020-12-22 09:52:12	The record with UID 'A272' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-May-2021'
2020-12-22 09:52:12	The record with UID 'A273' added as a new record!
2020-12-22 09:52:12	The record with UID 'A273' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A274' added as a new record!
2020-12-22 09:52:12	The record with UID 'A274' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A275' added as a new record!
2020-12-22 09:52:12	The record with UID 'A275' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A276' added as a new record!
2020-12-22 09:52:12	The record with UID 'A276' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A277' added as a new record!
2020-12-22 09:52:12	The record with UID 'A277' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A278' added as a new record!
2020-12-22 09:52:12	The record with UID 'A278' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A279' added as a new record!
2020-12-22 09:52:12	The record with UID 'A279' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A280' added as a new record!
2020-12-22 09:52:12	The record with UID 'A280' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A281' added as a new record!
2020-12-22 09:52:12	The record with UID 'A281' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A282' added as a new record!
2020-12-22 09:52:12	The record with UID 'A282' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A283' added as a new record!
2020-12-22 09:52:12	The record with UID 'A283' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A284' added as a new record!
2020-12-22 09:52:12	The record with UID 'A284' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A285' added as a new record!
2020-12-22 09:52:12	The record with UID 'A285' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A296' added as a new record!
2020-12-22 09:52:12	The record with UID 'A296' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Apr-2021'
2020-12-22 09:52:12	The record with UID 'A297' added as a new record!
2020-12-22 09:52:12	The record with UID 'A297' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A298' added as a new record!
2020-12-22 09:52:12	The record with UID 'A298' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A299' added as a new record!
2020-12-22 09:52:12	The record with UID 'A299' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A300' added as a new record!
2020-12-22 09:52:12	The record with UID 'A300' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A301' added as a new record!
2020-12-22 09:52:12	The record with UID 'A301' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A302' added as a new record!
2020-12-22 09:52:12	The record with UID 'A302' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A303' added as a new record!
2020-12-22 09:52:12	The record with UID 'A303' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A304' added as a new record!
2020-12-22 09:52:12	The record with UID 'A304' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A305' added as a new record!
2020-12-22 09:52:12	The record with UID 'A305' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '05-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A307' added as a new record!
2020-12-22 09:52:12	The record with UID 'A307' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A308' added as a new record!
2020-12-22 09:52:12	The record with UID 'A308' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A309' added as a new record!
2020-12-22 09:52:12	The record with UID 'A309' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A310' added as a new record!
2020-12-22 09:52:12	The record with UID 'A310' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A311' added as a new record!
2020-12-22 09:52:12	The record with UID 'A311' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A327' added as a new record!
2020-12-22 09:52:12	The record with UID 'A327' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Jan-2021'
2020-12-22 09:52:12	The record with UID 'A328' added as a new record!
2020-12-22 09:52:12	The record with UID 'A328' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A329' added as a new record!
2020-12-22 09:52:12	The record with UID 'A329' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A330' added as a new record!
2020-12-22 09:52:12	The record with UID 'A330' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A331' added as a new record!
2020-12-22 09:52:12	The record with UID 'A331' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A332' added as a new record!
2020-12-22 09:52:12	The record with UID 'A332' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 09:52:12	The record with UID 'A333' added as a new record!
2020-12-22 09:52:12	The record with UID 'A333' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A334' added as a new record!
2020-12-22 09:52:12	The record with UID 'A334' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A335' added as a new record!
2020-12-22 09:52:12	The record with UID 'A335' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 09:52:12	The record with UID 'A336' added as a new record!
2020-12-22 09:52:13	The record with UID 'A336' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 09:52:13	The record with UID 'A337' added as a new record!
2020-12-22 09:52:13	The record with UID 'A337' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 09:52:13	The record with UID 'A338' added as a new record!
2020-12-22 09:52:13	The record with UID 'A338' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 09:52:13	The record with UID 'A339' added as a new record!
2020-12-22 09:52:13	The record with UID 'A339' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 09:52:13	The record with UID 'A340' added as a new record!
2020-12-22 09:52:13	The record with UID 'A340' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Jan-2021'
2020-12-22 09:52:13	Merge Operation Finished!
2020-12-22 10:17:52	The CSV Imported Successfully to Timebars
2020-12-22 10:18:14	The CSV Imported Successfully to MetaData
2020-12-22 10:18:25	Merge Operation Started!
2020-12-22 10:18:25	The record with UID 'A062' updated from 'Timebars'! Details: Field['Finish'] :: '03-May-2021' ----> '04-Apr-2021'
2020-12-22 10:18:25	The record with UID 'A234' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '10-Mar-2021'
2020-12-22 10:18:25	The record with UID 'A235' updated from 'Timebars'! Details: Field['Finish'] :: '13-Feb-2021' ----> '19-Feb-2021'
2020-12-22 10:18:25	The record with UID 'A264' updated from 'Timebars'! Details: Field['Finish'] :: '26-Jan-2021' ----> '07-Feb-2021'
2020-12-22 10:18:25	The record with UID 'A008' updated from 'Timebars'! Details: Field['Finish'] :: '09-May-2021' ----> '15-May-2021'
2020-12-22 10:18:25	The record with UID 'A238' updated from 'Timebars'! Details: Field['Finish'] :: '14-Jan-2021' ----> '20-Jan-2021'
2020-12-22 10:18:25	The record with UID 'A237' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '17-Feb-2021'
2020-12-22 10:18:25	The record with UID 'A233' updated from 'Timebars'! Details: Field['Finish'] :: '10-Mar-2021' ----> '16-Mar-2021'
2020-12-22 10:18:25	The record with UID 'A266' updated from 'Timebars'! Details: Field['Finish'] :: '02-Feb-2021' ----> '14-Feb-2021'
2020-12-22 10:18:25	The record with UID 'A268' updated from 'Timebars'! Details: Field['Finish'] :: '15-Jan-2021' ----> '27-Jan-2021'
2020-12-22 10:18:25	The record with UID 'A011' updated from 'Timebars'! Details: Field['Finish'] :: '27-May-2021' ----> '20-May-2021'
2020-12-22 10:18:25	The record with UID 'A269' updated from 'Timebars'! Details: Field['Finish'] :: '14-Apr-2021' ----> '16-Mar-2021'
2020-12-22 10:18:25	The record with UID 'A277' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '03-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A021' updated from 'Timebars'! Details: Field['Finish'] :: '18-Mar-2021' ----> '13-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A265' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '12-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A267' updated from 'Timebars'! Details: Field['Finish'] :: '15-Jan-2021' ----> '27-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A285' updated from 'Timebars'! Details: Field['Finish'] :: '02-Mar-2021' ----> '01-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A282' updated from 'Timebars'! Details: Field['Finish'] :: '25-Mar-2021' ----> '24-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A270' updated from 'Timebars'! Details: Field['Finish'] :: '01-May-2021' ----> '02-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A049' updated from 'Timebars'! Details: Field['Finish'] :: '16-Mar-2021' ----> '11-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A279' updated from 'Timebars'! Details: Field['Finish'] :: '24-Apr-2021' ----> '26-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A281' updated from 'Timebars'! Details: Field['Finish'] :: '02-Mar-2021' ----> '01-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A284' updated from 'Timebars'! Details: Field['Finish'] :: '17-Mar-2021' ----> '16-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A033' updated from 'Timebars'! Details: Field['Finish'] :: '14-Mar-2021' ----> '20-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A124' updated from 'Timebars'! Details: Field['Finish'] :: '12-Sep-2020' ----> '02-Sep-2020'
2020-12-22 10:18:26	The record with UID 'A022' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '15-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A138' updated from 'Timebars'! Details: Field['Finish'] :: '21-Feb-2021' ----> '16-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A139' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '06-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A278' updated from 'Timebars'! Details: Field['Finish'] :: '29-Apr-2021' ----> '31-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A283' updated from 'Timebars'! Details: Field['Finish'] :: '19-Mar-2021' ----> '18-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A123' updated from 'Timebars'! Details: Field['Finish'] :: '13-Sep-2020' ----> '03-Sep-2020'
2020-12-22 10:18:26	The record with UID 'A141' updated from 'Timebars'! Details: Field['Finish'] :: '12-Feb-2021' ----> '07-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A065' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '15-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A041' updated from 'Timebars'! Details: Field['Finish'] :: '14-Mar-2021' ----> '19-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A122' updated from 'Timebars'! Details: Field['Finish'] :: '13-Sep-2020' ----> '03-Sep-2020'
2020-12-22 10:18:26	The record with UID 'A140' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '01-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A142' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '06-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A276' updated from 'Timebars'! Details: Field['Finish'] :: '28-Feb-2021' ----> '30-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A036' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '28-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A280' updated from 'Timebars'! Details: Field['Finish'] :: '28-Mar-2021' ----> '27-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A271' updated from 'Timebars'! Details: Field['Finish'] :: '28-Apr-2021' ----> '30-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A121' updated from 'Timebars'! Details: Field['Finish'] :: '30-Sep-2020' ----> '20-Sep-2020'
2020-12-22 10:18:26	The record with UID 'A308' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '15-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A111' updated from 'Timebars'! Details: Field['Finish'] :: '27-Nov-2020' ----> '02-Dec-2020'
2020-12-22 10:18:26	The record with UID 'A113' updated from 'Timebars'! Details: Field['Finish'] :: '15-Dec-2020' ----> '20-Dec-2020'
2020-12-22 10:18:26	The record with UID 'A112' updated from 'Timebars'! Details: Field['Finish'] :: '15-Jan-2021' ----> '20-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A107' updated from 'Timebars'! Details: Field['Finish'] :: '27-Nov-2020' ----> '02-Dec-2020'
2020-12-22 10:18:26	The record with UID 'A274' updated from 'Timebars'! Details: Field['Finish'] :: '10-Mar-2021' ----> '09-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A275' updated from 'Timebars'! Details: Field['Finish'] :: '19-Feb-2021' ----> '21-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A273' updated from 'Timebars'! Details: Field['Finish'] :: '02-Apr-2021' ----> '04-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A272' updated from 'Timebars'! Details: Field['Finish'] :: '01-May-2021' ----> '02-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A044' updated from 'Timebars'! Details: Field['Finish'] :: '08-Feb-2021' ----> '02-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A045' updated from 'Timebars'! Details: Field['Finish'] :: '27-Feb-2021' ----> '21-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A310' updated from 'Timebars'! Details: Field['Finish'] :: '28-Feb-2021' ----> '23-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A125' updated from 'Timebars'! Details: Field['Finish'] :: '29-Sep-2020' ----> '19-Sep-2020'
2020-12-22 10:18:26	The record with UID 'A110' updated from 'Timebars'! Details: Field['Finish'] :: '24-Dec-2020' ----> '29-Dec-2020'
2020-12-22 10:18:26	The record with UID 'A108' updated from 'Timebars'! Details: Field['Finish'] :: '11-Dec-2020' ----> '16-Dec-2020'
2020-12-22 10:18:26	The record with UID 'A311' updated from 'Timebars'! Details: Field['Finish'] :: '02-Mar-2021' ----> '25-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A309' updated from 'Timebars'! Details: Field['Finish'] :: '26-Feb-2021' ----> '21-Feb-2021'
2020-12-22 10:18:26	The record with UID 'A004' updated from 'Timebars'! Details: Field['Finish'] :: '22-Apr-2021' ----> '21-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A307' updated from 'Timebars'! Details: Field['Finish'] :: '15-Mar-2021' ----> '10-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A007' updated from 'Timebars'! Details: Field['Finish'] :: '13-Mar-2021' ----> '12-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A017' updated from 'Timebars'! Details: Field['Finish'] :: '28-Mar-2021' ----> '08-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A031' updated from 'Timebars'! Details: Field['Finish'] :: '09-Mar-2021' ----> '08-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A069' updated from 'Timebars'! Details: Field['Finish'] :: '09-Mar-2021' ----> '08-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A333' updated from 'Timebars'! Details: Field['Finish'] :: '08-Mar-2021' ----> '07-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A012' updated from 'Timebars'! Details: Field['Finish'] :: '16-Apr-2021' ----> '15-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A335' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '03-Mar-2021'
2020-12-22 10:18:26	The record with UID 'A030' updated from 'Timebars'! Details: Field['Finish'] :: '04-Apr-2021' ----> '03-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A336' updated from 'Timebars'! Details: Field['Finish'] :: '01-Feb-2021' ----> '31-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A064' updated from 'Timebars'! Details: Field['Finish'] :: '04-Apr-2021' ----> '03-Apr-2021'
2020-12-22 10:18:26	The record with UID 'A338' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '30-Jan-2021'
2020-12-22 10:18:26	The record with UID 'A337' updated from 'Timebars'! Details: Field['Finish'] :: '21-Feb-2021' ----> '20-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A334' updated from 'Timebars'! Details: Field['Finish'] :: '07-Mar-2021' ----> '06-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A296' updated from 'Timebars'! Details: Field['Finish'] :: '01-Apr-2021' ----> '31-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A303' updated from 'Timebars'! Details: Field['Finish'] :: '17-Mar-2021' ----> '16-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A304' updated from 'Timebars'! Details: Field['Finish'] :: '09-Feb-2021' ----> '08-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A339' updated from 'Timebars'! Details: Field['Finish'] :: '15-Feb-2021' ----> '14-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A340' updated from 'Timebars'! Details: Field['Finish'] :: '27-Jan-2021' ----> '26-Jan-2021'
2020-12-22 10:18:27	The record with UID 'A029' updated from 'Timebars'! Details: Field['Finish'] :: '01-Apr-2021' ----> '31-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A297' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '19-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A305' updated from 'Timebars'! Details: Field['Finish'] :: '05-Feb-2021' ----> '04-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A298' updated from 'Timebars'! Details: Field['Finish'] :: '28-Feb-2021' ----> '27-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A055' updated from 'Timebars'! Details: Field['Finish'] :: '31-Mar-2021' ----> '30-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A301' updated from 'Timebars'! Details: Field['Finish'] :: '17-Feb-2021' ----> '16-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A300' updated from 'Timebars'! Details: Field['Finish'] :: '01-Feb-2021' ----> '31-Jan-2021'
2020-12-22 10:18:27	The record with UID 'A299' updated from 'Timebars'! Details: Field['Finish'] :: '12-Mar-2021' ----> '11-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A198' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '05-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A200' updated from 'Timebars'! Details: Field['Finish'] :: '30-Mar-2021' ----> '29-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A205' updated from 'Timebars'! Details: Field['Finish'] :: '12-Feb-2021' ----> '11-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A302' updated from 'Timebars'! Details: Field['Finish'] :: '17-Mar-2021' ----> '16-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A206' updated from 'Timebars'! Details: Field['Finish'] :: '18-Feb-2021' ----> '17-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A207' updated from 'Timebars'! Details: Field['Finish'] :: '22-Mar-2021' ----> '21-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A199' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '10-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A202' updated from 'Timebars'! Details: Field['Finish'] :: '14-Mar-2021' ----> '13-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A204' updated from 'Timebars'! Details: Field['Finish'] :: '29-Jan-2021' ----> '28-Jan-2021'
2020-12-22 10:18:27	The record with UID 'A201' updated from 'Timebars'! Details: Field['Finish'] :: '27-Mar-2021' ----> '26-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A203' updated from 'Timebars'! Details: Field['Finish'] :: '27-Feb-2021' ----> '26-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A047' updated from 'Timebars'! Details: Field['Finish'] :: '22-Mar-2021' ----> '02-Apr-2021'
2020-12-22 10:18:27	The record with UID 'A048' updated from 'Timebars'! Details: Field['Finish'] :: '26-Mar-2021' ----> '06-Apr-2021'
2020-12-22 10:18:27	The record with UID 'A013' updated from 'Timebars'! Details: Field['Finish'] :: '13-Apr-2021' ----> '23-Apr-2021'
2020-12-22 10:18:27	The record with UID 'A136' updated from 'Timebars'! Details: Field['Finish'] :: '19-Mar-2021' ----> '30-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A137' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '11-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A023' updated from 'Timebars'! Details: Field['Finish'] :: '12-Mar-2021' ----> '28-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A135' updated from 'Timebars'! Details: Field['Finish'] :: '08-Feb-2021' ----> '19-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A134' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '22-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A054' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '23-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A133' updated from 'Timebars'! Details: Field['Finish'] :: '25-Feb-2021' ----> '08-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A026' updated from 'Timebars'! Details: Field['Finish'] :: '26-May-2021' ----> '30-May-2021'
2020-12-22 10:18:27	The record with UID 'A192' updated from 'Timebars'! Details: Field['Finish'] :: '28-Jan-2021' ----> '16-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A193' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '23-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A020' updated from 'Timebars'! Details: Field['Finish'] :: '21-Mar-2021' ----> '28-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A018' updated from 'Timebars'! Details: Field['Finish'] :: '17-Apr-2021' ----> '21-Apr-2021'
2020-12-22 10:18:27	The record with UID 'A194' updated from 'Timebars'! Details: Field['Finish'] :: '10-Feb-2021' ----> '01-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A059' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '26-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A196' updated from 'Timebars'! Details: Field['Finish'] :: '12-Feb-2021' ----> '03-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A068' updated from 'Timebars'! Details: Field['Finish'] :: '14-Mar-2021' ----> '18-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A241' updated from 'Timebars'! Details: Field['Finish'] :: '19-Jan-2021' ----> '03-Feb-2021'
2020-12-22 10:18:27	The record with UID 'A243' updated from 'Timebars'! Details: Field['Finish'] :: '03-Mar-2021' ----> '18-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A242' updated from 'Timebars'! Details: Field['Finish'] :: '14-Feb-2021' ----> '01-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A191' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '23-Mar-2021'
2020-12-22 10:18:27	The record with UID 'A197' updated from 'Timebars'! Details: Field['Finish'] :: '29-Jan-2021' ----> '17-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A327' updated from 'Timebars'! Details: Field['Finish'] :: '28-Jan-2021' ----> '01-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A329' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '15-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A244' updated from 'Timebars'! Details: Field['Finish'] :: '20-Jan-2021' ----> '04-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A245' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '26-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A332' updated from 'Timebars'! Details: Field['Finish'] :: '02-Feb-2021' ----> '06-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A330' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '10-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A002' updated from 'Timebars'! Details: Field['Finish'] :: '04-May-2022' ----> '10-May-2022'
2020-12-22 10:18:28	The record with UID 'A246' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '15-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A240' updated from 'Timebars'! Details: Field['Finish'] :: '26-Feb-2021' ----> '13-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A024' updated from 'Timebars'! Details: Field['Finish'] :: '24-Mar-2021' ----> '09-Apr-2021'
2020-12-22 10:18:28	The record with UID 'A331' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '15-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A328' updated from 'Timebars'! Details: Field['Finish'] :: '12-Mar-2021' ----> '16-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A239' updated from 'Timebars'! Details: Field['Finish'] :: '07-Mar-2021' ----> '22-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A046' updated from 'Timebars'! Details: Field['Finish'] :: '23-Feb-2021' ----> '11-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A126' updated from 'Timebars'! Details: Field['Finish'] :: '06-Jan-2021' ----> '22-Jan-2021'
2020-12-22 10:18:28	The record with UID 'A128' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '27-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A127' updated from 'Timebars'! Details: Field['Finish'] :: '18-Jan-2021' ----> '03-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A003' updated from 'Timebars'! Details: Field['Order'] :: '818' ----> '988'
2020-12-22 10:18:28	The record with UID 'A129' updated from 'Timebars'! Details: Field['Finish'] :: '17-Jan-2021' ----> '02-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A130' updated from 'Timebars'! Details: Field['Finish'] :: '07-Feb-2021' ----> '23-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A009' updated from 'Timebars'! Details: Field['Finish'] :: '13-May-2021' ----> '17-May-2021'
2020-12-22 10:18:28	The record with UID 'A132' updated from 'Timebars'! Details: Field['Finish'] :: '17-Jan-2021' ----> '02-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A131' updated from 'Timebars'! Details: Field['Finish'] :: '18-Feb-2021' ----> '06-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A027' updated from 'Timebars'! Details: Field['Finish'] :: '25-Mar-2021' ----> '05-Apr-2021'
2020-12-22 10:18:28	The record with UID 'A058' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '26-Mar-2021'
2020-12-22 10:18:28	The record with UID 'A019' updated from 'Timebars'! Details: Field['Finish'] :: '03-Feb-2021' ----> '15-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A010' updated from 'Timebars'! Details: Field['Finish'] :: '03-May-2021' ----> '04-Apr-2021'
2020-12-22 10:18:28	The record with UID 'A236' updated from 'Timebars'! Details: Field['Finish'] :: '17-Jan-2021' ----> '23-Jan-2021'
2020-12-22 10:18:28	The record with UID 'A061' updated from 'Timebars'! Details: Field['Finish'] :: '03-Feb-2021' ----> '15-Feb-2021'
2020-12-22 10:18:28	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '15-Jan-2021' ----> '20-Jan-2021'
2020-12-22 10:18:28	Merge Operation Finished!
2020-12-22 10:18:55	Merge Operation Started!
2020-12-22 10:18:56	The record with UID 'A003' added as a new record!
2020-12-22 10:18:56	The record with UID 'A003' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '45'
2020-12-22 10:18:56	The record with UID 'A003' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Jul-2022'
2020-12-22 10:18:56	The record with UID 'A004' added as a new record!
2020-12-22 10:18:56	The record with UID 'A004' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '46'
2020-12-22 10:18:56	The record with UID 'A004' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Apr-2021'
2020-12-22 10:18:56	The record with UID 'A007' added as a new record!
2020-12-22 10:18:56	The record with UID 'A007' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '47'
2020-12-22 10:18:56	The record with UID 'A007' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Mar-2021'
2020-12-22 10:18:56	The record with UID 'A008' added as a new record!
2020-12-22 10:18:56	The record with UID 'A008' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '48'
2020-12-22 10:18:56	The record with UID 'A008' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-May-2021'
2020-12-22 10:18:56	The record with UID 'A009' added as a new record!
2020-12-22 10:18:57	The record with UID 'A009' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '49'
2020-12-22 10:18:57	The record with UID 'A009' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-May-2021'
2020-12-22 10:18:57	The record with UID 'A010' added as a new record!
2020-12-22 10:18:57	The record with UID 'A010' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '50'
2020-12-22 10:18:57	The record with UID 'A010' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A011' added as a new record!
2020-12-22 10:18:57	The record with UID 'A011' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '51'
2020-12-22 10:18:57	The record with UID 'A011' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-May-2021'
2020-12-22 10:18:57	The record with UID 'A012' added as a new record!
2020-12-22 10:18:57	The record with UID 'A012' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '52'
2020-12-22 10:18:57	The record with UID 'A012' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A013' added as a new record!
2020-12-22 10:18:57	The record with UID 'A013' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '53'
2020-12-22 10:18:57	The record with UID 'A013' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A017' added as a new record!
2020-12-22 10:18:57	The record with UID 'A017' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '54'
2020-12-22 10:18:57	The record with UID 'A017' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A018' added as a new record!
2020-12-22 10:18:57	The record with UID 'A018' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 10:18:57	The record with UID 'A018' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A019' added as a new record!
2020-12-22 10:18:57	The record with UID 'A019' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 10:18:57	The record with UID 'A019' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 10:18:57	The record with UID 'A020' added as a new record!
2020-12-22 10:18:57	The record with UID 'A020' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 10:18:57	The record with UID 'A020' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 10:18:57	The record with UID 'A021' added as a new record!
2020-12-22 10:18:57	The record with UID 'A021' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 10:18:57	The record with UID 'A021' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Mar-2021'
2020-12-22 10:18:57	The record with UID 'A022' added as a new record!
2020-12-22 10:18:57	The record with UID 'A022' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 10:18:57	The record with UID 'A022' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 10:18:57	The record with UID 'A023' added as a new record!
2020-12-22 10:18:57	The record with UID 'A023' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 10:18:57	The record with UID 'A023' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Mar-2021'
2020-12-22 10:18:57	The record with UID 'A024' added as a new record!
2020-12-22 10:18:57	The record with UID 'A024' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 10:18:57	The record with UID 'A024' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Apr-2021'
2020-12-22 10:18:57	The record with UID 'A026' added as a new record!
2020-12-22 10:18:57	The record with UID 'A026' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '55'
2020-12-22 10:18:57	The record with UID 'A026' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-May-2021'
2020-12-22 10:18:58	The record with UID 'A027' added as a new record!
2020-12-22 10:18:58	The record with UID 'A027' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '57'
2020-12-22 10:18:58	The record with UID 'A027' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '05-Apr-2021'
2020-12-22 10:18:58	The record with UID 'A029' added as a new record!
2020-12-22 10:18:58	The record with UID 'A029' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '58'
2020-12-22 10:18:58	The record with UID 'A029' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A030' added as a new record!
2020-12-22 10:18:58	The record with UID 'A030' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '59'
2020-12-22 10:18:58	The record with UID 'A030' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Apr-2021'
2020-12-22 10:18:58	The record with UID 'A031' added as a new record!
2020-12-22 10:18:58	The record with UID 'A031' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '60'
2020-12-22 10:18:58	The record with UID 'A031' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A033' added as a new record!
2020-12-22 10:18:58	The record with UID 'A033' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '61'
2020-12-22 10:18:58	The record with UID 'A033' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A036' added as a new record!
2020-12-22 10:18:58	The record with UID 'A036' updated from 'MetaData'! Details: Field['Customer ID'] :: '' ----> '62'
2020-12-22 10:18:58	The record with UID 'A036' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Feb-2021'
2020-12-22 10:18:58	The record with UID 'A002' added as a new record!
2020-12-22 10:18:58	The record with UID 'A002' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-May-2022'
2020-12-22 10:18:58	The record with UID 'A062' added as a new record!
2020-12-22 10:18:58	The record with UID 'A062' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Apr-2021'
2020-12-22 10:18:58	The record with UID 'A047' added as a new record!
2020-12-22 10:18:58	The record with UID 'A047' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Apr-2021'
2020-12-22 10:18:58	The record with UID 'A048' added as a new record!
2020-12-22 10:18:58	The record with UID 'A048' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Apr-2021'
2020-12-22 10:18:58	The record with UID 'A068' added as a new record!
2020-12-22 10:18:58	The record with UID 'A068' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A061' added as a new record!
2020-12-22 10:18:58	The record with UID 'A061' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 10:18:58	The record with UID 'A059' added as a new record!
2020-12-22 10:18:58	The record with UID 'A059' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 10:18:58	The record with UID 'A049' added as a new record!
2020-12-22 10:18:58	The record with UID 'A049' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A065' added as a new record!
2020-12-22 10:18:58	The record with UID 'A065' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A054' added as a new record!
2020-12-22 10:18:58	The record with UID 'A054' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A046' added as a new record!
2020-12-22 10:18:58	The record with UID 'A046' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A058' added as a new record!
2020-12-22 10:18:58	The record with UID 'A058' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A055' added as a new record!
2020-12-22 10:18:58	The record with UID 'A055' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Mar-2021'
2020-12-22 10:18:58	The record with UID 'A064' added as a new record!
2020-12-22 10:18:59	The record with UID 'A064' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Apr-2021'
2020-12-22 10:18:59	The record with UID 'A069' added as a new record!
2020-12-22 10:18:59	The record with UID 'A069' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Mar-2021'
2020-12-22 10:18:59	The record with UID 'A041' added as a new record!
2020-12-22 10:18:59	The record with UID 'A041' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 10:18:59	The record with UID 'A044' added as a new record!
2020-12-22 10:18:59	The record with UID 'A044' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A107' added as a new record!
2020-12-22 10:18:59	The record with UID 'A107' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Dec-2020'
2020-12-22 10:18:59	The record with UID 'A108' added as a new record!
2020-12-22 10:18:59	The record with UID 'A108' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Dec-2020'
2020-12-22 10:18:59	The record with UID 'A109' added as a new record!
2020-12-22 10:18:59	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 10:18:59	The record with UID 'A110' added as a new record!
2020-12-22 10:18:59	The record with UID 'A110' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Dec-2020'
2020-12-22 10:18:59	The record with UID 'A111' added as a new record!
2020-12-22 10:18:59	The record with UID 'A111' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Dec-2020'
2020-12-22 10:18:59	The record with UID 'A112' added as a new record!
2020-12-22 10:18:59	The record with UID 'A112' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 10:18:59	The record with UID 'A113' added as a new record!
2020-12-22 10:18:59	The record with UID 'A113' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Dec-2020'
2020-12-22 10:18:59	The record with UID 'A045' added as a new record!
2020-12-22 10:18:59	The record with UID 'A045' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A121' added as a new record!
2020-12-22 10:18:59	The record with UID 'A121' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Sep-2020'
2020-12-22 10:18:59	The record with UID 'A122' added as a new record!
2020-12-22 10:18:59	The record with UID 'A122' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Sep-2020'
2020-12-22 10:18:59	The record with UID 'A123' added as a new record!
2020-12-22 10:18:59	The record with UID 'A123' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Sep-2020'
2020-12-22 10:18:59	The record with UID 'A124' added as a new record!
2020-12-22 10:18:59	The record with UID 'A124' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Sep-2020'
2020-12-22 10:18:59	The record with UID 'A125' added as a new record!
2020-12-22 10:18:59	The record with UID 'A125' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Sep-2020'
2020-12-22 10:18:59	The record with UID 'A126' added as a new record!
2020-12-22 10:18:59	The record with UID 'A126' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Jan-2021'
2020-12-22 10:18:59	The record with UID 'A127' added as a new record!
2020-12-22 10:18:59	The record with UID 'A127' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A128' added as a new record!
2020-12-22 10:18:59	The record with UID 'A128' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A129' added as a new record!
2020-12-22 10:18:59	The record with UID 'A129' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A130' added as a new record!
2020-12-22 10:18:59	The record with UID 'A130' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A131' added as a new record!
2020-12-22 10:18:59	The record with UID 'A131' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 10:18:59	The record with UID 'A132' added as a new record!
2020-12-22 10:18:59	The record with UID 'A132' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A133' added as a new record!
2020-12-22 10:18:59	The record with UID 'A133' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Mar-2021'
2020-12-22 10:18:59	The record with UID 'A134' added as a new record!
2020-12-22 10:18:59	The record with UID 'A134' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 10:18:59	The record with UID 'A135' added as a new record!
2020-12-22 10:18:59	The record with UID 'A135' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Feb-2021'
2020-12-22 10:18:59	The record with UID 'A136' added as a new record!
2020-12-22 10:19:00	The record with UID 'A136' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A137' added as a new record!
2020-12-22 10:19:00	The record with UID 'A137' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A138' added as a new record!
2020-12-22 10:19:00	The record with UID 'A138' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A139' added as a new record!
2020-12-22 10:19:00	The record with UID 'A139' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A140' added as a new record!
2020-12-22 10:19:00	The record with UID 'A140' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A141' added as a new record!
2020-12-22 10:19:00	The record with UID 'A141' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A142' added as a new record!
2020-12-22 10:19:00	The record with UID 'A142' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A191' added as a new record!
2020-12-22 10:19:00	The record with UID 'A191' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A192' added as a new record!
2020-12-22 10:19:00	The record with UID 'A192' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A193' added as a new record!
2020-12-22 10:19:00	The record with UID 'A193' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A194' added as a new record!
2020-12-22 10:19:00	The record with UID 'A194' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A196' added as a new record!
2020-12-22 10:19:00	The record with UID 'A196' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A197' added as a new record!
2020-12-22 10:19:00	The record with UID 'A197' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A198' added as a new record!
2020-12-22 10:19:00	The record with UID 'A198' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '05-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A199' added as a new record!
2020-12-22 10:19:00	The record with UID 'A199' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A200' added as a new record!
2020-12-22 10:19:00	The record with UID 'A200' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '29-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A201' added as a new record!
2020-12-22 10:19:00	The record with UID 'A201' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A202' added as a new record!
2020-12-22 10:19:00	The record with UID 'A202' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A203' added as a new record!
2020-12-22 10:19:00	The record with UID 'A203' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A204' added as a new record!
2020-12-22 10:19:00	The record with UID 'A204' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '28-Jan-2021'
2020-12-22 10:19:00	The record with UID 'A205' added as a new record!
2020-12-22 10:19:00	The record with UID 'A205' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A206' added as a new record!
2020-12-22 10:19:00	The record with UID 'A206' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A207' added as a new record!
2020-12-22 10:19:00	The record with UID 'A207' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A233' added as a new record!
2020-12-22 10:19:00	The record with UID 'A233' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A234' added as a new record!
2020-12-22 10:19:00	The record with UID 'A234' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A235' added as a new record!
2020-12-22 10:19:00	The record with UID 'A235' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A236' added as a new record!
2020-12-22 10:19:00	The record with UID 'A236' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Jan-2021'
2020-12-22 10:19:00	The record with UID 'A237' added as a new record!
2020-12-22 10:19:00	The record with UID 'A237' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '17-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A238' added as a new record!
2020-12-22 10:19:00	The record with UID 'A238' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 10:19:00	The record with UID 'A239' added as a new record!
2020-12-22 10:19:00	The record with UID 'A239' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '22-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A240' added as a new record!
2020-12-22 10:19:00	The record with UID 'A240' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '13-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A241' added as a new record!
2020-12-22 10:19:00	The record with UID 'A241' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A242' added as a new record!
2020-12-22 10:19:00	The record with UID 'A242' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A243' added as a new record!
2020-12-22 10:19:00	The record with UID 'A243' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Mar-2021'
2020-12-22 10:19:00	The record with UID 'A244' added as a new record!
2020-12-22 10:19:00	The record with UID 'A244' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A245' added as a new record!
2020-12-22 10:19:00	The record with UID 'A245' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A246' added as a new record!
2020-12-22 10:19:00	The record with UID 'A246' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A264' added as a new record!
2020-12-22 10:19:00	The record with UID 'A264' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A265' added as a new record!
2020-12-22 10:19:00	The record with UID 'A265' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '12-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A266' added as a new record!
2020-12-22 10:19:00	The record with UID 'A266' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Feb-2021'
2020-12-22 10:19:00	The record with UID 'A267' added as a new record!
2020-12-22 10:19:00	The record with UID 'A267' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Jan-2021'
2020-12-22 10:19:00	The record with UID 'A268' added as a new record!
2020-12-22 10:19:00	The record with UID 'A268' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Jan-2021'
2020-12-22 10:19:00	The record with UID 'A269' added as a new record!
2020-12-22 10:19:01	The record with UID 'A269' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A270' added as a new record!
2020-12-22 10:19:01	The record with UID 'A270' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Apr-2021'
2020-12-22 10:19:01	The record with UID 'A271' added as a new record!
2020-12-22 10:19:01	The record with UID 'A271' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A272' added as a new record!
2020-12-22 10:19:01	The record with UID 'A272' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '02-Apr-2021'
2020-12-22 10:19:01	The record with UID 'A273' added as a new record!
2020-12-22 10:19:01	The record with UID 'A273' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A274' added as a new record!
2020-12-22 10:19:01	The record with UID 'A274' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '09-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A275' added as a new record!
2020-12-22 10:19:01	The record with UID 'A275' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Jan-2021'
2020-12-22 10:19:01	The record with UID 'A276' added as a new record!
2020-12-22 10:19:01	The record with UID 'A276' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Jan-2021'
2020-12-22 10:19:01	The record with UID 'A277' added as a new record!
2020-12-22 10:19:01	The record with UID 'A277' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A278' added as a new record!
2020-12-22 10:19:01	The record with UID 'A278' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A279' added as a new record!
2020-12-22 10:19:01	The record with UID 'A279' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A280' added as a new record!
2020-12-22 10:19:01	The record with UID 'A280' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A281' added as a new record!
2020-12-22 10:19:01	The record with UID 'A281' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A282' added as a new record!
2020-12-22 10:19:01	The record with UID 'A282' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '24-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A283' added as a new record!
2020-12-22 10:19:01	The record with UID 'A283' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '18-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A284' added as a new record!
2020-12-22 10:19:01	The record with UID 'A284' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A285' added as a new record!
2020-12-22 10:19:01	The record with UID 'A285' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A296' added as a new record!
2020-12-22 10:19:01	The record with UID 'A296' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A297' added as a new record!
2020-12-22 10:19:01	The record with UID 'A297' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '19-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A298' added as a new record!
2020-12-22 10:19:01	The record with UID 'A298' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '27-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A299' added as a new record!
2020-12-22 10:19:01	The record with UID 'A299' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '11-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A300' added as a new record!
2020-12-22 10:19:01	The record with UID 'A300' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 10:19:01	The record with UID 'A301' added as a new record!
2020-12-22 10:19:01	The record with UID 'A301' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A302' added as a new record!
2020-12-22 10:19:01	The record with UID 'A302' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A303' added as a new record!
2020-12-22 10:19:01	The record with UID 'A303' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A304' added as a new record!
2020-12-22 10:19:01	The record with UID 'A304' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '08-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A305' added as a new record!
2020-12-22 10:19:01	The record with UID 'A305' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '04-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A307' added as a new record!
2020-12-22 10:19:01	The record with UID 'A307' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A308' added as a new record!
2020-12-22 10:19:01	The record with UID 'A308' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A309' added as a new record!
2020-12-22 10:19:01	The record with UID 'A309' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '21-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A310' added as a new record!
2020-12-22 10:19:01	The record with UID 'A310' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '23-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A311' added as a new record!
2020-12-22 10:19:01	The record with UID 'A311' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '25-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A327' added as a new record!
2020-12-22 10:19:01	The record with UID 'A327' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '01-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A328' added as a new record!
2020-12-22 10:19:01	The record with UID 'A328' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '16-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A329' added as a new record!
2020-12-22 10:19:01	The record with UID 'A329' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A330' added as a new record!
2020-12-22 10:19:01	The record with UID 'A330' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '10-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A331' added as a new record!
2020-12-22 10:19:01	The record with UID 'A331' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '15-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A332' added as a new record!
2020-12-22 10:19:01	The record with UID 'A332' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Feb-2021'
2020-12-22 10:19:01	The record with UID 'A333' added as a new record!
2020-12-22 10:19:01	The record with UID 'A333' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '07-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A334' added as a new record!
2020-12-22 10:19:01	The record with UID 'A334' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '06-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A335' added as a new record!
2020-12-22 10:19:01	The record with UID 'A335' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '03-Mar-2021'
2020-12-22 10:19:01	The record with UID 'A336' added as a new record!
2020-12-22 10:19:01	The record with UID 'A336' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '31-Jan-2021'
2020-12-22 10:19:01	The record with UID 'A337' added as a new record!
2020-12-22 10:19:02	The record with UID 'A337' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Feb-2021'
2020-12-22 10:19:02	The record with UID 'A338' added as a new record!
2020-12-22 10:19:02	The record with UID 'A338' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '30-Jan-2021'
2020-12-22 10:19:02	The record with UID 'A339' added as a new record!
2020-12-22 10:19:02	The record with UID 'A339' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '14-Feb-2021'
2020-12-22 10:19:02	The record with UID 'A340' added as a new record!
2020-12-22 10:19:02	The record with UID 'A340' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '26-Jan-2021'
2020-12-22 10:19:02	Merge Operation Finished!
2020-12-22 10:31:30	The CSV Imported Successfully to Timebars
2020-12-22 10:32:15	Merge Operation Started!
2020-12-22 10:32:15	The record with UID 'A330' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '991'
2020-12-22 10:32:15	The record with UID 'A003' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '988'
2020-12-22 10:32:15	The record with UID 'A332' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '985'
2020-12-22 10:32:15	The record with UID 'A329' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '930'
2020-12-22 10:32:15	The record with UID 'A327' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '922'
2020-12-22 10:32:16	The record with UID 'A068' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '876'
2020-12-22 10:32:16	The record with UID 'A018' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '834'
2020-12-22 10:32:16	The record with UID 'A131' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '831'
2020-12-22 10:32:16	The record with UID 'A132' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '826'
2020-12-22 10:32:16	The record with UID 'A130' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '786'
2020-12-22 10:32:16	The record with UID 'A026' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '783'
2020-12-22 10:32:16	The record with UID 'A129' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '783'
2020-12-22 10:32:16	The record with UID 'A127' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '737'
2020-12-22 10:32:16	The record with UID 'A126' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '734'
2020-12-22 10:32:16	The record with UID 'A128' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '734'
2020-12-22 10:32:16	The record with UID 'A191' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '720'
2020-12-22 10:32:16	The record with UID 'A197' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '720'
2020-12-22 10:32:16	The record with UID 'A046' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '699'
2020-12-22 10:32:16	The record with UID 'A196' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '676'
2020-12-22 10:32:16	The record with UID 'A024' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '651'
2020-12-22 10:32:16	The record with UID 'A194' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '633'
2020-12-22 10:32:16	The record with UID 'A002' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '61'
2020-12-22 10:32:16	The record with UID 'A239' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '604'
2020-12-22 10:32:16	The record with UID 'A193' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '588'
2020-12-22 10:32:16	The record with UID 'A192' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '587'
2020-12-22 10:32:16	The record with UID 'A240' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '557'
2020-12-22 10:32:16	The record with UID 'A246' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '549'
2020-12-22 10:32:16	The record with UID 'A054' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '545'
2020-12-22 10:32:16	The record with UID 'A245' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '502'
2020-12-22 10:32:16	The record with UID 'A244' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '496'
2020-12-22 10:32:16	The record with UID 'A023' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '487'
2020-12-22 10:32:16	The record with UID 'A242' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '433'
2020-12-22 10:32:16	The record with UID 'A013' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '432'
2020-12-22 10:32:16	The record with UID 'A243' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '432'
2020-12-22 10:32:16	The record with UID 'A241' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '430'
2020-12-22 10:32:16	The record with UID 'A133' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '417'
2020-12-22 10:32:16	The record with UID 'A059' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '373'
2020-12-22 10:32:16	The record with UID 'A134' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '365'
2020-12-22 10:32:16	The record with UID 'A135' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '363'
2020-12-22 10:32:16	The record with UID 'A020' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '328'
2020-12-22 10:32:17	The record with UID 'A137' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '317'
2020-12-22 10:32:17	The record with UID 'A136' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '314'
2020-12-22 10:32:17	The record with UID 'A203' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2878'
2020-12-22 10:32:17	The record with UID 'A201' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2870'
2020-12-22 10:32:17	The record with UID 'A204' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2848'
2020-12-22 10:32:17	The record with UID 'A202' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2830'
2020-12-22 10:32:17	The record with UID 'A199' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2814'
2020-12-22 10:32:17	The record with UID 'A207' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2779'
2020-12-22 10:32:17	The record with UID 'A206' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2767'
2020-12-22 10:32:17	The record with UID 'A302' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2742'
2020-12-22 10:32:17	The record with UID 'A200' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2730'
2020-12-22 10:32:17	The record with UID 'A205' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2730'
2020-12-22 10:32:17	The record with UID 'A198' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2729'
2020-12-22 10:32:17	The record with UID 'A048' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '272'
2020-12-22 10:32:17	The record with UID 'A299' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2693'
2020-12-22 10:32:17	The record with UID 'A300' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2690'
2020-12-22 10:32:17	The record with UID 'A301' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2689'
2020-12-22 10:32:17	The record with UID 'A055' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2678'
2020-12-22 10:32:17	The record with UID 'A298' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2642'
2020-12-22 10:32:17	The record with UID 'A297' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2641'
2020-12-22 10:32:17	The record with UID 'A305' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2641'
2020-12-22 10:32:17	The record with UID 'A029' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2614'
2020-12-22 10:32:17	The record with UID 'A340' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2612'
2020-12-22 10:32:17	The record with UID 'A339' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2611'
2020-12-22 10:32:17	The record with UID 'A303' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2593'
2020-12-22 10:32:17	The record with UID 'A304' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2593'
2020-12-22 10:32:17	The record with UID 'A296' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2592'
2020-12-22 10:32:17	The record with UID 'A334' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2558'
2020-12-22 10:32:17	The record with UID 'A337' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2551'
2020-12-22 10:32:17	The record with UID 'A338' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2550'
2020-12-22 10:32:17	The record with UID 'A064' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2542'
2020-12-22 10:32:17	The record with UID 'A336' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2502'
2020-12-22 10:32:17	The record with UID 'A030' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2492'
2020-12-22 10:32:17	The record with UID 'A335' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2490'
2020-12-22 10:32:17	The record with UID 'A012' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2441'
2020-12-22 10:32:17	The record with UID 'A333' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2435'
2020-12-22 10:32:17	The record with UID 'A069' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2384'
2020-12-22 10:32:17	The record with UID 'A031' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2344'
2020-12-22 10:32:17	The record with UID 'A007' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2283'
2020-12-22 10:32:17	The record with UID 'A233' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2268'
2020-12-22 10:32:17	The record with UID 'A237' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2264'
2020-12-22 10:32:17	The record with UID 'A238' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2255'
2020-12-22 10:32:17	The record with UID 'A004' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2247'
2020-12-22 10:32:17	The record with UID 'A047' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '223'
2020-12-22 10:32:17	The record with UID 'A235' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2204'
2020-12-22 10:32:17	The record with UID 'A234' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2197'
2020-12-22 10:32:17	The record with UID 'A236' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2193'
2020-12-22 10:32:17	The record with UID 'A058' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2142'
2020-12-22 10:32:17	The record with UID 'A027' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2098'
2020-12-22 10:32:17	The record with UID 'A044' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2017'
2020-12-22 10:32:18	The record with UID 'A045' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2017'
2020-12-22 10:32:18	The record with UID 'A307' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '2006'
2020-12-22 10:32:18	The record with UID 'A108' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1994'
2020-12-22 10:32:18	The record with UID 'A110' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1992'
2020-12-22 10:32:18	The record with UID 'A036' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1959'
2020-12-22 10:32:18	The record with UID 'A309' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1958'
2020-12-22 10:32:18	The record with UID 'A107' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1933'
2020-12-22 10:32:18	The record with UID 'A112' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1932'
2020-12-22 10:32:18	The record with UID 'A113' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1931'
2020-12-22 10:32:18	The record with UID 'A111' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1930'
2020-12-22 10:32:18	The record with UID 'A311' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1900'
2020-12-22 10:32:18	The record with UID 'A041' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1858'
2020-12-22 10:32:18	The record with UID 'A310' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1853'
2020-12-22 10:32:18	The record with UID 'A125' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1835'
2020-12-22 10:32:18	The record with UID 'A033' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1813'
2020-12-22 10:32:18	The record with UID 'A308' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1811'
2020-12-22 10:32:18	The record with UID 'A121' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1767'
2020-12-22 10:32:18	The record with UID 'A017' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '175'
2020-12-22 10:32:18	The record with UID 'A065' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1741'
2020-12-22 10:32:18	The record with UID 'A122' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1730'
2020-12-22 10:32:18	The record with UID 'A272' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1716'
2020-12-22 10:32:18	The record with UID 'A273' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1713'
2020-12-22 10:32:18	The record with UID 'A275' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1709'
2020-12-22 10:32:18	The record with UID 'A274' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1708'
2020-12-22 10:32:18	The record with UID 'A022' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1696'
2020-12-22 10:32:18	The record with UID 'A123' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1691'
2020-12-22 10:32:18	The record with UID 'A140' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1687'
2020-12-22 10:32:18	The record with UID 'A142' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1687'
2020-12-22 10:32:18	The record with UID 'A271' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1671'
2020-12-22 10:32:18	The record with UID 'A280' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1668'
2020-12-22 10:32:18	The record with UID 'A276' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1650'
2020-12-22 10:32:18	The record with UID 'A124' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1646'
2020-12-22 10:32:18	The record with UID 'A141' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1646'
2020-12-22 10:32:18	The record with UID 'A139' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1638'
2020-12-22 10:32:18	The record with UID 'A138' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1607'
2020-12-22 10:32:18	The record with UID 'A283' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1597'
2020-12-22 10:32:18	The record with UID 'A278' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1596'
2020-12-22 10:32:18	The record with UID 'A049' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1561'
2020-12-22 10:32:18	The record with UID 'A281' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1543'
2020-12-22 10:32:18	The record with UID 'A284' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1543'
2020-12-22 10:32:18	The record with UID 'A279' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1541'
2020-12-22 10:32:18	The record with UID 'A021' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1517'
2020-12-22 10:32:18	The record with UID 'A270' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1498'
2020-12-22 10:32:18	The record with UID 'A282' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1492'
2020-12-22 10:32:18	The record with UID 'A285' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1490'
2020-12-22 10:32:18	The record with UID 'A277' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1447'
2020-12-22 10:32:18	The record with UID 'A269' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1445'
2020-12-22 10:32:18	The record with UID 'A011' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1418'
2020-12-22 10:32:18	The record with UID 'A265' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1345'
2020-12-22 10:32:18	The record with UID 'A267' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1345'
2020-12-22 10:32:18	The record with UID 'A062' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1330'
2020-12-22 10:32:18	The record with UID 'A266' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1286'
2020-12-22 10:32:18	The record with UID 'A268' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1286'
2020-12-22 10:32:18	The record with UID 'A010' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1279'
2020-12-22 10:32:18	The record with UID 'A264' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1244'
2020-12-22 10:32:18	The record with UID 'A061' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1193'
2020-12-22 10:32:18	The record with UID 'A019' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1143'
2020-12-22 10:32:18	The record with UID 'A008' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '114'
2020-12-22 10:32:18	The record with UID 'A328' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1061'
2020-12-22 10:32:18	The record with UID 'A009' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1060'
2020-12-22 10:32:19	The record with UID 'A331' updated from 'Timebars'! Details: Field['Order'] :: '' ----> '1048'
2020-12-22 10:32:19	The record with UID 'A109' added as a new record!
2020-12-22 10:32:19	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-22 10:32:19	Merge Operation Finished!
2020-12-29 11:57:31	Merge Operation Started!
2020-12-29 11:57:31	The record with UID 'A008' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> 'NA'
2020-12-29 11:57:31	The record with UID 'A017' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:31	The record with UID 'A020' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:31	The record with UID 'A013' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A023' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A024' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A026' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A018' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A003' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> 'NA'
2020-12-29 11:57:32	The record with UID 'A009' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A019' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A010' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A011' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:32	The record with UID 'A021' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A022' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A033' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A036' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A027' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A004' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> 'NA'
2020-12-29 11:57:33	The record with UID 'A007' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> 'NA'
2020-12-29 11:57:33	The record with UID 'A031' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A012' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A030' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A029' updated from 'MetaData'! Details: Field['Phase'] :: '' ----> '1 Pre-execution (evaluation and selection)'
2020-12-29 11:57:33	The record with UID 'A109' added as a new record!
2020-12-29 11:57:33	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '' ----> '20-Jan-2021'
2020-12-29 11:57:33	Merge Operation Finished!
2020-12-31 16:31:24	The CSV Imported Successfully to Timebars
2020-12-31 16:31:46	The CSV Imported Successfully to MetaData
2020-12-31 16:32:15	Merge Operation Started!
2020-12-31 16:32:16	The record with UID 'A002' updated from 'Timebars'! Details: Field['Finish'] :: '10-May-2022' ----> '09-May-2022'
2020-12-31 16:32:16	The record with UID 'A008' updated from 'Timebars'! Details: Field['Finish'] :: '15-May-2021' ----> '14-May-2021'
2020-12-31 16:32:16	The record with UID 'A017' updated from 'Timebars'! Details: Field['Finish'] :: '08-Apr-2021' ----> '07-Apr-2021'
2020-12-31 16:32:16	The record with UID 'A047' updated from 'Timebars'! Details: Field['Finish'] :: '02-Apr-2021' ----> '08-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A048' updated from 'Timebars'! Details: Field['Finish'] :: '06-Apr-2021' ----> '10-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A136' updated from 'Timebars'! Details: Field['Finish'] :: '30-Mar-2021' ----> '03-Apr-2021'
2020-12-31 16:32:16	The record with UID 'A137' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '15-Feb-2021'
2020-12-31 16:32:16	The record with UID 'A020' updated from 'Timebars'! Details: Field['Finish'] :: '28-Feb-2021' ----> '23-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A135' updated from 'Timebars'! Details: Field['Finish'] :: '19-Feb-2021' ----> '23-Feb-2021'
2020-12-31 16:32:16	The record with UID 'A134' updated from 'Timebars'! Details: Field['Finish'] :: '22-Mar-2021' ----> '26-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A059' updated from 'Timebars'! Details: Field['Finish'] :: '26-Feb-2021' ----> '22-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A133' updated from 'Timebars'! Details: Field['Finish'] :: '08-Mar-2021' ----> '12-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A241' updated from 'Timebars'! Details: Field['Finish'] :: '03-Feb-2021' ----> '07-Feb-2021'
2020-12-31 16:32:16	The record with UID 'A013' updated from 'Timebars'! Details: Field['Finish'] :: '23-Apr-2021' ----> '03-May-2021'
2020-12-31 16:32:16	The record with UID 'A243' updated from 'Timebars'! Details: Field['Finish'] :: '18-Mar-2021' ----> '22-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A242' updated from 'Timebars'! Details: Field['Finish'] :: '01-Mar-2021' ----> '05-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A023' updated from 'Timebars'! Details: Field['Finish'] :: '28-Mar-2021' ----> '07-Apr-2021'
2020-12-31 16:32:16	The record with UID 'A244' updated from 'Timebars'! Details: Field['Finish'] :: '04-Feb-2021' ----> '08-Feb-2021'
2020-12-31 16:32:16	The record with UID 'A245' updated from 'Timebars'! Details: Field['Finish'] :: '26-Feb-2021' ----> '02-Mar-2021'
2020-12-31 16:32:16	The record with UID 'A054' updated from 'Timebars'! Details: Field['Finish'] :: '23-Mar-2021' ----> '02-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A246' updated from 'Timebars'! Details: Field['Finish'] :: '15-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A240' updated from 'Timebars'! Details: Field['Finish'] :: '13-Mar-2021' ----> '17-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A192' updated from 'Timebars'! Details: Field['Finish'] :: '16-Feb-2021' ----> '26-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A193' updated from 'Timebars'! Details: Field['Finish'] :: '23-Mar-2021' ----> '02-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A239' updated from 'Timebars'! Details: Field['Finish'] :: '22-Mar-2021' ----> '26-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A194' updated from 'Timebars'! Details: Field['Finish'] :: '01-Mar-2021' ----> '11-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A024' updated from 'Timebars'! Details: Field['Finish'] :: '09-Apr-2021' ----> '22-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A196' updated from 'Timebars'! Details: Field['Finish'] :: '03-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A046' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '24-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A191' updated from 'Timebars'! Details: Field['Finish'] :: '23-Mar-2021' ----> '02-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A197' updated from 'Timebars'! Details: Field['Finish'] :: '17-Feb-2021' ----> '27-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A126' updated from 'Timebars'! Details: Field['Finish'] :: '22-Jan-2021' ----> '04-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A128' updated from 'Timebars'! Details: Field['Finish'] :: '27-Feb-2021' ----> '12-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A127' updated from 'Timebars'! Details: Field['Finish'] :: '03-Feb-2021' ----> '16-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A026' updated from 'Timebars'! Details: Field['Finish'] :: '30-May-2021' ----> '31-May-2021'
2020-12-31 16:32:17	The record with UID 'A129' updated from 'Timebars'! Details: Field['Finish'] :: '02-Feb-2021' ----> '15-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A130' updated from 'Timebars'! Details: Field['Finish'] :: '23-Feb-2021' ----> '08-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A132' updated from 'Timebars'! Details: Field['Finish'] :: '02-Feb-2021' ----> '15-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A131' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '19-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A018' updated from 'Timebars'! Details: Field['Finish'] :: '21-Apr-2021' ----> '22-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A068' updated from 'Timebars'! Details: Field['Finish'] :: '18-Mar-2021' ----> '19-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A327' updated from 'Timebars'! Details: Field['Finish'] :: '01-Feb-2021' ----> '02-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A329' updated from 'Timebars'! Details: Field['Finish'] :: '15-Mar-2021' ----> '16-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A332' updated from 'Timebars'! Details: Field['Finish'] :: '06-Feb-2021' ----> '07-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A003' updated from 'Timebars'! Details: Field['Finish'] :: '17-Jul-2022' ----> '16-Jul-2022'
2020-12-31 16:32:17	The record with UID 'A330' updated from 'Timebars'! Details: Field['Finish'] :: '10-Mar-2021' ----> '11-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A331' updated from 'Timebars'! Details: Field['Finish'] :: '15-Feb-2021' ----> '16-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A009' updated from 'Timebars'! Details: Field['Finish'] :: '17-May-2021' ----> '13-May-2021'
2020-12-31 16:32:17	The record with UID 'A328' updated from 'Timebars'! Details: Field['Finish'] :: '16-Mar-2021' ----> '17-Mar-2021'
2020-12-31 16:32:17	The record with UID 'A019' updated from 'Timebars'! Details: Field['Finish'] :: '15-Feb-2021' ----> '13-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A061' updated from 'Timebars'! Details: Field['Finish'] :: '15-Feb-2021' ----> '13-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A264' updated from 'Timebars'! Details: Field['Finish'] :: '07-Feb-2021' ----> '05-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A010' updated from 'Timebars'! Details: Field['Finish'] :: '04-Apr-2021' ----> '05-Apr-2021'
2020-12-31 16:32:17	The record with UID 'A266' updated from 'Timebars'! Details: Field['Finish'] :: '14-Feb-2021' ----> '12-Feb-2021'
2020-12-31 16:32:17	The record with UID 'A268' updated from 'Timebars'! Details: Field['Finish'] :: '27-Jan-2021' ----> '25-Jan-2021'
2020-12-31 16:32:17	The record with UID 'A062' updated from 'Timebars'! Details: Field['Finish'] :: '04-Apr-2021' ----> '05-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A265' updated from 'Timebars'! Details: Field['Finish'] :: '12-Feb-2021' ----> '10-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A267' updated from 'Timebars'! Details: Field['Finish'] :: '27-Jan-2021' ----> '25-Jan-2021'
2020-12-31 16:32:18	The record with UID 'A011' updated from 'Timebars'! Details: Field['Finish'] :: '20-May-2021' ----> '11-May-2021'
2020-12-31 16:32:18	The record with UID 'A269' updated from 'Timebars'! Details: Field['Finish'] :: '16-Mar-2021' ----> '17-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A277' updated from 'Timebars'! Details: Field['Finish'] :: '03-Feb-2021' ----> '04-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A285' updated from 'Timebars'! Details: Field['Finish'] :: '01-Feb-2021' ----> '02-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A282' updated from 'Timebars'! Details: Field['Finish'] :: '24-Feb-2021' ----> '25-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A270' updated from 'Timebars'! Details: Field['Finish'] :: '02-Apr-2021' ----> '03-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A021' updated from 'Timebars'! Details: Field['Finish'] :: '13-Mar-2021' ----> '03-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A279' updated from 'Timebars'! Details: Field['Finish'] :: '26-Mar-2021' ----> '27-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A281' updated from 'Timebars'! Details: Field['Finish'] :: '01-Feb-2021' ----> '02-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A284' updated from 'Timebars'! Details: Field['Finish'] :: '16-Feb-2021' ----> '17-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A049' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '27-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A278' updated from 'Timebars'! Details: Field['Finish'] :: '31-Mar-2021' ----> '01-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A283' updated from 'Timebars'! Details: Field['Finish'] :: '18-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A138' updated from 'Timebars'! Details: Field['Finish'] :: '16-Feb-2021' ----> '04-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A139' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '22-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A124' updated from 'Timebars'! Details: Field['Finish'] :: '02-Sep-2020' ----> '30-Aug-2020'
2020-12-31 16:32:18	The record with UID 'A141' updated from 'Timebars'! Details: Field['Finish'] :: '07-Feb-2021' ----> '26-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A276' updated from 'Timebars'! Details: Field['Finish'] :: '30-Jan-2021' ----> '31-Jan-2021'
2020-12-31 16:32:18	The record with UID 'A280' updated from 'Timebars'! Details: Field['Finish'] :: '27-Feb-2021' ----> '28-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A271' updated from 'Timebars'! Details: Field['Finish'] :: '30-Mar-2021' ----> '31-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A140' updated from 'Timebars'! Details: Field['Finish'] :: '01-Mar-2021' ----> '17-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A142' updated from 'Timebars'! Details: Field['Finish'] :: '06-Feb-2021' ----> '25-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A123' updated from 'Timebars'! Details: Field['Finish'] :: '03-Sep-2020' ----> '31-Aug-2020'
2020-12-31 16:32:18	The record with UID 'A022' updated from 'Timebars'! Details: Field['Finish'] :: '15-Mar-2021' ----> '05-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A274' updated from 'Timebars'! Details: Field['Finish'] :: '09-Feb-2021' ----> '10-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A275' updated from 'Timebars'! Details: Field['Finish'] :: '21-Jan-2021' ----> '22-Jan-2021'
2020-12-31 16:32:18	The record with UID 'A273' updated from 'Timebars'! Details: Field['Finish'] :: '04-Mar-2021' ----> '05-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A272' updated from 'Timebars'! Details: Field['Finish'] :: '02-Apr-2021' ----> '03-Apr-2021'
2020-12-31 16:32:18	The record with UID 'A122' updated from 'Timebars'! Details: Field['Finish'] :: '03-Sep-2020' ----> '31-Aug-2020'
2020-12-31 16:32:18	The record with UID 'A065' updated from 'Timebars'! Details: Field['Finish'] :: '15-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A121' updated from 'Timebars'! Details: Field['Finish'] :: '20-Sep-2020' ----> '17-Sep-2020'
2020-12-31 16:32:18	The record with UID 'A308' updated from 'Timebars'! Details: Field['Finish'] :: '15-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:18	The record with UID 'A033' updated from 'Timebars'! Details: Field['Finish'] :: '20-Mar-2021' ----> '22-May-2021'
2020-12-31 16:32:18	The record with UID 'A125' updated from 'Timebars'! Details: Field['Finish'] :: '19-Sep-2020' ----> '16-Sep-2020'
2020-12-31 16:32:18	The record with UID 'A310' updated from 'Timebars'! Details: Field['Finish'] :: '23-Feb-2021' ----> '21-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A041' updated from 'Timebars'! Details: Field['Finish'] :: '19-Mar-2021' ----> '21-May-2021'
2020-12-31 16:32:18	The record with UID 'A311' updated from 'Timebars'! Details: Field['Finish'] :: '25-Feb-2021' ----> '23-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A111' updated from 'Timebars'! Details: Field['Finish'] :: '02-Dec-2020' ----> '22-Feb-2021'
2020-12-31 16:32:18	The record with UID 'A113' updated from 'Timebars'! Details: Field['Finish'] :: '20-Dec-2020' ----> '12-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A112' updated from 'Timebars'! Details: Field['Finish'] :: '20-Jan-2021' ----> '12-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A107' updated from 'Timebars'! Details: Field['Finish'] :: '02-Dec-2020' ----> '22-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A309' updated from 'Timebars'! Details: Field['Finish'] :: '21-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A036' updated from 'Timebars'! Details: Field['Finish'] :: '28-Feb-2021' ----> '21-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A110' updated from 'Timebars'! Details: Field['Finish'] :: '29-Dec-2020' ----> '21-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A108' updated from 'Timebars'! Details: Field['Finish'] :: '16-Dec-2020' ----> '08-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A307' updated from 'Timebars'! Details: Field['Finish'] :: '10-Mar-2021' ----> '08-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A044' updated from 'Timebars'! Details: Field['Finish'] :: '02-Feb-2021' ----> '26-Jan-2021'
2020-12-31 16:32:19	The record with UID 'A045' updated from 'Timebars'! Details: Field['Finish'] :: '21-Feb-2021' ----> '14-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A027' updated from 'Timebars'! Details: Field['Finish'] :: '05-Apr-2021' ----> '31-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A058' updated from 'Timebars'! Details: Field['Order'] :: '2142' ----> '2629'
2020-12-31 16:32:19	The record with UID 'A236' updated from 'Timebars'! Details: Field['Order'] :: '2193' ----> '2680'
2020-12-31 16:32:19	The record with UID 'A234' updated from 'Timebars'! Details: Field['Order'] :: '2197' ----> '2684'
2020-12-31 16:32:19	The record with UID 'A235' updated from 'Timebars'! Details: Field['Order'] :: '2204' ----> '2691'
2020-12-31 16:32:19	The record with UID 'A004' updated from 'Timebars'! Details: Field['Finish'] :: '21-Apr-2021' ----> '24-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A238' updated from 'Timebars'! Details: Field['Order'] :: '2255' ----> '2742'
2020-12-31 16:32:19	The record with UID 'A237' updated from 'Timebars'! Details: Field['Order'] :: '2264' ----> '2751'
2020-12-31 16:32:19	The record with UID 'A233' updated from 'Timebars'! Details: Field['Order'] :: '2268' ----> '2755'
2020-12-31 16:32:19	The record with UID 'A007' updated from 'Timebars'! Details: Field['Finish'] :: '12-Mar-2021' ----> '17-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A031' updated from 'Timebars'! Details: Field['Finish'] :: '08-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A069' updated from 'Timebars'! Details: Field['Finish'] :: '08-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A333' updated from 'Timebars'! Details: Field['Finish'] :: '07-Mar-2021' ----> '12-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A012' updated from 'Timebars'! Details: Field['Finish'] :: '15-Apr-2021' ----> '18-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A335' updated from 'Timebars'! Details: Field['Finish'] :: '03-Mar-2021' ----> '08-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A030' updated from 'Timebars'! Details: Field['Finish'] :: '03-Apr-2021' ----> '06-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A336' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '05-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A064' updated from 'Timebars'! Details: Field['Finish'] :: '03-Apr-2021' ----> '06-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A338' updated from 'Timebars'! Details: Field['Finish'] :: '30-Jan-2021' ----> '04-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A337' updated from 'Timebars'! Details: Field['Finish'] :: '20-Feb-2021' ----> '25-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A334' updated from 'Timebars'! Details: Field['Finish'] :: '06-Mar-2021' ----> '11-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A296' updated from 'Timebars'! Details: Field['Finish'] :: '31-Mar-2021' ----> '03-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A303' updated from 'Timebars'! Details: Field['Finish'] :: '16-Mar-2021' ----> '19-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A304' updated from 'Timebars'! Details: Field['Finish'] :: '08-Feb-2021' ----> '11-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A339' updated from 'Timebars'! Details: Field['Finish'] :: '14-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A340' updated from 'Timebars'! Details: Field['Finish'] :: '26-Jan-2021' ----> '31-Jan-2021'
2020-12-31 16:32:19	The record with UID 'A029' updated from 'Timebars'! Details: Field['Finish'] :: '31-Mar-2021' ----> '08-Apr-2021'
2020-12-31 16:32:19	The record with UID 'A297' updated from 'Timebars'! Details: Field['Finish'] :: '19-Mar-2021' ----> '22-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A305' updated from 'Timebars'! Details: Field['Finish'] :: '04-Feb-2021' ----> '07-Feb-2021'
2020-12-31 16:32:19	The record with UID 'A298' updated from 'Timebars'! Details: Field['Finish'] :: '27-Feb-2021' ----> '02-Mar-2021'
2020-12-31 16:32:19	The record with UID 'A055' updated from 'Timebars'! Details: Field['Finish'] :: '30-Mar-2021' ----> '07-Apr-2021'
2020-12-31 16:32:20	The record with UID 'A301' updated from 'Timebars'! Details: Field['Finish'] :: '16-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A300' updated from 'Timebars'! Details: Field['Finish'] :: '31-Jan-2021' ----> '03-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A299' updated from 'Timebars'! Details: Field['Finish'] :: '11-Mar-2021' ----> '14-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A198' updated from 'Timebars'! Details: Field['Finish'] :: '05-Mar-2021' ----> '13-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A200' updated from 'Timebars'! Details: Field['Finish'] :: '29-Mar-2021' ----> '06-Apr-2021'
2020-12-31 16:32:20	The record with UID 'A205' updated from 'Timebars'! Details: Field['Finish'] :: '11-Feb-2021' ----> '19-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A302' updated from 'Timebars'! Details: Field['Finish'] :: '16-Mar-2021' ----> '19-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A206' updated from 'Timebars'! Details: Field['Finish'] :: '17-Feb-2021' ----> '25-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A207' updated from 'Timebars'! Details: Field['Finish'] :: '21-Mar-2021' ----> '29-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A199' updated from 'Timebars'! Details: Field['Finish'] :: '10-Feb-2021' ----> '18-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A202' updated from 'Timebars'! Details: Field['Finish'] :: '13-Mar-2021' ----> '21-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A204' updated from 'Timebars'! Details: Field['Finish'] :: '28-Jan-2021' ----> '05-Feb-2021'
2020-12-31 16:32:20	The record with UID 'A201' updated from 'Timebars'! Details: Field['Finish'] :: '26-Mar-2021' ----> '03-Apr-2021'
2020-12-31 16:32:20	The record with UID 'A203' updated from 'Timebars'! Details: Field['Finish'] :: '26-Feb-2021' ----> '06-Mar-2021'
2020-12-31 16:32:20	The record with UID 'A109' updated from 'Timebars'! Details: Field['Finish'] :: '20-Jan-2021' ----> '31-Mar-2021'
2020-12-31 16:32:20	Merge Operation Finished!
2021-01-10 15:04:51	The CSV Imported Successfully to Timebars
2021-01-10 15:05:09	The CSV Imported Successfully to MetaData
2021-01-10 15:29:44	The CSV Imported Successfully to Timebars
2021-01-11 15:35:41
2021-01-11 15:37:32	The CSV Imported Successfully to Timebars
2021-01-12 08:33:36	The CSV Imported Successfully to Timebars
2021-01-12 08:36:54	Merge Operation Started!
2021-01-12 08:36:54	The record with UID 'A002' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '80720'
2021-01-12 08:36:54	The record with UID 'A008' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '7920'
2021-01-12 08:36:54	The record with UID 'A017' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '5840'
2021-01-12 08:36:54	The record with UID 'A047' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:54	The record with UID 'A048' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '5840'
2021-01-12 08:36:54	The record with UID 'A136' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:54	The record with UID 'A137' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:54	The record with UID 'A020' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '2080'
2021-01-12 08:36:54	The record with UID 'A135' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2000'
2021-01-12 08:36:54	The record with UID 'A134' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1440'
2021-01-12 08:36:55	The record with UID 'A059' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2080'
2021-01-12 08:36:55	The record with UID 'A133' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2400'
2021-01-12 08:36:55	The record with UID 'A241' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A013' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '24120'
2021-01-12 08:36:55	The record with UID 'A243' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A242' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A023' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '12840'
2021-01-12 08:36:55	The record with UID 'A244' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A245' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2080'
2021-01-12 08:36:55	The record with UID 'A054' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '12840'
2021-01-12 08:36:55	The record with UID 'A246' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A240' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A192' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '3400'
2021-01-12 08:36:55	The record with UID 'A193' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2000'
2021-01-12 08:36:55	The record with UID 'A239' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A194' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2080'
2021-01-12 08:36:55	The record with UID 'A024' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '11280'
2021-01-12 08:36:55	The record with UID 'A196' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2240'
2021-01-12 08:36:55	The record with UID 'A046' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '11280'
2021-01-12 08:36:55	The record with UID 'A191' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1840'
2021-01-12 08:36:55	The record with UID 'A197' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1280'
2021-01-12 08:36:55	The record with UID 'A126' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '480'
2021-01-12 08:36:55	The record with UID 'A128' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A127' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A026' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:55	The record with UID 'A129' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '4800'
2021-01-12 08:36:55	The record with UID 'A130' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1200'
2021-01-12 08:36:55	The record with UID 'A132' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '960'
2021-01-12 08:36:55	The record with UID 'A131' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '3840'
2021-01-12 08:36:55	The record with UID 'A018' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:55	The record with UID 'A068' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:55	The record with UID 'A327' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1360'
2021-01-12 08:36:56	The record with UID 'A329' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A332' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1600'
2021-01-12 08:36:56	The record with UID 'A003' does not exist in 'Timebars' and 'MetaData'!
2021-01-12 08:36:56	The record with UID 'A330' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '3360'
2021-01-12 08:36:56	The record with UID 'A331' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1920'
2021-01-12 08:36:56	The record with UID 'A009' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '31360'
2021-01-12 08:36:56	The record with UID 'A328' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1600'
2021-01-12 08:36:56	The record with UID 'A019' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '5040'
2021-01-12 08:36:56	The record with UID 'A061' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '5040'
2021-01-12 08:36:56	The record with UID 'A264' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A010' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '26320'
2021-01-12 08:36:56	The record with UID 'A266' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1600'
2021-01-12 08:36:56	The record with UID 'A268' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1040'
2021-01-12 08:36:56	The record with UID 'A062' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '26320'
2021-01-12 08:36:56	The record with UID 'A265' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A267' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2400'
2021-01-12 08:36:56	The record with UID 'A011' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '0'
2021-01-12 08:36:56	The record with UID 'A269' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '4480'
2021-01-12 08:36:56	The record with UID 'A277' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2560'
2021-01-12 08:36:56	The record with UID 'A285' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1360'
2021-01-12 08:36:56	The record with UID 'A282' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1200'
2021-01-12 08:36:56	The record with UID 'A270' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '4000'
2021-01-12 08:36:56	The record with UID 'A021' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:56	The record with UID 'A279' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A281' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A284' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2080'
2021-01-12 08:36:56	The record with UID 'A049' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A278' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A283' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1280'
2021-01-12 08:36:56	The record with UID 'A138' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A139' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A124' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A141' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A276' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2880'
2021-01-12 08:36:56	The record with UID 'A280' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A271' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A140' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A142' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A123' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A022' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '0'
2021-01-12 08:36:56	The record with UID 'A274' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2400'
2021-01-12 08:36:56	The record with UID 'A275' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '880'
2021-01-12 08:36:56	The record with UID 'A273' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '3200'
2021-01-12 08:36:56	The record with UID 'A272' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A122' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A065' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A121' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A308' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A033' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:56	The record with UID 'A125' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A310' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:56	The record with UID 'A041' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A311' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A111' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A113' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A112' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A107' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A309' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A036' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '0'
2021-01-12 08:36:57	The record with UID 'A110' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A108' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A307' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A044' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A045' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A027' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '0'
2021-01-12 08:36:57	The record with UID 'A058' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A236' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '1600'
2021-01-12 08:36:57	The record with UID 'A234' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '960'
2021-01-12 08:36:57	The record with UID 'A235' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2240'
2021-01-12 08:36:57	The record with UID 'A004' does not exist in 'Timebars' and 'MetaData'!
2021-01-12 08:36:57	The record with UID 'A238' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A237' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A233' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '2800'
2021-01-12 08:36:57	The record with UID 'A007' updated from 'Timebars'! Details: Field['Cost'] :: 'Customer Support Department' ----> '61440'
2021-01-12 08:36:57	The record with UID 'A031' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '61440'
2021-01-12 08:36:57	The record with UID 'A069' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '61440'
2021-01-12 08:36:57	The record with UID 'A333' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A012' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:57	The record with UID 'A335' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A030' updated from 'Timebars'! Details: Field['Cost'] :: 'IT Department' ----> '0'
2021-01-12 08:36:57	The record with UID 'A336' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '21760'
2021-01-12 08:36:57	The record with UID 'A064' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A338' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '20480'
2021-01-12 08:36:57	The record with UID 'A337' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A334' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A296' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A303' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A304' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A339' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A340' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '19200'
2021-01-12 08:36:57	The record with UID 'A029' updated from 'Timebars'! Details: Field['Cost'] :: 'Presidents Office' ----> '0'
2021-01-12 08:36:57	The record with UID 'A297' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A305' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A298' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A055' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A301' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A300' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A299' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A198' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A200' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A205' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A302' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A206' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A207' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A199' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A202' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A204' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A201' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A203' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	The record with UID 'A109' updated from 'Timebars'! Details: Field['Cost'] :: '' ----> '0'
2021-01-12 08:36:57	Merge Operation Finished!
2021-01-12 08:37:24	Merge Operation Started!
2021-01-12 08:37:24	The record with UID 'A002' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '5997.9'
2021-01-12 08:37:25	The record with UID 'A008' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '405.6'
2021-01-12 08:37:25	The record with UID 'A017' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '106.8'
2021-01-12 08:37:25	The record with UID 'A047' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:25	The record with UID 'A048' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '106.8'
2021-01-12 08:37:25	The record with UID 'A136' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '28.2'
2021-01-12 08:37:25	The record with UID 'A137' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20.2'
2021-01-12 08:37:25	The record with UID 'A020' updated from 'Timebars'! Details: Field['Hours'] :: 'Accounting' ----> '298.8'
2021-01-12 08:37:25	The record with UID 'A135' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20'
2021-01-12 08:37:25	The record with UID 'A134' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '14.4'
2021-01-12 08:37:25	The record with UID 'A059' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '298.8'
2021-01-12 08:37:25	The record with UID 'A133' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '24'
2021-01-12 08:37:25	The record with UID 'A241' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '33.6'
2021-01-12 08:37:25	The record with UID 'A013' updated from 'Timebars'! Details: Field['Hours'] :: 'Finance' ----> '265.5'
2021-01-12 08:37:25	The record with UID 'A243' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '32'
2021-01-12 08:37:25	The record with UID 'A242' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '28.8'
2021-01-12 08:37:25	The record with UID 'A023' updated from 'Timebars'! Details: Field['Hours'] :: 'Product Engineering' ----> '128.4'
2021-01-12 08:37:25	The record with UID 'A244' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '19.2'
2021-01-12 08:37:25	The record with UID 'A245' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20.8'
2021-01-12 08:37:25	The record with UID 'A054' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '128.4'
2021-01-12 08:37:25	The record with UID 'A246' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '23.5'
2021-01-12 08:37:25	The record with UID 'A240' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '54.4'
2021-01-12 08:37:25	The record with UID 'A192' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '34'
2021-01-12 08:37:25	The record with UID 'A193' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20'
2021-01-12 08:37:25	The record with UID 'A239' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '86.5'
2021-01-12 08:37:25	The record with UID 'A194' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20.8'
2021-01-12 08:37:25	The record with UID 'A024' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '137.1'
2021-01-12 08:37:25	The record with UID 'A196' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '22.4'
2021-01-12 08:37:25	The record with UID 'A046' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '137.1'
2021-01-12 08:37:25	The record with UID 'A191' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '18.4'
2021-01-12 08:37:25	The record with UID 'A197' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '12.8'
2021-01-12 08:37:25	The record with UID 'A126' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '4.8'
2021-01-12 08:37:25	The record with UID 'A128' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '17.3'
2021-01-12 08:37:25	The record with UID 'A127' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '7'
2021-01-12 08:37:25	The record with UID 'A026' updated from 'Timebars'! Details: Field['Hours'] :: 'Product Engineering' ----> '89.6'
2021-01-12 08:37:25	The record with UID 'A129' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '48'
2021-01-12 08:37:25	The record with UID 'A130' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '12'
2021-01-12 08:37:25	The record with UID 'A132' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '9.6'
2021-01-12 08:37:25	The record with UID 'A131' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '38.4'
2021-01-12 08:37:26	The record with UID 'A018' updated from 'Timebars'! Details: Field['Hours'] :: 'Product Engineering' ----> '0'
2021-01-12 08:37:26	The record with UID 'A068' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A327' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '13.6'
2021-01-12 08:37:26	The record with UID 'A329' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '21.1'
2021-01-12 08:37:26	The record with UID 'A332' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '16'
2021-01-12 08:37:26	The record with UID 'A003' does not exist in 'Timebars' and 'MetaData'!
2021-01-12 08:37:26	The record with UID 'A330' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '33.6'
2021-01-12 08:37:26	The record with UID 'A331' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '19.2'
2021-01-12 08:37:26	The record with UID 'A009' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '562'
2021-01-12 08:37:26	The record with UID 'A328' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '16'
2021-01-12 08:37:26	The record with UID 'A019' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '102.2'
2021-01-12 08:37:26	The record with UID 'A061' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '102.2'
2021-01-12 08:37:26	The record with UID 'A264' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '35.2'
2021-01-12 08:37:26	The record with UID 'A010' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '459.8'
2021-01-12 08:37:26	The record with UID 'A266' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '16'
2021-01-12 08:37:26	The record with UID 'A268' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '10.4'
2021-01-12 08:37:26	The record with UID 'A062' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '459.8'
2021-01-12 08:37:26	The record with UID 'A265' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '16.6'
2021-01-12 08:37:26	The record with UID 'A267' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '24'
2021-01-12 08:37:26	The record with UID 'A011' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '4531.2'
2021-01-12 08:37:26	The record with UID 'A269' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '44.8'
2021-01-12 08:37:26	The record with UID 'A277' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '25.6'
2021-01-12 08:37:26	The record with UID 'A285' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '13.6'
2021-01-12 08:37:26	The record with UID 'A282' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '12'
2021-01-12 08:37:26	The record with UID 'A270' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '40'
2021-01-12 08:37:26	The record with UID 'A021' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '1126.4'
2021-01-12 08:37:26	The record with UID 'A279' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '42.2'
2021-01-12 08:37:26	The record with UID 'A281' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A284' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '20.8'
2021-01-12 08:37:26	The record with UID 'A049' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '1126.4'
2021-01-12 08:37:26	The record with UID 'A278' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '45.4'
2021-01-12 08:37:26	The record with UID 'A283' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '12.8'
2021-01-12 08:37:26	The record with UID 'A138' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A139' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A124' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A141' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '480'
2021-01-12 08:37:26	The record with UID 'A276' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '28.8'
2021-01-12 08:37:26	The record with UID 'A280' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '36.8'
2021-01-12 08:37:26	The record with UID 'A271' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '37'
2021-01-12 08:37:26	The record with UID 'A140' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '480'
2021-01-12 08:37:26	The record with UID 'A142' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '166.4'
2021-01-12 08:37:26	The record with UID 'A123' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A022' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '3404.8'
2021-01-12 08:37:26	The record with UID 'A274' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '24'
2021-01-12 08:37:26	The record with UID 'A275' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '8.8'
2021-01-12 08:37:26	The record with UID 'A273' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '32'
2021-01-12 08:37:26	The record with UID 'A272' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '35.2'
2021-01-12 08:37:26	The record with UID 'A122' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A065' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '3404.8'
2021-01-12 08:37:26	The record with UID 'A121' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A308' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '512'
2021-01-12 08:37:26	The record with UID 'A033' updated from 'Timebars'! Details: Field['Hours'] :: 'Product Engineering' ----> '60.8'
2021-01-12 08:37:26	The record with UID 'A125' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A310' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '320'
2021-01-12 08:37:26	The record with UID 'A041' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '28'
2021-01-12 08:37:26	The record with UID 'A311' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '332.8'
2021-01-12 08:37:26	The record with UID 'A111' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A113' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A112' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A107' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:26	The record with UID 'A309' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '320'
2021-01-12 08:37:27	The record with UID 'A036' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '0'
2021-01-12 08:37:27	The record with UID 'A110' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A108' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A307' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '1920'
2021-01-12 08:37:27	The record with UID 'A044' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A045' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A027' updated from 'Timebars'! Details: Field['Hours'] :: 'Information Technology' ----> '48'
2021-01-12 08:37:27	The record with UID 'A058' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '44'
2021-01-12 08:37:27	The record with UID 'A236' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '16'
2021-01-12 08:37:27	The record with UID 'A234' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '9.6'
2021-01-12 08:37:27	The record with UID 'A235' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '22.4'
2021-01-12 08:37:27	The record with UID 'A004' does not exist in 'Timebars' and 'MetaData'!
2021-01-12 08:37:27	The record with UID 'A238' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '14.1'
2021-01-12 08:37:27	The record with UID 'A237' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '23.5'
2021-01-12 08:37:27	The record with UID 'A233' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '28'
2021-01-12 08:37:27	The record with UID 'A007' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '1830.4'
2021-01-12 08:37:27	The record with UID 'A031' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '1830.4'
2021-01-12 08:37:27	The record with UID 'A069' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '1830.4'
2021-01-12 08:37:27	The record with UID 'A333' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A012' updated from 'Timebars'! Details: Field['Hours'] :: 'Finance' ----> '5766.4'
2021-01-12 08:37:27	The record with UID 'A335' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '268.8'
2021-01-12 08:37:27	The record with UID 'A030' updated from 'Timebars'! Details: Field['Hours'] :: 'Procurement' ----> '2585.6'
2021-01-12 08:37:27	The record with UID 'A336' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '217.6'
2021-01-12 08:37:27	The record with UID 'A064' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '2585.6'
2021-01-12 08:37:27	The record with UID 'A338' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '204.8'
2021-01-12 08:37:27	The record with UID 'A337' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '192'
2021-01-12 08:37:27	The record with UID 'A334' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '576'
2021-01-12 08:37:27	The record with UID 'A296' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '128'
2021-01-12 08:37:27	The record with UID 'A303' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '320'
2021-01-12 08:37:27	The record with UID 'A304' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '563.2'
2021-01-12 08:37:27	The record with UID 'A339' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '179.2'
2021-01-12 08:37:27	The record with UID 'A340' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '192'
2021-01-12 08:37:27	The record with UID 'A029' updated from 'Timebars'! Details: Field['Hours'] :: 'Accounting' ----> '3180.8'
2021-01-12 08:37:27	The record with UID 'A297' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '576'
2021-01-12 08:37:27	The record with UID 'A305' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A298' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '192'
2021-01-12 08:37:27	The record with UID 'A055' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '3180.8'
2021-01-12 08:37:27	The record with UID 'A301' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A300' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A299' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '192'
2021-01-12 08:37:27	The record with UID 'A198' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '384'
2021-01-12 08:37:27	The record with UID 'A200' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '217.6'
2021-01-12 08:37:27	The record with UID 'A205' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A302' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '614.4'
2021-01-12 08:37:27	The record with UID 'A206' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	The record with UID 'A207' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '640'
2021-01-12 08:37:27	The record with UID 'A199' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '268.8'
2021-01-12 08:37:27	The record with UID 'A202' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '256'
2021-01-12 08:37:27	The record with UID 'A204' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '358.4'
2021-01-12 08:37:27	The record with UID 'A201' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '544'
2021-01-12 08:37:27	The record with UID 'A203' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '512'
2021-01-12 08:37:27	The record with UID 'A109' updated from 'Timebars'! Details: Field['Hours'] :: '' ----> '0'
2021-01-12 08:37:27	Merge Operation Finished!
2021-01-12 08:40:13	The CSV Imported Successfully to MetaData
Clear Log!

## TEMP
tbMDID	tbMDGate	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDROMEstimate	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSize	tbMDStageApprover	tbMDWrittenBy	tbMDBusinessAdvisor	tbMDBusinessOwner	tbMDDeliveryManager	tbMDOrgManager	tbMDPriorityStrategic	tbMDSponsoringDepartment	tbMDPrimaryContact	tbMDBenefitCostRatio	tbMDContactNumber	tbMDResponsibleTeam	tbMDRiskVsSizeAndComplexity	tbMDEcnomicValueAdded	tbMDEstimationClass	tbMDInternalRateOfReturn	tbMDSprintName	tbMDSunkCosts	tbMDSyncNotes	tbMDNotesProject	tbMDContractNumber	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDPrimaryLineOfBusiness	tbMDBackgroundInfo	tbMDCapabilitiesNeeded	tbMDConsequence	tbMDExpectedBenfits	tbMDProblemOpportunity	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDExecutiveSummary	tbMDSeniorLevelCommittment	tbMDStakeholderDescription	tbMDNotesWorkflow	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	tbMDName	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDProjectNumber	tbMDDescription	tbMDNotes	tbMDExtLink1	tbMDExtSystemID1	tbMDSortOrder	tbMDtbLastModified	tbMDPriority	tbMDStatus	tbMDState	tbMDSeverity	tbMDStage	tbMDPhase	tbMDCategory	tbMDHealth	tbMDResponsibility	tbMDDepartment	tbMDExSponsor	tbMDPM	tbMDProjectType	tbMDShowIn	tbMDYesNoSelector	tbMDProduct	tbMDContact	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDPrimarySkill	tbMDPrimaryRole	tbMDOther2	tbMDOther3	tbMDOther4	canvasNo	tbMDRefID	id
A008	NA	Red	Green	Red	Green	Green	Red		Business Systems	Improve productivity	Transform	Increase share of market	501K to750K	R&D New Technology	NA		Large	Erica Stg Apvr	Joe Who	Joe Ba	Sam bo	Al dm	Kent Om	High			NA			Large		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Business Technology Solutions	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	A portfolio that will allow for the creation and deployment of the future-state systems. We continue to invent new products and technologies for our customers	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									R&D New Technology Portfolio	48	NA	NA	PF 05	This is my Brief Description	Enter project notes here	NA	NA	NA	NA	Critical	Active	Spawned	NA	NA	NA	NA	Red	Information Technology	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	Display URT	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	5		1
A009	3 Approved to Implement	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Source Cloud services for our Core products	Run	Improve and maintain workplace safety	251K to 500K	Business Support Systems	Centralized Billing and Receivables		Large	Erica Stg Apvr	Joe Who	Sally Ba	Julia bo	Jim Dm	Kent Om	High			NA			Large		Class C	NA	Not a Sprint	30k	NA			NA	NA	NA	Business Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Implement a broader rollout of Projx based on the outcomes/recommendations of the Phase 1 project pilot.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Billing Strategy and Policy Review	49	NA	NA	PJ 004	Review and report on findings	Enter project notes here	NA	NA	NA	NA	Low	Active	Spawned	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	Presidents Office	Colin Sp	Al PM		NA	NA	Display URT	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	6		2
A010	2 Approved to Develop	Yellow	Red	Yellow	Red	Red	Yellow		Office Environment	Improve productivity	Grow the Business	Best in market core products	101K to250K	Building Services	Building and Office Modernization		Large	Erica Stg Apvr	Joe Who	Joe Ba	Sam bo	Al dm	Kent Om	Medium			NA			Large		Class C	NA	Not a Sprint	30k	NA			NA	NA	NA	Business Technology Solutions	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	This program shall roll up all investments regarding our buildings and office space.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Building and Office Modernization Program	50	NA	NA	PG 001	This program shall roll up all investments regarding our buildings and office space.	Enter project notes here	NA	NA	NA	NA	Medium	Active	NA	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	SIT 5000	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	7		3
A011	2 Approved to Develop	Yellow	Red	Yellow	Red	Red	Yellow		Information Technology	Source Cloud services for our Core products	Run	Ensure compliance	750K Plus	R&D New Technology	Business Continuity Management Program		Small	Julia Stg Apvr	Jim Cox	Joe Ba	Sam bo	Al dm	Perry Om	Medium			NA			Medium		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Corporate Affairs	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	A group of projects that will enable an effective Business Continuity Management process that establishes and maintains continuity plans across all levels of the organization based on a prioritization of business objectives and critical business operations that are essential for recovery, following an incident or disruption.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Business Continuity Management Program	51	NA	NA	PG 016	This is my Brief Description	Enter project notes here	NA	NA	NA	NA	NA	Active	Approved	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Information Technology	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	SAP Financial System	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	8		4
A012	1 Approved to Design	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Support moden digital workplace	Run	Reduce waste	0 to 100K	Business Support Systems	Ticketing System and Requirements Management		Small	Julia Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Al dm	Perry Om	High			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Research and Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	This represents a funding envelope that will allow for changes to the environment that are not yet understood.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Upgrade Ticketing System	52	NA	NA	PJ 024	Enabling an employee experience that is simple, relevant and caring.	Enter project notes here	NA	NA	NA	NA	High	Active	Approved	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Finance	IT Department	Marsha Sp	PM011		NA	NA	SAP Financial System	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	9		5
A013	2 Approved to Develop	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Faster response to new business opportunities	Run	Improve customer service	101K to250K	Business Support Systems	Centralized Billing and Receivables		Medium	Ben Stg Apvr	Jim Cox	Joe Ba	Sam bo	Al dm	Perry Om	Medium			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Research and Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Northern Wireless Inc. currently has distinct invoicing, receipt and collection processes for each separate product group. These processes have developed over time and are specific to individual products. The current disparate processes create a number of challenges as current processes do not reflect best practices and are not standardized. Invoices and payment terms vary with the product and invoicing and receipt functionality are embedded in legacy systems which limits Northern Wireless Inc. ability to respond to new products.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Centralized Billing and Receivables Program	53	NA	NA	PG 002	The objective of this initiative is to be able to apply life cycle management of unstructured content by providing an enterprise document and records management platform.	Enter project notes here	NA	NA	NA	NA	Medium	Active	Awaiting Review	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Finance	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	FAM 6000	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	10		6
A017	2 Approved to Develop	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Source Cloud services for our Core products	Run	Become more Agile, less process	750K Plus	Business Support Systems	IM Policy and Guidelines		Small	Julia Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	Low			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Business Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Moving our key propriatiary and other classified data to the Cloud must be done with systematic care. We must develop processes and procudures and training to ensure security of our IP data.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Classified data in Public Cloud	54	NA	NA	PJ 012	A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	Enter project notes here	NA	NA	NA	NA	NA	Cancelled	Approved	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	FAM 6000	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	11		7
A018	1 Approved to Design	Yellow	Red	Yellow	Red	Red	Yellow		Information Technology	Support moden digital workplace	Run	Attract and retain the best people	0 to 100K	R&D New Technology	Continuous Improvement Transformation		Medium	Ben Stg Apvr	Joe Who	Mike Ba	Joe Bo	Al dm	Kent Om	Low			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Engineering and Product Delivery	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	CI Transformation - Project	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Continuous Improvement Transformation Program	55	NA	NA	PG 017	This is my Brief Description	Enter project notes here	NA	NA	NA	NA	High	Active	Requested Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Product Engineering	IT Department	Marsha Sp	PM011		NA	NA	SIT 5000	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	12		8
A019	2 Approved to Develop	Yellow	Red	Yellow	Red	Red	Yellow		Building Services	Cross-sell our Network Device products	Grow	Increase revenue	251K to 500K	Core Product Delivery	Continuous Internal Delivery Enablement		Large	Erica Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	High			NA			Large		Class C	NA	Not a Sprint	30k	NA			NA	NA	NA	Business Technology Solutions	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives where resourcing to tactical projects within the portfolio, but are not accountable for project delivery.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Continuous Internal Delivery Enablement Program	57	NA	NA	PG 008	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Enter project notes here	NA	NA	NA	NA	Low	On-Hold	Awaiting Input	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Information Technology	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	FAM 6000	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	14		9
A020	3 Approved to Implement	Yellow	Red	Yellow	Red	Red	Yellow		Business Systems	Engineering Tool Innovation	Transform	Increase share of market	501K to750K	Core Product Delivery	Core Operations Program		Small	Julia Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Medium			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Corporate Affairs	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives related to planning, development and implementation of BlIN within Northern Wireless Inc.. Specifically, the program will have a focus on core technology projects to sustain and enhance service provision and compliance.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Core Operations Program	58	NA	NA	PG 009	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	Enter project notes here	NA	NA	NA	NA	Critical	On-Hold	Awaiting Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Accounting	Presidents Office	Colin Sp	Al PM		NA	NA	Display URT	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	15		10
A021	1 Approved to Design	Yellow	Red	Yellow	Red	Red	Yellow		Business Systems	Faster response to new business opportunities	Transform	Ensure compliance	750K Plus	Core Product Delivery	Core Operations Program		Medium	Ben Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Jim Dm	Perry Om	Medium			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Engineering and Product Delivery	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	No Consequence of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives related to planning, development and implementation of the Automate selection system. Specifically, the program will have a focus on achievement of strategic goals and efficiency gains.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Automate selection system	59	NA	NA	PJ 005	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here	NA	NA	NA	NA	NA	On-Hold	Awaiting Review	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	IT Department	Marsha Sp	PM011		NA	NA	SAP Financial System	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	16		11
A022	3 Approved to Implement	Yellow	Red	Yellow	Red	Red	Yellow		Information Technology	Source Cloud services for our Core products	Run	Attract and retain the best people	251K to 500K	Core Product Delivery	Market Information Management		Small	Julia Stg Apvr	Jim Cox	Sally Ba	Julia bo	Al dm	Perry Om	High			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Finance	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	No Consequence of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Modernize our data marts	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Database Upgrade Market Datamart	60	NA	NA	PJ 020	Study and make recommendations.	Enter project notes here	NA	NA	NA	NA	Low	Active	Approved	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	Presidents Office	Colin Sp	Al PM		NA	NA	SAP Financial System	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	17		12
A023	1 Approved to Design	Yellow	Red	Yellow	Red	Red	Yellow		Building Services	Faster response to new business opportunities	Grow	Attract and retain the best people	0 to 100K	IT Platform	Digital Workplace - Transformation		Small	Julia Stg Apvr	Joe Who	Mike Ba	Joe Bo	Jim Dm	Kent Om	Medium			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Business Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Providing accurate and timely reporting on Projects within the program, supporting the projects in key areas of program management, such as resource, risk, financial, outcomes management, etc.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Digital Workplace - Transformation Program	61	NA	NA	PG 012	Upgrade the collaboration sites in conjunction with business owners.	Enter project notes here	NA	NA	NA	NA	High	Active	Awaiting Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Product Engineering	IT Department	Marsha Sp	PM011		NA	NA	Display URT	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	18		13
A024	3 Approved to Implement	Yellow	Red	Yellow	Red	Red	Yellow		Business Support	Support moden digital workplace	Run	Server more customers	750K Plus	Business Support Systems	ERP Transformation		Medium	Ben Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Low			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Corporate Affairs	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	This program will establish standardized and modern procurement processes for all of Northern Wireless Inc. purchases using online supply chain and internal cost approval processes. We must ensure procurements align to budgets.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									ERP Procurement Module Renewal	62	NA	NA	PJ 009	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here	NA	NA	NA	NA	NA	Active	Requested Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Information Technology	Presidents Office	Colin Sp	Al PM		NA	NA	SIT 5000	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	19		14
A026																	Medium	Ben Stg Apvr	Joe Who	Mike Ba	Joe Bo	Al dm	Kent Om	Low			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Engineering and Product Delivery	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	CI Transformation - Project	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Continuous Improvement Transformation Program	55	NA	NA	PG 017	This is my Brief Description	Enter project notes here	NA	NA	NA	NA	High	Active	Requested Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Product Engineering	IT Department	Marsha Sp	PM011		NA	NA	SIT 5000	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	12		15
A027																	Large	Erica Stg Apvr	Jim Cox	Joe Ba	Sam bo	Jim Dm	Perry Om	High			NA			Large		Class C	NA	Not a Sprint	30k	NA			NA	NA	NA	Business Technology Solutions	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives where resourcing to tactical projects within the portfolio, but are not accountable for project delivery.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Continuous Internal Delivery Enablement Program	57	NA	NA	PG 008	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Enter project notes here	NA	NA	NA	NA	Low	On-Hold	Awaiting Input	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Information Technology	Customer Support Department	Sydney Sp	Jim Pm		NA	NA	FAM 6000	Sam Pc	NA	NA	NA	NA	NA	NA	NA	NA	14		16
A029																	Small	Julia Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Medium			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Corporate Affairs	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives related to planning, development and implementation of BlIN within Northern Wireless Inc.. Specifically, the program will have a focus on core technology projects to sustain and enhance service provision and compliance.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Core Operations Program	58	NA	NA	PG 009	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	Enter project notes here	NA	NA	NA	NA	Critical	On-Hold	Awaiting Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Accounting	Presidents Office	Colin Sp	Al PM		NA	NA	Display URT	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	15		17
A030																	Medium	Ben Stg Apvr	Jim Cox	Mike Ba	Joe Bo	Jim Dm	Perry Om	Medium			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Engineering and Product Delivery	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	No Consequence of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Projects and initiatives related to planning, development and implementation of the Automate selection system. Specifically, the program will have a focus on achievement of strategic goals and efficiency gains.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Automate selection system	59	NA	NA	PJ 005	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here	NA	NA	NA	NA	NA	On-Hold	Awaiting Review	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	IT Department	Marsha Sp	PM011		NA	NA	SAP Financial System	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	16		18
A031																	Small	Julia Stg Apvr	Jim Cox	Sally Ba	Julia bo	Al dm	Perry Om	High			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Finance	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	No Consequence of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Modernize our data marts	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Database Upgrade Market Datamart	60	NA	NA	PJ 020	Study and make recommendations.	Enter project notes here	NA	NA	NA	NA	Low	Active	Approved	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Procurement	Presidents Office	Colin Sp	Al PM		NA	NA	SAP Financial System	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	17		19
A033																	Small	Julia Stg Apvr	Joe Who	Mike Ba	Joe Bo	Jim Dm	Kent Om	Medium			NA			Medium		Class C	NA	Not a Sprint	50k	NA			NA	NA	NA	Business Development	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	Providing accurate and timely reporting on Projects within the program, supporting the projects in key areas of program management, such as resource, risk, financial, outcomes management, etc.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									Digital Workplace - Transformation Program	61	NA	NA	PG 012	Upgrade the collaboration sites in conjunction with business owners.	Enter project notes here	NA	NA	NA	NA	High	Active	Awaiting Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Product Engineering	IT Department	Marsha Sp	PM011		NA	NA	Display URT	Ben Pc	NA	NA	NA	NA	NA	NA	NA	NA	18		20
A036																	Medium	Ben Stg Apvr	Joe Who	Sally Ba	Julia bo	Al dm	Kent Om	Low			NA			Small		Class C	NA	Not a Sprint	130k	NA			NA	NA	NA	Corporate Affairs	See corporate portal http://xyz.com/zzz	The org needs x y and z Required Capabilities	Major Consequences of Inaction	There are not measurable Expected Benefits and Outcomes	We are proposing this project to solve problem x and y		Describe the cost vs benefits	This program will establish standardized and modern procurement processes for all of Northern Wireless Inc. purchases using online supply chain and internal cost approval processes. We must ensure procurements align to budgets.	No Senior Level Commitment, yet we hope this proposal meets expectations for selection	My Stakeholder Description is unknown.	Enter Wf Notes here									ERP Procurement Module Renewal	62	NA	NA	PJ 009	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Enter project notes here	NA	NA	NA	NA	NA	Active	Requested Approval	NA	1 Proposed	1 Pre-execution (evaluation and selection)	Cat 1	Yellow	Information Technology	Presidents Office	Colin Sp	Al PM		NA	NA	SIT 5000	Dave Pc	NA	NA	NA	NA	NA	NA	NA	NA	19		21