## Portfolio
Custom Report			Add desired columns first, then cliick “Run Report” to merge Timebars sheet data MetaData sheet data into this sheet. When a column name in this sheet matches a column name in Timebars or MetaData sheets, data will import and overwrite existing data.					Audit
UID	Parent	Hierarchy Order	Name	Type	Description	Executive Summary	Work Hours	Cost	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Priority Strategic	PPM Yes No Selected	PPM Select Score	PPM Selection Notes	ROM Estimate	Estimation Class	Decision Notes					Updated From Which Sheet	When last updated
A002		01.00.00.00.00	Business Systems Portfolio	Portfolio			55480	5548000					101K to250K	Class C	Decision notes					Timebars	2024-12-30 15:38:32
A008	A002	01.01.00.00.00	Centralized Billing and Receivables	Project	This is my Brief Description	The <strong>Centralized Billing and Receivables</strong> project represents a critical step forward in modernizing our financial infrastructure. By investing in this initiative, the company will achieve greater operational efficiency, cost savings, and improved customer relationships, positioning us for sustainable growth.	6040	604000	Business Systems	Strengthen Cybersecurity Infrastructure	Grow the Business	Attract and retain the best people					750K Plus	Class A	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 100.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16114	A008	01.01.01.00.00	Task for: Centralized Billing and Receivables	Task			6040	604000					Decision notes					Timebars	2024-12-30 15:38:32
16156	16114	01.01.01.01.00	General	Allocation			6040	604000					Decision notes					Timebars	2024-12-30 15:38:32
A011	A002	01.02.00.00.00	Core Operations Program	Project	This is my Brief Description	The <strong>Core Operations Program</strong> is a strategic initiative designed to enhance the efficiency, reliability, and scalability of our organization’s core operations. This program focuses on optimizing workflows, integrating advanced technologies, and standardizing processes across departments to support the growing demands of our business. By addressing operational bottlenecks and improving resource utilization, the program aims to drive sustained performance improvements and reduce operational risks.	6080	608000	Digital Transformation	Improve product reliability	Run the Business	Improve customer service					750K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve customer service): 60.00,Project Score: 51.25					MetaData - Timebars	2024-12-30 15:38:32
16117	A011	01.02.01.00.00	Task for: Core Operations Program	Task			6080	608000					Decision notes					MetaData - Timebars	2024-12-30 15:38:32
16159	16117	01.02.01.01.00	General	Allocation			6080	608000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A023	A002	01.03.00.00.00	HR Policy Update	Project	Upgrade the collaboration sites in conjunction with business owners.	Upgrade the collaboration sites in conjunction with business owners.	2200	220000	Business Systems	Faster response to new business opportunities	Run the Business	Attract and retain the best people					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 87.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16126	A023	01.03.01.00.00	Task for: HR Policy Update	Task			2200	220000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16168	16126	01.03.01.01.00	General	Allocation			2200	220000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A024	A002	01.04.00.00.00	HR SAP Envisioning	Project	<p>The <strong>HR SAP Envisioning</strong> project is a strategic initiative to explore the implementation of SAP solutions for modernizing and centralizing the company's HR functions. This project focuses on identifying business requirements, assessing current gaps, and envisioning a scalable HR system that supports workforce management, payroll, talent acquisition, and employee engagement. The initiative will provide a roadmap for leveraging SAP technology to streamline HR processes, improve data accuracy, and enhance the overall employee experience.</p><p></p>	The <strong>HR SAP Envisioning</strong> project aims to redefine the company’s HR capabilities by exploring the potential of SAP solutions to centralize and optimize workforce management. This initiative will deliver a comprehensive assessment of current HR challenges and propose a future-ready SAP system tailored to our needs. By focusing on process standardization and advanced analytics, this project will lay the foundation for an efficient, compliant, and employee-centric HR ecosystem, driving productivity and supporting the company’s growth objectives.	2480	248000	Business Systems	Improve employee skills	Transform the Business	Improve our core products					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 69.38DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 70, Decision: Review |					MetaData - Timebars	2024-12-30 15:38:32
16127	A024	01.04.01.00.00	Task for: HR SAP Envisioning	Task			2480	248000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16169	16127	01.04.01.01.00	General	Allocation			2480	248000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A026	A002	01.05.00.00.00	IM Policy and Guidelines	Project	The <strong>IM Policy and Guidelines</strong> project is focused on developing comprehensive policies and guidelines for Information Management (IM) across the organization. This initiative aims to establish clear standards and protocols for data handling, storage, access, and security. By aligning IM practices with industry standards and regulatory requirements, the project seeks to enhance data integrity, minimize risks, and support informed decision-making.	The <strong>IM Policy and Guidelines</strong> project will create a robust framework to govern the company’s Information Management practices. This initiative addresses the need for consistent and secure data handling protocols to support operational efficiency and regulatory compliance. By defining clear guidelines and policies, the project will mitigate risks related to data breaches, improve access controls, and ensure that information assets are managed effectively, providing a strong foundation for the organization’s digital transformation and growth.	5320	532000	Innovation	Improve employee skills	Grow the Business	Accelerate Time-to-Market					251K to 500K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 68.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 0, Work Avg Score: 100,Final Score: 75, Decision: Review |					MetaData - Timebars	2024-12-30 15:38:32
16128	A026	01.05.01.00.00	Task for: IM Policy and Guidelines	Task			5320	532000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16170	16128	01.05.01.01.00	General	Allocation			5320	532000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A033	A002	01.06.00.00.00	TBS Compliance	Project	The <strong>TBS Compliance</strong> project is focused on ensuring adherence to the Treasury Board Secretariat (TBS) standards and regulatory requirements. This initiative involves reviewing, updating, and aligning organizational policies, processes, and systems to meet compliance obligations. By embedding TBS guidelines into operations, the project aims to reduce compliance risks and enhance accountability and transparency across the organization.	The <strong>TBS Compliance</strong> project addresses the critical need to align the company’s operations with Treasury Board Secretariat standards. This initiative will assess current practices, identify gaps, and implement measures to achieve full compliance. By doing so, the project will mitigate regulatory risks, strengthen governance, and position the organization as a trusted and compliant entity, ensuring sustainable operations and fostering stakeholder confidence.	4680	468000	Digital Transformation	Faster response to new business opportunities	Run the Business	Ensure compliance					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 62.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16133	A033	01.06.01.00.00	Task for: TBS Compliance	Task			4680	468000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16175	16133	01.06.01.01.00	General	Allocation			4680	468000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
BS-2024-003	A002	01.07.00.00.00	Knowledge Management System	Project	Centralized platform for managing technical documentation, training materials, and best practices.	Implement a modern knowledge management system that improves information sharing and reduces support costs through better documentation and training resources.	2320	232000	Business Systems	Strengthen Cybersecurity Infrastructure	Grow the Business	Accelerate Time-to-Market					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 92.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 58, State null,Financial Metrics: 0. |					MetaData - Timebars	2024-12-30 15:38:33
16137	BS-2024-003	01.07.01.00.00	Task for: Knowledge Management System	Task			2320	232000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16179	16137	01.07.01.01.00	General	Allocation			2320	232000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A020	A002	01.08.00.00.00	ERP Procurement Module Renewal	Project	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	3400	340000	Digital Transformation	Build AI/ML Capabilities	Run the Business	Ensure compliance					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 65.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16123	A020	01.08.01.00.00	Task for: ERP Procurement Module Renewal	Task			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16165	16123	01.08.01.01.00	General	Allocation			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
BS-2024-002	A002	01.09.00.00.00	Supply Chain Optimization System	Project	AI-driven system for managing component inventory, supplier relationships, and production planning.	Develop an intelligent supply chain management system that improves efficiency, reduces costs, and ensures component availability. System will provide predictive analytics for demand forecasting and inventory optimization.	4600	460000	Business Systems	Build AI/ML Capabilities	Run the Business	Ensure compliance					0 to 100K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 85.63DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 55, State Warning! Awaiting Approval,Financial Metrics: 0. |					MetaData - Timebars	2024-12-30 15:38:34
16136	BS-2024-002	01.09.01.00.00	Task for: Supply Chain Optimization System	Task			4600	460000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16178	16136	01.09.01.01.00	General	Allocation			4600	460000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
BS-2024-004	A002	01.10.00.00.00	Project Portfolio Management Platform	Project	Integrated system for managing product development projects, resources, and portfolio analytics.	Deploy a comprehensive project management solution that improves visibility into product development efforts and enables better resource allocation and decision-making.	6040	604000	Business Systems	Faster response to new business opportunities	Run the Business	Ensure compliance					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 82.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 0,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 54, State null,Financial Metrics: 0. |					MetaData - Timebars	2024-12-30 15:38:34
16138	BS-2024-004	01.10.01.00.00	Task for: Project Portfolio Management Platform	Task			6040	604000					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
16180	16138	01.10.01.01.00	General	Allocation			6040	604000					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
A013	A002	01.11.00.00.00	HR Service Delivery	Project	The objective of this initiative is to be able to apply life cycle management of unstructured content by providing an enterprise document and records management platform.	The objective of this initiative is to be able to apply life cycle management of unstructured content by providing an enterprise document and records management platform.	5520	552000	Business Systems	Build AI/ML Capabilities	Run the Business	Improve our core products					101K to250K	Class B	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 88.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 4, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 59, Decision: Consider Terminating |					MetaData - Timebars	2024-12-30 15:38:32
16119	A013	01.11.01.00.00	Task for: HR Service Delivery	Task			5520	552000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16161	16119	01.11.01.01.00	General	Allocation			5520	552000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A017	A002	01.12.00.00.00	Billing Strategy and Policy Review	Project	A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	3400	340000	Innovation	Strengthen Cybersecurity Infrastructure	Run the Business	Drive Contract Renewals					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 58.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 93, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16120	A017	01.12.01.00.00	Task for: Billing Strategy and Policy Review	Task			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16162	16120	01.12.01.01.00	General	Allocation			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A027	A002	01.13.00.00.00	Internal IM Policy Modernization	Project	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	3400	340000	Innovation	Strengthen Cybersecurity Infrastructure	Grow the Business	Accelerate Time-to-Market					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 77.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16129	A027	01.13.01.00.00	Task for: Internal IM Policy Modernization	Task			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
16171	16129	01.13.01.01.00	General	Allocation			3400	340000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A0021		02.00.00.00.00	Digital Transformation Portfolio	Portfolio			499.4	24968.8					Decision notes					MetaData - Timebars	2024-12-24 13:13:18
A007	A0021	02.01.00.00.00	Business Continuity Management	Project	The <strong>Business Continuity Management</strong> project focuses on developing and implementing a comprehensive framework to ensure the organization can maintain critical operations during disruptions. This initiative includes risk assessments, contingency planning, and the establishment of response and recovery protocols. By prioritizing resilience and preparedness, the project aims to minimize downtime and protect organizational assets in the face of unforeseen events.	The <strong>Business Continuity Management</strong> project is a strategic initiative to safeguard the organization against operational disruptions. By creating a robust framework that includes risk analysis, contingency plans, and recovery strategies, this project ensures the company’s ability to continue delivering critical services during crises. This proactive approach not only mitigates risks but also enhances stakeholder trust, operational stability, and long-term resilience, ensuring the company is prepared for any eventuality.	0	0	Our Core Products	Source Cloud services for our Core products	Transform the Business	Increase share of market					101K to250K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 42.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 46, State Warning! Awaiting Input,Financial Metrics: 0. |					MetaData - Timebars	2024-12-30 15:38:32
16113	A007	02.01.01.00.00	Task for: Business Continuity Management	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16155	16113	02.01.01.01.00	General	Allocation			6560	656000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A019	A0021	02.02.00.00.00	Database Upgrade Market Datamart	Project	The <strong>Database Upgrade Market Datamart</strong> project is aimed at upgrading the current database infrastructure supporting the Market Datamart. This initiative focuses on enhancing performance, scalability, and security to meet growing business demands and support advanced analytics capabilities. The project will involve migrating to a more robust database platform, optimizing data storage, and ensuring seamless integration with existing systems.	The <strong>Database Upgrade Market Datamart</strong> project is a critical upgrade initiative to modernize the data infrastructure powering the Market Datamart. By enhancing database performance, scalability, and security, this project will enable faster data processing, improved analytics, and support for future business growth. This upgrade ensures that the organization remains competitive in managing and leveraging market data efficiently while reducing operational risks and ensuring compliance with data governance standards.	0	0	Business Systems	Improve product reliability	Grow the Business	Build Recurring Revenue Streams					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue |					MetaData - Timebars	2024-12-30 15:38:32
16122	A019	02.02.01.00.00	Task for: Database Upgrade Market Datamart	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16164	16122	02.02.01.01.00	General	Allocation			3480	348000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A009	A0021	02.03.00.00.00	Continuous Improvement Transformation	Project	The <strong>Continuous Improvement Transformation</strong> project focuses on fostering a culture of ongoing enhancement in processes, workflows, and systems across the organization. This initiative seeks to identify inefficiencies, implement agile practices, and leverage technology to drive operational excellence and innovation.	The <strong>Continuous Improvement Transformation</strong> and <strong>Digital Desktop Transformation</strong> projects are interrelated initiatives aimed at driving operational excellence and employee productivity. Continuous Improvement lays the foundation by streamlining workflows and promoting agility, while Digital Desktop Transformation equips employees with modern tools and a seamless digital workspace to execute these enhanced processes effectively. Together, these projects create a synergy that empowers the workforce, optimizes resource utilization, and positions the organization for sustained innovation and growth.	378.8	37875	Business Systems	Improve productivity with Agile Teams	Modernize the Business	Build Recurring Revenue Streams					0 to 100K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 59.38DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 75, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 46, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:32
16115	A009	02.03.01.00.00	Task for: Continuous Improvement Transformation	Task			378.8	37875					Decision notes					MetaData	2024-12-30 15:38:32
16157	16115	02.03.01.01.00	General	Allocation			3825	382500					Decision notes					MetaData - Timebars	2024-12-30 15:38:32
A012	A0021	02.04.00.00.00	Digital Desktop - Transformation	Project	The <strong>Digital Desktop Transformation</strong> project is closely aligned, emphasizing the modernization of employee workstations through digital tools, cloud integration, and streamlined user interfaces. This initiative is designed to enhance productivity, collaboration, and user experience by providing a cohesive and efficient digital workspace.	Enabling an employee experience that is simple, relevant and caring.	487.5	48750	Digital Transformation	Faster response to new business opportunities	Modernize the Business	Build Recurring Revenue Streams					0 to 100K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 48.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 50, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 50, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:32
16118	A012	02.04.01.00.00	Task for: Digital Workplace - Transformation	Task			487.5	48750					Decision notes					MetaData	2024-12-30 15:38:33
16160	16118	02.04.01.01.00	General	Allocation			3750	375000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
BS-2024-001	A0021	02.05.00.00.00	Customer Experience Platform	Project	Integrated platform for managing customer relationships, support tickets, and product deployment tracking.	Implement a modern CRM system tailored to our industry, improving customer satisfaction through better service delivery and proactive support. System will integrate with existing tools and provide comprehensive analytics.	159.4	15937.5	Business Systems	Strengthen Cybersecurity Infrastructure	Run the Business	Drive Contract Renewals					1000K Plus	Class B	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 73.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 75,Final Score: 50, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16135	BS-2024-001	02.05.01.00.00	Task for: Customer Experience Platform	Task			159.4	15937.5					Decision notes					MetaData	2024-12-30 15:38:33
16177	16135	02.05.01.01.00	General	Allocation			3187.5	318750					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A010	A0021	02.06.00.00.00	Constant Internal Delivery Enablement	Project	The <strong>Constant Internal Delivery Enablement</strong> project aims to enhance the organization’s ability to deliver internal initiatives effectively and consistently. This initiative focuses on standardizing delivery processes, improving resource allocation, and leveraging tools and methodologies to enable teams to execute internal projects with greater efficiency and quality.	The <strong>Constant Internal Delivery Enablement</strong> project is designed to streamline the execution of internal initiatives by building a robust framework for delivery excellence. By standardizing processes, optimizing resource utilization, and adopting proven methodologies, this project will ensure timely and high-quality outcomes for internal projects. This initiative not only improves operational efficiency but also fosters a culture of continuous improvement, enabling the organization to respond quickly and effectively to internal needs and strategic objectives.	1830.4	26320	Productivity Tools	Improve employee skills	Grow the Business	Reduce waste					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Reduce waste): 30.00,Project Score: 63.13					MetaData	2024-12-30 15:38:32
16116	A010	02.06.01.00.00	Task for: Constant Internal Delivery Enablement	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16158	16116	02.06.01.01.00	General	Allocation			4987.5	498750					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A018	A0021	02.07.00.00.00	Classified data in Public Cloud	Project	The <strong>Classified Data in Public Cloud</strong> project focuses on establishing a secure and compliant framework for managing classified data in public cloud environments. This initiative involves implementing advanced encryption, access controls, and monitoring systems to ensure the confidentiality, integrity, and availability of sensitive information. It also aims to align with regulatory standards and industry best practices to mitigate risks associated with data breaches and unauthorized access.	The <strong>Classified Data in Public Cloud</strong> project addresses the critical need to securely manage sensitive information in public cloud infrastructures. By implementing robust security measures such as encryption, identity management, and continuous monitoring, this initiative ensures compliance with regulatory requirements while leveraging the scalability and efficiency of cloud technology. The project supports the organization’s digital transformation goals, enabling secure data handling and fostering stakeholder confidence in the protection of classified information.	562	31360	Productivity Tools	Strengthen Cybersecurity Infrastructure	Transform the Business	Ensure compliance					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |					MetaData	2024-12-30 15:38:32
16121	A018	02.07.01.00.00	Task for: Classified data in Public Cloud	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16163	16121	02.07.01.01.00	General	Allocation			4050	405000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A031	A0021	02.08.00.00.00	SAP Platform Upgrade	Project	The <strong>SAP Platform Upgrade</strong> project focuses on modernizing the organization’s existing SAP infrastructure to support advanced capabilities, improve system performance, and align with evolving business needs. This initiative involves upgrading to the latest SAP version, enhancing integration with other SAP projects, and ensuring a seamless transition for all users while maintaining business continuity.	The <strong>SAP Platform Upgrade</strong> is a critical initiative that underpins the success of related SAP projects, such as <strong>HR SAP Envisioning</strong>. By upgrading the core SAP platform, this project provides the robust infrastructure needed to support new modules, enhance system integration, and deliver improved functionality across departments. This initiative ensures the organization can fully leverage SAP’s advanced features, streamline operations, and enable digital transformation, creating a cohesive ecosystem for projects that rely on SAP capabilities. Together, these efforts align to achieve a unified and efficient enterprise system.	1830.4	24968.8	Digital Transformation	Support moden digital workplace	Grow the Business	Server more customers					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |					MetaData	2024-12-30 15:38:32
16132	A031	02.08.01.00.00	Task for: SAP Platform Upgrade	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16174	16132	02.08.01.01.00	General	Allocation			4500	450000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A036	A0021	02.09.00.00.00	Upgrade Ticketing System	Project	The <strong>Upgrade Ticketing System</strong> project is focused on modernizing the organization’s existing ticketing platform to improve issue tracking, resolution efficiency, and user experience. This initiative includes upgrading to a more scalable and feature-rich system, integrating advanced analytics, and enhancing automation capabilities to streamline workflows and improve service delivery.	The <strong>Upgrade Ticketing System</strong> project aims to enhance the organization’s issue management and resolution processes by implementing a modern, scalable ticketing platform. This upgrade will address current system limitations, improve user experience, and introduce automation and analytics for better decision-making. By streamlining workflows and increasing efficiency, this project supports the company’s commitment to delivering high-quality services and maintaining operational excellence.	5766.4	24968.8	Our Core Products	Improve product reliability	Transform the Business	Increase share of market					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review |					MetaData	2024-12-30 15:38:32
16134	A036	02.09.01.00.00	Task for: Upgrade Ticketing System	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16176	16134	02.09.01.01.00	General	Allocation			2175	217500					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A030	A0021	02.10.00.00.00	Public Cloud Phase 1	Project	The <strong>Public Cloud Phase 1</strong> project marks the initial step in the organization’s strategic transition to leveraging public cloud infrastructure. This phase focuses on migrating non-critical workloads, establishing foundational security protocols, and configuring essential cloud services to support scalability and flexibility. It will serve as the groundwork for future cloud adoption initiatives.	The <strong>Public Cloud Phase 1</strong> project is a foundational initiative aimed at enabling the organization to begin its transition to public cloud environments. By migrating select workloads, establishing robust security measures, and configuring core cloud services, this phase ensures a secure and controlled introduction to cloud technology. This project sets the stage for scalability, cost optimization, and enhanced operational agility, providing the organization with the tools needed to adapt to evolving business needs and technology trends.	2585.6	16031.3	Our Core Products	Build AI/ML Capabilities	Transform the Business	Server more customers					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue |					MetaData	2024-12-30 15:38:32
16131	A030	02.10.01.00.00	Task for: Public Cloud Phase 1	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16173	16131	02.10.01.01.00	General	Allocation			3712.5	371250					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
BS-2024-005	A0021	02.11.00.00.00	Sales Enablement Platform	Project	Digital platform for managing sales content, product configurations, and quote generation.	Implement a comprehensive sales enablement system that streamlines the sales process through better content management, automated configuration tools, and integrated quote generation.	1830.4	31360	Business Systems	Improve productivity with Agile Teams	Transform the Business	Reduce waste					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 48.13DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 40, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16139	BS-2024-005	02.11.01.00.00	Task for: Sales Enablement Platform	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16181	16139	02.11.01.01.00	General	Allocation			6150	615000					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
BS-2024-006	A0021	02.12.00.00.00	Partner Portal Platform	Project	Collaborative platform for managing relationships with channel partners, including training, certification, and deal registration.	Create a comprehensive partner management platform that strengthens channel relationships through better communication, training, and deal management capabilities.	5766.4	61441	Business Systems	Support moden digital workplace	Grow the Business	Server more customers					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 55.63DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 0, Work Avg Score: 0,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 14, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16140	BS-2024-006	02.12.01.00.00	Task for: Partner Portal Platform	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16182	16140	02.12.01.01.00	General	Allocation			5587.5	558750					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
A029	A0021	02.13.00.00.00	Private Cloud Phase 1	Project	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	3180.8	5062.5	Business Systems	Strengthen Cybersecurity Infrastructure	Run the Business	Server more customers					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |					MetaData	2024-12-30 15:38:32
16130	A029	02.13.01.00.00	Task for: Private Cloud Phase 1	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16172	16130	02.13.01.01.00	General	Allocation			4050	405000					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
A0022		03.00.00.00.00	New Products Portfolio	Portfolio			2090.2	128968.9					Decision notes					MetaData - Timebars	2024-12-24 13:13:19
NP-2024-008	A0022	03.01.00.00.00	Event Venue WiFi Solution	Project	High-density WiFi solution designed for temporary deployments at large events and venues.	Develop a specialized solution for event venues that can handle high-density user environments while providing easy deployment and management features for temporary installations.	225	22500	New Products	Source Cloud services for our Core products	Grow the Business	Drive Contract Renewals					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 36.25DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 39, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16148	NP-2024-008	03.01.01.00.00	Task for: Event Venue WiFi Solution	Task			225	22500					Decision notes					MetaData	2024-12-30 15:38:33
16190	16148	03.01.01.01.00	General	Allocation			4500	450000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
TT-2024-004	A0022	03.02.00.00.00	Virtual Network Simulator	Project	Advanced simulation environment for testing network configurations and scenarios before deployment.	Create a comprehensive virtual testing environment that allows customers to validate network designs and configurations before physical deployment, reducing risk and optimizing performance.	204.4	20437.5	New Testing Tools	Improve employee skills	Grow the Business	Reduce waste					1001K to 5000K	Class A	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Reduce waste): 30.00,Project Score: 48.13DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 25,Class Estimate Score: 100,Final Score: 64, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16152	TT-2024-004	03.02.01.00.00	Task for: Virtual Network Simulator	Task			204.4	20437.5					Decision notes					MetaData	2024-12-30 15:38:33
16194	16152	03.02.01.01.00	General	Allocation			4125	412500					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
TT-2024-005	A0022	03.03.00.00.00	Security Vulnerability Scanner	Project	Automated testing tool for identifying and assessing security vulnerabilities in wireless network deployments.	Create a comprehensive security testing solution that helps customers identify and address potential vulnerabilities before they can be exploited. Tool will include automated scanning, risk assessment, and remediation recommendations.	165	16500	New Testing Tools	Strengthen Cybersecurity Infrastructure	Transform the Business	Ensure compliance					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 51.25DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 45, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16153	TT-2024-005	03.03.01.00.00	Task for: Security Vulnerability Scanner	Task			165	16500					Decision notes					MetaData	2024-12-30 15:38:33
16195	16153	03.03.01.01.00	General	Allocation			3262.5	326250					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
TT-2024-006	A0022	03.04.00.00.00	Performance Benchmarking Tool	Project	Automated system for conducting standardized performance tests across different wireless products and configurations.	Create a standardized benchmarking solution that enables objective comparison of different wireless products and configurations, supporting both internal product development and customer decision-making.	191.3	19125	New Testing Tools	Improve product reliability	Transform the Business	Increase share of market					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 28.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 25,Class Estimate Score: 50,Final Score: 44, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16154	TT-2024-006	03.04.01.00.00	Task for: Performance Benchmarking Tool	Task			191.3	19125					Decision notes					MetaData	2024-12-30 15:38:33
16196	16154	03.04.01.01.00	General	Allocation			3900	390000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
A022	A0022	03.05.00.00.00	Google Maps Integration	Project	The <strong>Google Maps Integration with Sales Tool</strong> project aims to enhance the organization’s sales capabilities by embedding Google Maps functionality into the existing sales platform. This initiative will enable advanced location-based features such as route optimization, territory visualization, and proximity analysis, empowering sales teams to plan and execute strategies more effectively.Study and make recommendations.	The <strong>Google Maps Integration with Sales Tool</strong> project is a strategic initiative to improve the efficiency and effectiveness of the sales process. By incorporating location-based intelligence, the project will provide sales teams with actionable insights for territory management, customer outreach, and route planning. This integration will enhance decision-making, reduce travel costs, and improve customer engagement, aligning with the organization’s goal of driving sales performance and operational efficiency.. Study and make recommendations.	3404.8	49937.6	Innovation	Source Cloud services for our Core products	Grow the Business	Drive Contract Renewals					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 46.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 50, Work Avg Score: 0,Final Score: 55, Decision: Consider Terminating |					MetaData	2024-12-30 15:38:32
16125	A022	03.05.01.00.00	Task for: Google Maps Integration	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:33
16167	16125	03.05.01.01.00	General	Allocation			3900	390000					Decision notes					MetaData - Timebars	2024-12-30 15:38:33
NP-2024-001	A0022	03.06.00.00.00	AI-Powered Mesh Network System	Project	Next-generation mesh WiFi system with AI-driven optimization for automatic network configuration, load balancing, and interference mitigation.	Develop a premium mesh network solution that leverages machine learning to provide superior coverage and performance. The system will automatically adapt to changing network conditions, optimize channel selection, and provide predictive maintenance alerts. Target market includes high-end residential and small business customers seeking enterprise-grade reliability.	998.8	57937.5	New Products	Strengthen Cybersecurity Infrastructure	Grow the Business	Attract and retain the best people					0 to 100K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 75.00DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 100,Cost Avg Score: 0, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 58, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:33
16141	NP-2024-001	03.06.01.00.00	Task for: AI-Powered Mesh Network System	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16183	16141	03.06.01.01.00	General	Allocation			9675	967500					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
NP-2024-002	A0022	03.07.00.00.00	Industrial IoT Gateway Pro	Project	Ruggedized WiFi 6E gateway designed specifically for industrial IoT applications with enhanced security features and environmental hardening.	Address the growing industrial IoT market with a robust gateway solution that can withstand harsh environments while providing enterprise-grade security and management features. Product will include dual-band support, advanced encryption, and integration with major industrial automation platforms.	499.4	24968.8	New Products	Build AI/ML Capabilities	Run the Business	Improve our core products					101K to250K	Class A	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 63.13DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 100,Final Score: 54, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16142	NP-2024-002	03.07.01.00.00	Task for: Industrial IoT Gateway Pro	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16184	16142	03.07.01.01.00	General	Allocation			3187.5	318750					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
NP-2024-003	A0022	03.08.00.00.00	Smart City WiFi Antenna Array	Project	High-capacity, weather-resistant antenna array designed for municipal WiFi deployments with integrated environmental monitoring capabilities.	Capitalize on smart city initiatives by offering a comprehensive outdoor WiFi solution that combines high-performance wireless connectivity with environmental sensors. System will include air quality monitoring, weather tracking, and traffic flow analysis capabilities.	499.4	24968.8	New Products	Faster response to new business opportunities	Modernize the Business	Build Recurring Revenue Streams					1000K Plus	Class B	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 43.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 75,Final Score: 44, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16143	NP-2024-003	03.08.01.00.00	Task for: Smart City WiFi Antenna Array	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16185	16143	03.08.01.01.00	General	Allocation			3187.5	318750					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
NP-2024-005	A0022	03.09.00.00.00	Educational Institution WiFi Bundle	Project	Comprehensive WiFi solution package designed specifically for educational institutions with content filtering and bandwidth management.	Create a turnkey solution for schools and universities that combines hardware, software, and services for easy deployment and management. Package will include content filtering, user authentication, and detailed usage analytics.	562	31360	New Products	Faster response to new business opportunities	Run the Business	Attract and retain the best people					101K to250K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 62.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 40, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16145	NP-2024-005	03.09.01.00.00	Task for: Educational Institution WiFi Bundle	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16187	16145	03.09.01.01.00	General	Allocation			7612.5	761250					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
A0023		04.00.00.00.00	Our Core Products Portfolio	Portfolio			2090.2	128968.9					Decision notes					MetaData - Timebars	2024-12-24 13:13:20
A021	A0023	04.01.00.00.00	Extend WWT to support AI	Project	The <strong>Extend WWT to Support AI</strong> project focuses on enhancing the organization’s existing <strong>Wireless Workflow Tool (WWT)</strong> by integrating artificial intelligence capabilities. This initiative aims to incorporate AI-driven features such as predictive analytics, automated decision-making, and intelligent task prioritization to streamline workflows, improve operational efficiency, and support data-driven strategies.	The <strong>Extend WWT to Support AI</strong> project is a transformative step in modernizing the <strong>Wireless Workflow Tool</strong> by leveraging artificial intelligence to enhance its capabilities. By integrating AI-powered analytics, automation, and machine learning, this initiative will enable smarter decision-making, improve process efficiency, and provide actionable insights for optimizing wireless equipment and installation workflows. This extension supports the organization’s commitment to innovation and positions WWT as a cutting-edge tool for driving operational excellence and competitive advantage.	1126.4	21093.8	Productivity Tools	Improve productivity with Agile Teams	Transform the Business	Reduce waste					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 38.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |					MetaData	2024-12-30 15:38:32
16124	A021	04.01.01.00.00	Task for: Extend WWT to support AI	Task			0	0					Decision notes					MetaData - Timebars	2024-12-24 13:13:20
16166	16124	04.01.01.01.00	General	Allocation			2812.5	281250					Decision notes					Timebars	2024-12-30 15:38:34
NP-2024-004	A0023	04.02.00.00.00	Healthcare-Optimized Access Point	Project	Specialized access point designed for healthcare environments with enhanced HIPAA compliance features and medical device interference prevention.	Develop a purpose-built wireless solution for healthcare facilities that addresses specific industry requirements including regulatory compliance, medical device compatibility, and reliable coverage in challenging building layouts.	315.1	21093.8	New Products	Improve employee skills	Grow the Business	Accelerate Time-to-Market					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 58.13DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 51, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16144	NP-2024-004	04.02.01.00.00	Task for: Healthcare-Optimized Access Point	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16186	16144	04.02.01.01.00	General	Allocation			5175	517500					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
NP-2024-006	A0023	04.03.00.00.00	Retail Analytics Hotspot	Project	Specialized hotspot solution with integrated customer analytics and behavior tracking capabilities for retail environments.	Develop a retail-focused wireless solution that provides both customer connectivity and valuable business intelligence through anonymous traffic analysis and behavior tracking.	459.8	26320	New Products	Improve employee skills	Transform the Business	Improve our core products					1000K Plus	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 44.38DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 28, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16146	NP-2024-006	04.03.01.00.00	Task for: Retail Analytics Hotspot	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16188	16146	04.03.01.01.00	General	Allocation			5025	502500					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
NP-2024-007	A0023	04.04.00.00.00	Hospitality WiFi Management Suite	Project	Complete WiFi management solution for hotels and resorts with guest analytics and service quality monitoring.	Develop an integrated solution for the hospitality industry that combines high-performance WiFi with guest management features and detailed analytics for service optimization.	1126.4	11390.6	New Products	Improve product reliability	Grow the Business	Build Recurring Revenue Streams					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Products): 0.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 50.00DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 25,Class Estimate Score: 50,Final Score: 50, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16147	NP-2024-007	04.04.01.00.00	Task for: Hospitality WiFi Management Suite	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16189	16147	04.04.01.01.00	General	Allocation			2887.5	288750					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
TT-2024-001	A0023	04.05.00.00.00	Spectrum Analysis Pro Suite	Project	Advanced RF spectrum analysis toolkit with AI-powered interference detection and automated reporting capabilities.	Create a comprehensive testing solution that combines hardware sensors with intelligent software to streamline network troubleshooting and optimization. Tool will provide real-time analysis, predictive insights, and automated recommendation generation.	101.3	5062.5	New Testing Tools	Improve product reliability	Run the Business	Improve customer service					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve customer service): 60.00,Project Score: 46.25DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 39, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16149	TT-2024-001	04.05.01.00.00	Task for: Spectrum Analysis Pro Suite	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16191	16149	04.05.01.01.00	General	Allocation			2025	202500					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
TT-2024-002	A0023	04.06.00.00.00	Mobile Network Validator	Project	Portable testing device for field verification of wireless network performance, coverage mapping, and quality of service metrics.	Develop a compact, all-in-one testing solution for field technicians that combines multiple testing capabilities in a single device. Tool will streamline installation and maintenance processes while providing detailed documentation and reporting.	213.8	16031.3	New Testing Tools	Improve productivity with Agile Teams	Modernize the Business	Build Recurring Revenue Streams					101K to 300K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 34.38DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 75,Class Estimate Score: 50,Final Score: 45, State Warning! Awaiting Approval,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16150	TT-2024-002	04.06.01.00.00	Task for: Mobile Network Validator	Task			0	0					Decision notes					MetaData	2024-12-30 15:38:34
16192	16150	04.06.01.01.00	General	Allocation			2325	232500					Decision notes					MetaData - Timebars	2024-12-30 15:38:34
TT-2024-003	A0023	04.07.00.00.00	Automated Certification Platform	Project	Cloud-based platform for automated testing and certification of wireless devices and configurations against industry standards.	Build a scalable testing platform that reduces certification time and costs while ensuring consistent quality standards. Platform will support multiple wireless standards and provide detailed compliance reporting.	776.3	57937.5	New Testing Tools	Source Cloud services for our Core products	Transform the Business	Increase share of market					1001K to 5000K	Class C	STRATEGIC PRIORITY ANALYSIS - Category Score: (New Testing Tools): 0.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 22.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 0, Work Avg Score: 100,ROM Estimate Score: 25,Class Estimate Score: 50,Final Score: 40, State null,Financial Metrics: 0. |					MetaData	2024-12-30 15:38:34
16151	TT-2024-003	04.07.01.00.00	Task for: Automated Certification Platform	Task			0	0					MetaData	2024-12-30 15:38:34
16193	16151	04.07.01.01.00	General	Allocation			3225	322500					MetaData - Timebars	2024-12-30 15:38:34
Run Report

## AdminPanel
apID	ap_name	apCustomerID	apFilteredFrom	apAzureID	apTS_WeeklyOrMonthly	apTS_WeeklyPxFactor	apTS_Start	apTS_Finish	apHelpCoordTop	apHelpCoordLeft	apTS_MonthlyPxFactor	apStatusDate	apFilteredFromTbID	ap_HolidayDate	ap_HolidayName	apSchMethod	apTbVisibleLevel	totalNumberOfPeople	numberOfPeoplePerLine	pxPerPerson	apHideCompletedBarsYN	showGhostBarsYN	showBaselineBarsYN	apFilteredFromKbID	apTbProduct	apT1	apT2	apT3	apT4	apT5	apT6	apT7	apT8	apT9	apT10	apT11	apT12	apT14	apT15
Timebar Application Settings																									auto filled	ApT1TaskLines – task lines on/off	User ID linked to license\	expires on	count of timebars for license	project count	close intro perm	fFrom P3Menu	product URI	dupe counter	lines on yes no	Bar/Box Toggle	Dark Mode Toggle	last scroll y	Use corrdTop P3 Menu
MDUID	Name	Customer ID	Filtered From	Azure ID	TS Weekly Or Monthly	TS Weekly Px Factor	TS Start	TSFinish	Help Coord Top	Help Coord Left	TS Monthly Px Factor	StatusDate	Filtered From Tb ID	Holiday Date	Holiday Name	Sch Method	Tb Visible Level	Total Number Of People	Number Of People Per Line	Px Per Person	Hide Completed Bars YN	Show Ghost Bars YN	Show Baseline Bars YN	apFilteredFromKbID	apTbProduct	apT1	apT2	apT3	apT4	apT5	apT6	apT7	apT8	apT9	apT10	apT11	apT12	apT14	apT15
1	Standard Config Settings	44	Canvas		Monthly	10	04-Nov-24		50	400	2	25-Nov-24	A012			Standard	L5				false	No	No	A012	CBT03	true	jcox@costbars.com	08-Jul-2029	40	13	doNotShowIntro	FM-OFF	CB	99	false	false	false	0:0	false
2	Bar Graph Settings		Timebars															30	3	7
3	Standard Holidays		Timebars											09-Oct-2023	Thanks Giving
4	Standard Holidays		Timebars											25-Dec-2023	Christmas
5	Standard Holidays		Timebars											26-Dec-2023	Boxing Day
6	Standard Holidays		Timebars											01-Jan-2024	New Years Day
7	Standard Holidays		Timebars											04-Sep-2023	Labour Day
8	Standard Holidays		Timebars											17-Mar-2023	Good Friday
9	Standard Holidays		Timebars											20-Mar-2023	Easter Monday
10	Standard Holidays		Timebars											01-May-2023	Victoria Day
11	Standard Holidays		Timebars											01-Jul-2023	Canada Day
12	Standard Holidays		Timebars											7-Aug-2023	Summer Day Off
13	Standard Holidays		Timebars											09-Oct-2024	Thanks Giving
14	Standard Holidays		Timebars											25-Dec-2024	Christmas
15	Standard Holidays		Timebars											26-Dec-2023	Boxing Day
16	Standard Holidays		Timebars											01-Jan-2024	New Years Day
17	Standard Holidays		Timebars											02-Sep-2024	Labour Day
18	Standard Holidays		Timebars											17-Mar-2024	Good Friday
19	Standard Holidays		Timebars											20-Mar-2024	Easter Monday
20	Standard Holidays		Timebars											01-May-2024	Victoria Day
21	Standard Holidays		Timebars											01-Jul-2024	Canada Day
22	Standard Holidays		Timebars											7-Aug-2024	Summer Day Off
Import Data

## Timebars
tbID	tbSelfKey2	tbPredecessor	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	kbCoordLeft	tbCoordTopP3Menu	tbResID	tbOwner	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbCost	tbACost	tbCostRemaining	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbCostID	tbCostType	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbStatus	tbState	tbPriority	tbTaskParent
Timebars Data Store		Import Data	Format	tbTypeInternal	SubType																																																					Timebar Status
UID	Parent	Predecessor	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Lane	Custom Coord Top	ResID	Owner	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	Cost	Actual Cost	Cost Remaining	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbCostID	Cost Type	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	Status	State	Priority	tbTaskParent??
A0021			Digital Transformation Portfolio	Portfolio		02.00.00.00.00	28			150		Jim Cox	58880	0	58880	0	30-Jan-2025	17-Nov-2026			469	469	5888000	0	5888000			0				Phase	Digital Transformation Portfolio	NA	NA	NA	NA											30		44
A007	A0021		Business Continuity Management	Project		02.01.00.00.00	246			760		Jim Cox	6600	0	6600	0	02-Mar-2025	17-Oct-2025			165	165	660000	0	660000							Phase	Digital Transformation Portfolio	Business Continuity Management	NA	NA	NA											30		44
16113	A007		Task for: Business Continuity Management	Task		02.01.01.00.00	286						6600	0	6600	0	02-Mar-2025	17-Oct-2025			165	165	660000	0	660000		0						Digital Transformation Portfolio	Business Continuity Management	NA	Task for: Business Continuity Management	NA				0	0	1							44								Active
16155	16113		General	Allocation		02.01.01.01.00	326				800	CRM Team	6600	0	6600	0	02-Mar-2025	17-Oct-2025			165	165	660000	0	660000	8	2	500	100		Generic		Digital Transformation Portfolio	Business Continuity Management	NA	Task for: Business Continuity Management	General				0	0	1							44								Active
A019	A0021	A007	Database Upgrade Market Datamart	Project		02.02.00.00.00	236			560		Jim Cox	3480	0	3480	0	28-Dec-2025	28-Apr-2026			87	87	348000	0	348000								Digital Transformation Portfolio	Database Upgrade Market Datamart	NA	NA	NA											30		44
16122	A019		Task for: Database Upgrade Market Datamart	Task		02.02.01.00.00	276						3480	0	3480	0	28-Dec-2025	28-Apr-2026			87	87	348000	0	348000		0						Digital Transformation Portfolio	Database Upgrade Market Datamart	NA	Task for: Database Upgrade Market Datamart	NA				0	0	1							44								Active
16164	16122		General	Allocation		02.02.01.01.00	316				800	CRM Team	3480	0	3480	0	28-Dec-2025	28-Apr-2026			87	87	348000	0	348000	8	2	500	100		Generic		Digital Transformation Portfolio	Database Upgrade Market Datamart	NA	Task for: Database Upgrade Market Datamart	General				0	0	1							44								Active
A009	A0021		Continuous Improvement Transformation	Project		02.03.00.00.00	70			480		Jim Cox	4120	0	4120	0	12-Feb-2025	05-Jul-2025			103	103	412000	0	412000							Phase	Digital Transformation Portfolio	Continuous Improvement Transformation	NA	NA	NA											30		44
16115	A009		Task for: Continuous Improvement Transformation	Task		02.03.01.00.00	112						4120	0	4120	0	12-Feb-2025	04-Jul-2025			103	103	412000	0	412000		0						Digital Transformation Portfolio	Continuous Improvement Transformation	NA	Task for: Continuous Improvement Transformation	NA				0	0	1					30		44								Active
16157	16115		General	Allocation		02.03.01.01.00	154				800	CRM Team	4120	0	4120	0	12-Feb-2025	04-Jul-2025			103	103	412000	0	412000	8	2	500	100		Generic		Digital Transformation Portfolio	Continuous Improvement Transformation	NA	Task for: Continuous Improvement Transformation	General				0	0	1							44								Active
A012	A0021		Digital Desktop - Transformation	Project		02.04.00.00.00	82			840		Jim Cox	3960	0	3960	0	18-Sep-2025	29-Jan-2026			96	96	396000	0	396000							Phase	Digital Transformation Portfolio	Digital Desktop - Transformation	NA	NA	NA											30		44
16118	A012		Task for: Digital Workplace - Transformation	Task		02.04.01.00.00	124						3960	0	3960	0	18-Sep-2025	03-Feb-2026			99	99	396000	0	396000		0						Digital Transformation Portfolio	Digital Desktop - Transformation	NA	Task for: Digital Workplace - Transformation	NA				0	0	1					30		44								Active
16160	16118		General	Allocation		02.04.01.01.00	166				800	CRM Team	3960	0	3960	0	18-Sep-2025	03-Feb-2026			99	99	396000	0	396000	8	2	500	100		Generic		Digital Transformation Portfolio	Digital Desktop - Transformation	NA	Task for: Digital Workplace - Transformation	General				0	0	1							44								Active
BS-2024-001	A0021		Customer Experience Platform	Project		02.05.00.00.00	394			1280		Jim Cox	3400	0	3400	0	05-Mar-2025	01-Jul-2025			85	85	340000	0	340000								Digital Transformation Portfolio	Customer Experience Platform	NA	NA	NA											30		44
16135	BS-2024-001		Task for: Customer Experience Platform	Task		02.05.01.00.00	436						3400	0	3400	0	05-Mar-2025	01-Jul-2025			85	85	340000	0	340000		0						Digital Transformation Portfolio	Customer Experience Platform	NA	Task for: Customer Experience Platform	NA				0	0	1							44								Active
16177	16135		General	Allocation		02.05.01.01.00	478				800	CRM Team	3400	0	3400	0	05-Mar-2025	01-Jul-2025			85	85	340000	0	340000	8	2	500	100		Generic		Digital Transformation Portfolio	Customer Experience Platform	NA	Task for: Customer Experience Platform	General				0	0	1							44								Active
A010	A0021		Constant Internal Delivery Enablement	Project		02.06.00.00.00	394			520		Jim Cox	5280	0	5280	0	09-Aug-2025	10-Feb-2026			132	132	528000	0	528000							Phase	Digital Transformation Portfolio	Constant Internal Delivery Enablement	NA	NA	NA											30		44
16116	A010		Task for: Constant Internal Delivery Enablement	Task		02.06.01.00.00	436						5280	0	5280	0	09-Aug-2025	10-Feb-2026			132	132	528000	0	528000		0						Digital Transformation Portfolio	Constant Internal Delivery Enablement	NA	Task for: Constant Internal Delivery Enablement	NA				0	0	1							44								Active
16158	16116		General	Allocation		02.06.01.01.00	478				800	CRM Team	5280	0	5280	0	09-Aug-2025	10-Feb-2026			132	132	528000	0	528000	8	2	500	100		Generic		Digital Transformation Portfolio	Constant Internal Delivery Enablement	NA	Task for: Constant Internal Delivery Enablement	General				0	0	1							44								Active
A018	A0021		Classified data in Public Cloud	Project		02.07.00.00.00	736			360		Jim Cox	4360	0	4360	0	18-Feb-2025	19-Jul-2025			109	109	436000	0	436000								Digital Transformation Portfolio	Classified data in Public Cloud	NA	NA	NA											30		44
16121	A018		Task for: Classified data in Public Cloud	Task		02.07.01.00.00	778						4360	0	4360	0	18-Feb-2025	19-Jul-2025			109	109	436000	0	436000		0						Digital Transformation Portfolio	Classified data in Public Cloud	NA	Task for: Classified data in Public Cloud	NA				0	0	1							44								Active
16163	16121		General	Allocation		02.07.01.01.00	820				800	CRM Team	4360	0	4360	0	18-Feb-2025	19-Jul-2025			109	109	436000	0	436000	8	2	500	100		Generic		Digital Transformation Portfolio	Classified data in Public Cloud	NA	Task for: Classified data in Public Cloud	General				0	0	1							44								Active
A031	A0021		SAP Platform Upgrade	Project		02.08.00.00.00	916			800		Jim Cox	4800	0	4800	0	15-Feb-2025	01-Aug-2025			120	120	480000	0	480000								Digital Transformation Portfolio	SAP Platform Upgrade	NA	NA	NA											30		44
16132	A031		Task for: SAP Platform Upgrade	Task		02.08.01.00.00	958						4800	0	4800	0	15-Feb-2025	01-Aug-2025			120	120	480000	0	480000		0						Digital Transformation Portfolio	SAP Platform Upgrade	NA	Task for: SAP Platform Upgrade	NA				0	0	1							44								Active
16174	16132		General	Allocation		02.08.01.01.00	1000				800	CRM Team	4800	0	4800	0	15-Feb-2025	01-Aug-2025			120	120	480000	0	480000	8	2	500	100		Generic		Digital Transformation Portfolio	SAP Platform Upgrade	NA	Task for: SAP Platform Upgrade	General				0	0	1							44								Active
A036	A0021		Upgrade Ticketing System	Project		02.09.00.00.00	394			600		Jim Cox	2400	0	2400	0	23-Mar-2026	12-Jun-2026			60	60	240000	0	240000								Digital Transformation Portfolio	Upgrade Ticketing System	NA	NA	NA											30		44
16134	A036		Task for: Upgrade Ticketing System	Task		02.09.01.00.00	436						2400	0	2400	0	23-Mar-2026	12-Jun-2026			60	60	240000	0	240000		0						Digital Transformation Portfolio	Upgrade Ticketing System	NA	Task for: Upgrade Ticketing System	NA				0	0	1							44								Active
16176	16134		General	Allocation		02.09.01.01.00	478				800	CRM Team	2400	0	2400	0	23-Mar-2026	12-Jun-2026			60	60	240000	0	240000	8	2	500	100		Generic		Digital Transformation Portfolio	Upgrade Ticketing System	NA	Task for: Upgrade Ticketing System	General				0	0	1							44								Active
A030	A0021	A018	Public Cloud Phase 1	Project		02.10.00.00.00	742			920		Jim Cox	3880	0	3880	0	28-Aug-2025	11-Jan-2026			97	97	388000	0	388000								Digital Transformation Portfolio	Public Cloud Phase 1	NA	NA	NA											30		44
16131	A030		Task for: Public Cloud Phase 1	Task		02.10.01.00.00	784						3880	0	3880	0	28-Aug-2025	11-Jan-2026			97	97	388000	0	388000		0						Digital Transformation Portfolio	Public Cloud Phase 1	NA	Task for: Public Cloud Phase 1	NA				0	0	1							44								Active
16173	16131		General	Allocation		02.10.01.01.00	826				800	CRM Team	3880	0	3880	0	28-Aug-2025	11-Jan-2026			97	97	388000	0	388000	8	2	500	100		Generic		Digital Transformation Portfolio	Public Cloud Phase 1	NA	Task for: Public Cloud Phase 1	General				0	0	1							44								Active
BS-2024-005	A0021		Sales Enablement Platform	Project		02.11.00.00.00	550			1640		Jim Cox	6600	0	6600	0	30-May-2025	14-Jan-2026			164	164	660000	0	660000							Phase	Digital Transformation Portfolio	Sales Enablement Platform	NA	NA	NA											30		44
16139	BS-2024-005		Task for: Sales Enablement Platform	Task		02.11.01.00.00	592						6600	0	6600	0	30-May-2025	14-Jan-2026			164	164	660000	0	660000		0						Digital Transformation Portfolio	Sales Enablement Platform	NA	Task for: Sales Enablement Platform	NA				0	0	1							44								Active
16181	16139		General	Allocation		02.11.01.01.00	634				800	CRM Team	6560	0	6560	0	30-May-2025	14-Jan-2026			164	164	656000	0	656000	8	2	500	100		Generic		Digital Transformation Portfolio	Sales Enablement Platform	NA	Task for: Sales Enablement Platform	General				0	0	1							44								Active
BS-2024-006	A0021	A030	Partner Portal Platform	Project		02.12.00.00.00	916			1720		Jim Cox	5880	0	5880	0	29-Jan-2026	21-Aug-2026			147	147	588000	0	588000							Phase	Digital Transformation Portfolio	Partner Portal Platform	NA	NA	NA											30		44
16140	BS-2024-006		Task for: Partner Portal Platform	Task		02.12.01.00.00	958						5880	0	5880	0	29-Jan-2026	23-Aug-2026			147	147	588000	0	588000		0						Digital Transformation Portfolio	Partner Portal Platform	NA	Task for: Partner Portal Platform	NA				0	0	1					30		44								Active
16182	16140		General	Allocation		02.12.01.01.00	1000				800	CRM Team	5880	0	5880	0	29-Jan-2026	23-Aug-2026			147	147	588000	0	588000	8	2	500	100		Generic		Digital Transformation Portfolio	Partner Portal Platform	NA	Task for: Partner Portal Platform	General				0	0	1							44								Active
A029	A0021	A030	Private Cloud Phase 1	Project		02.13.00.00.00	742			880		Jim Cox	4240	0	4240	0	30-Jan-2026	28-Jun-2026			106	106	424000	0	424000								Digital Transformation Portfolio	Private Cloud Phase 1	NA	NA	NA											30		44
16130	A029		Task for: Private Cloud Phase 1	Task		02.13.01.00.00	784						4240	0	4240	0	30-Jan-2026	28-Jun-2026			106	106	424000	0	424000		0						Digital Transformation Portfolio	Private Cloud Phase 1	NA	Task for: Private Cloud Phase 1	NA				0	0	1							44								Active
16172	16130		General	Allocation		02.13.01.01.00	826				800	CRM Team	4240	0	4240	0	30-Jan-2026	28-Jun-2026			106	106	424000	0	424000	8	2	500	100		Generic		Digital Transformation Portfolio	Private Cloud Phase 1	NA	Task for: Private Cloud Phase 1	General				0	0	1							44								Active

## MetaData
tbMDID	tbMDParent	tbMDName / Format	tbMDTypes / Toggle Cols	tbMDSubtype	tbMDHierarchy	tbMDProduct	tbMDNotesProject	tbMDDescription	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDHealth	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDEscalationLevel	tbMDProjectNumber	tbMDPM	tbMDExSponsor	tbMDNotes	tbMDPrimaryContact	tbMDDepartment	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDProjectType	tbMDRiskVsSizeAndComplexity	tbMDROMEstimate	tbMDEstimationClass	tbMDSize	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDYesNoSelector	tbMDPriorityStrategic	tbMDCostbarsScore	tbMDFinancialScore	tbMDDecisionStrategic	tbMDDecisionNotes	tbMDPrimaryLineOfBusiness	tbMDSponsoringDepartment	tbMDContact	tbMDContactNumber	tbMDResponsibleTeam	tbMDBusinessAdvisor	tbMDDeliveryManager	tbMDOrgManager	tbMDBenefitCostRatio	tbMDEcnomicValueAdded	tbMDInternalRateOfReturn	tbMDSunkCosts	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDOther2	tbMDBusinessOwner	tbMDBackgroundInfo	tbMDCapabilitiesNeeded	tbMDConsequence	tbMDExpectedBenefits	tbMDProblemOpportunity	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommittment	tbMDStakeholderDescription	tbMDWrittenBy	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDResID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDResponsibility	tbMDExtSystemID1	tbMDSyncNotes	tbMDStageApprover	tbMDSprintName	tbMDExtLink1	tbMDOther3	canvasNo	tbMDRefID	tbMDSortOrder	tbMDtbLastModified	tbMDShowIn	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDNotesWorkflow	tbMDContractNumber	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSeverity	tbMDContingency	tbMDMitigationPlan	tbMDMitigationStatus	tbMDProbability	tbMDImpact	tbMDRiskResponseStrategy	tbMDContingencyPlan	tbMDTriggerEvent	tbMDEarlyWarningIndicators	tbMDScore
MetaData Store	Import Data	Set Picklists	tbType			Product				Timebar Priority	Timebar Status	Health	WF State	Stage	Phase	Gate	Category	Escalation Level						Department	Health Overall	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Type Of Initiative	Risk Vs Size	ROM Estimate	Estimation Class	Size	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Selected	Strategic Priority					Primary Line Of Business	Sponsoring Department			Responsible Team	Business Advisor	Delivery Manager	Organization Manager																								Primary Skill	Primary Role	Responsibility																								Risk Probability	Risk Impact
MDUID	Parent	Name	Type	SubType	Hierarchy Order	Product	Project Notes	Description	Executive Summary	Priority	Status	Health Status	WF State	Stage	Phase	Gate	Category	Escelation Level	Project Number	PM	Executive Sponsor	General Notes	Primary Contact	Department	Health Overall	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Initiative Type	Risk Vs Size And Complexity	ROM Estimate	Estimation Class	Size	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Selected	Strategic Priority	Costbars Score	Financial Score	Strategic Decision	Decision Notes	Primary Line Of Business	Sponsoring Department	Contact	Contact Number	Responsible Team	Business Advisor	Delivery Manager	Organization Manager	Benefit Cost Ratio	Ecnomic Value Added	Internal Rate Of Return	Sunk Costs	Net Present Value	Opportunity Cost	Payback Period	Financial Score	Business Owner	Background Info	Capabilities Needed	Consequence of Inaction	Expected Benefits	Problem Opportunity	Constraints Assumptions	Cost Benefit Analysis	Senior Level Committment	Stakeholder Description	Written By	WBS	Weighting	Location	ResID	Primary Skill	Primary Role	Responsibility	Ext ID	Sync Notes	Stage Approver	Sprint Name	tbMDExtLink1	Other3	canvasNo	tbMDRefID	Sort Order	Last Modified	Show In	Customer ID	Azure ID	Name Short	Notes Workflow	Contract Number	Portfolio	Program	Program Activity Alignment	Severity	Contingency	Mitigation Plan	Mitigation Status	Probability	Impact	Risk Response Strategy	Contingency Plan	Trigger Event	Early Warning Indicators	Score
A0021					02.00.00.00.00
A007	A0021				02.01.00.00.00	CEP		Upgrade the collaboration sites in conjunction with business owners.	Upgrade the collaboration sites in conjunction with business owners.	Low	New	No Assessed	Awaiting Input				Systems	Not Assessed	1007	Joe Invent	Ally HR		Ally HR	Engineering	Green	Green	Green	Green	Green	Green	Green	Proposal	2	101K to250K	Class C	Small	Our Core Products	Source Cloud services for our Core products	Transform the Business	Increase share of market	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Integration																																							44
16113	A007				02.01.01.00.00																																																																																		1					44
16155	16113				02.01.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A019	A0021				02.02.00.00.00	CEP		Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Fix burdens on operations in terms of non-value add activities required by the state of source data and the manual processes required by the current tool set.	Low	In progress	On schedule	Awaiting Input				Systems	Not Assessed	1016	Joe Invent	Ally HR			Engineering	Green	Green	Green	Green	Green	Green	Green	Project	2	1000K Plus	Class C		Business Systems	Improve product reliability	Grow the Business	Build Recurring Revenue Streams	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Integration																																							44
16122	A019				02.02.01.00.00																																																																																		1					44
16164	16122				02.02.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A009	A0021				02.03.00.00.00	NA		A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.	Normal	New	No Assessed	Awaiting Review				Services	Not Assessed	1006	Julia Finance	Ally HR		Ally HR	Business Development	Green	Green	Green	Green	Green	Green	Green	Proposal	4	0 to 100K	Class C	Small	Business Systems	Improve productivity with Agile Teams	Modernize the Business	Build Recurring Revenue Streams	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of IT																																							45
16115	A009				02.03.01.00.00																																																																																		1					44
16157	16115				02.03.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A012	A0021				02.04.00.00.00	NA		Enabling an employee experience that is simple, relevant and caring.	Enabling an employee experience that is simple, relevant and caring.	Normal	New	No Assessed	Approved				Services	Not Assessed	1003	Julia Finance	Ally HR		Joe Invent	Business Development	Yellow	Red	Yellow	Red	Red	Yellow	Yellow	Proposal	3	0 to 100K	Class C	Small	Digital Transformation	Faster response to new business opportunities	Modernize the Business	Build Recurring Revenue Streams	Not Assessed	0	0	0	Not Assessed	Not Assessed	Research and Development						Manager of IT																																							44
16118	A012				02.04.01.00.00																																																																																		1					44
16160	16118				02.04.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
BS-2024-001	A0021				02.05.00.00.00	CEP		Integrated platform for managing customer relationships, support tickets, and product deployment tracking.	Implement a modern CRM system tailored to our industry, improving customer satisfaction through better service delivery and proactive support. System will integrate with existing tools and provide comprehensive analytics.		New	On schedule	Approved				Systems	Not Assessed	1031	Joe Invent	Ally HR			Engineering	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Proposal	2	1000K Plus	Class B		Business Systems	Strengthen Cybersecurity Infrastructure	Run the Business	Drive Contract Renewals	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Engineering
16135	BS-2024-001				02.05.01.00.00																																																																																		1					44
16177	16135				02.05.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A010	A0021				02.06.00.00.00	CEP		This program shall roll up all investments regarding our buildings and office space.	This program shall roll up all investments regarding our buildings and office space.	Low	In progress	Early	Spawned				External	Not Assessed	1008	Joe Invent	Ally HR			Engineering	Green	Green	Green	Green	Green	Green	Green	Project	1	1000K Plus	Class C	Small	Productivity Tools	Improve employee skills	Grow the Business	Reduce waste	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Integration																																							44
16116	A010				02.06.01.00.00																																																																																		1					44
16158	16116				02.06.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A018	A0021				02.07.00.00.00	Secure Cloud System		This is my Brief Description	This is my Brief Description	Normal	In progress	Early	Requested Approval				Systems	Not Assessed	1013	Julia Finance	Ally HR			Business Development	Green	Green	Green	Green	Green	Green	Green	Project	4	1001K to 5000K	Class C		Productivity Tools	Strengthen Cybersecurity Infrastructure	Transform the Business	Ensure compliance	Not Assessed	0	0	0	Not Assessed	Not Assessed	Engineering and Product Delivery						Manager of IT																																							44
16121	A018				02.07.01.00.00																																																																																		1					44
16163	16121				02.07.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A031	A0021				02.08.00.00.00	SAP System		Study and make recommendations.	Study and make recommendations.	High	In progress	On schedule	Approved				External	Not Assessed	1020	Julia Finance	Ally HR			Manufacturing	Green	Green	Green	Green	Green	Green	Green	Project	4	1000K Plus	Class C		Digital Transformation	Support moden digital workplace	Grow the Business	Server more customers	Not Assessed	0	0	0	Not Assessed	Not Assessed	Engineering and Product Delivery						Manager of Engineering																																							44
16132	A031				02.08.01.00.00																																																																																		1					44
16174	16132				02.08.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A036	A0021				02.09.00.00.00	Ticketing system		Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Low	In progress	Slipping	Requested Approval				External	Not Assessed	1017	Julia Finance	Ally HR			Engineering	Green	Green	Green	Green	Green	Green	Green	Project	3	1001K to 5000K	Class C		Our Core Products	Improve product reliability	Transform the Business	Increase share of market	Not Assessed	0	0	0	Not Assessed	Not Assessed	Corporate Affairs						Manager of Integration																																							44
16134	A036				02.09.01.00.00																																																																																		1					44
16176	16134				02.09.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A030	A0021				02.10.00.00.00	CEP		Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Projects and initiatives related to planning, development and implementation of Data Management Capabilities within Northern Wireless Inc.. Specifically, the program will have a focus on Business Glossary, Metadata Management, Data Quality Management, Reference and Master Data Management Capabilities.	Low	In progress	On schedule	Awaiting Review				Systems	Not Assessed	1022	Joe Invent	Ally HR			Engineering	Green	Green	Green	Green	Green	Green	Green	Project	1	1001K to 5000K	Class C		Our Core Products	Build AI/ML Capabilities	Transform the Business	Server more customers	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Integration																																							44
16131	A030				02.10.01.00.00																																																																																		1					44
16173	16131				02.10.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
BS-2024-005	A0021				02.11.00.00.00	CEP		Digital platform for managing sales content, product configurations, and quote generation.	Implement a comprehensive sales enablement system that streamlines the sales process through better content management, automated configuration tools, and integrated quote generation.		New	On schedule	Approved				Systems	Not Assessed	1040	Joe Invent	Ally HR			Manufacturing	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Project	3	1000K Plus	Class C		Business Systems	Improve productivity with Agile Teams	Transform the Business	Reduce waste	Not Assessed	0	0	0	Not Assessed	Not Assessed	Corporate Affairs						Manager of Engineering
16139	BS-2024-005				02.11.01.00.00																																																																																		1					44
16181	16139				02.11.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
BS-2024-006	A0021				02.12.00.00.00	CEP		Collaborative platform for managing relationships with channel partners, including training, certification, and deal registration.	Create a comprehensive partner management platform that strengthens channel relationships through better communication, training, and deal management capabilities.		New	On schedule	Approved				Services	Not Assessed	1042	Julia Finance	Ally HR			Manufacturing	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Proposal	4	1000K Plus	Class C		Business Systems	Support moden digital workplace	Grow the Business	Server more customers	Not Assessed	0	0	0	Not Assessed	Not Assessed	Business Technology Solutions						Manager of Integration
16140	BS-2024-006				02.12.01.00.00																																																																																		1					44
16182	16140				02.12.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D
A029	A0021				02.13.00.00.00	Secure Cloud System		It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	It was determined that Northern Wireless Inc. would work the market and share it with the private organizations.	Normal	In progress	On schedule	Awaiting Approval				Services	Not Assessed	1021	Joe Invent	Ally HR			Business Development	Green	Green	Green	Green	Green	Green	Green	Project	2	101K to 300K	Class C		Business Systems	Strengthen Cybersecurity Infrastructure	Run the Business	Server more customers	Not Assessed	0	0	0	Not Assessed	Not Assessed	Engineering and Product Delivery						Manager of IT																																							44
16130	A029				02.13.01.00.00																																																																																		1					44
16172	16130				02.13.01.01.00																			Mechanical																																																				Ottawa			R&D								1					44		R&D

## Resources
tbResID	tbResResourceCalendar	tbResQuantity	tbResPayRate	tbResExtSystemResID	tbResName	tbResPrimaryRole	tbResPrimarySkill	tbResNameShort	tbResLabourType	tbResPercentGeneralAvailability	tbResEmail	tbResDepartment	tbResManager	tbResTeam	tbResLocation	tbResTeamLeader	tbResSupervisor	tbResPartTimeFullTime	tbResResourceType	tbResResourceClass	tbResCostCode	tbResCustomerID	tbResSortOrder	tbResLastModified	tbResPasswordHash	tbResPIN	tbResEmail2	tbResFirstName	tbResLastName	tbResMiddleName	tbResStreet	tbResCity	tbResStateProvince	tbResZipPostalCode	tbResPhoneNo	tbResPhoneNo2	tbResCellPhoneNo	tbResCountry	tbResCompany	tbResBirthday	tbResLanguage	tbResSocialLinks	tbResCourse	tbResCourseFinishDate	tbResPhoto	tbResPOBoxNo	tbResAptNo	tbResPostalStation	tbResOccupation	tbResSignature	tbResCertNo	tbResStatus	tbResState	tbResStage	tbResStep	tbResStepNotes	tbResOffice	tbResTransDate	tbResStartDate	tbResTermDate	tbResRemarks
Resources					Import Data	Primary Role / Format	Primary Skill		Labour Type			Resource Department	Manager		Location	Team Leader	Supervisor	Parttime Fulltime	Resource Type	Resource Class
ResID	Calendar	Qty Resources	Pay Rate	ExtResID	Name	Primary Role *	Primary Skill *	Name Short	Labour Type	Default Percent Available	Res Email	Res Department	Res Manager	Team	Res Location	Team Leader	Res Supervisor	Part or Full Time	Res Type	Res Class	Cost Code	CustID	Sort Order	Last Modified	Password Hash	PIN	tbResEmail2	tbResFirstName	tbResLastName	tbResMiddleName	tbResStreet	tbResCity	tbResStateProvince	tbResZipPostalCode	tbResPhoneNo	tbResPhoneNo2	tbResCellPhoneNo	tbResCountry	tbResCompany	tbResBirthday	tbResLanguage	tbResSocialLinks	tbResCourse	tbResCourseFinishDate	tbResPhoto	tbResPOBoxNo	tbResAptNo	tbResPostalStation	tbResOccupation	tbResSignature	tbResCertNo	tbResStatus	tbResState	tbResStage	tbResStep	tbResStepNotes	tbResOffice	tbResTransDate	tbResStartDate	tbResTermDate	tbResRemarks
700	8	1	50		Joe Invent	R&D	Testing	JI	Human	50	joe@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A404	44	1	05-Jun-2024	111111	111111	null	null	null	null	null	null	null	null
701	8	1	50		Ally HR	HR SME	IT Architecture	AH	Human	50	ally@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A405	44	2	05-Jun-2024	111111	111111
702	8	1	50		Julia Finance	Finance SME	Procurement	JF	Human	50	julia@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A406	44	3	05-Jun-2024	111111	111111
717	8	1	75		Ryan Tower	Engineer	Testing	RT	Human	25	ryan@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A411	44	18	05-Jun-2024	111111	111111
719	8	1	50		Chris Java	Developer	IT Architecture	CJ	Human	25	chris@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111
720	8	1	50		John Test	Tester	Hardware/Software Testing	JT	Human	25	john@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111
800	8	40	100		General	Catch All Role	Catch All Skill	Catchall	Generic	50									Labour		A411	44	22	07/11/2018	111111	111111
801	8	10	100		R&D	R&D		R&D	Generic	50									Labour		A411	44	22	07/11/2018	111111	111111
802	8	11	50		HR SME	HR SME		HR SME	Generic	50									Labour		A411	44	23	07/11/2018	111111	111111
803	8	12	75		Finance SME	Finance SME		Finance SME	Generic	50									Labour		A411	44	24	07/11/2018	111111	111111
804	8	13	100		Engineer	Engineer		Engineer	Generic	50									Labour		A411	44	25	07/11/2018	111111	111111
805	8	14	50		Developer	Developer		Developer	Generic	50									Labour		A411	44	26	07/11/2018	111111	111111
806	8	15	75		Tester	Tester		Tester	Generic	50									Labour		A411	44	27	07/11/2018	111111	111111

## Tags
tbTagID	tbTagGroup	tbTagName	tbTagSortOrder	tbTagOpFieldName	tbTagOpInternalName	tbTagTbInternalName	tbTagOpTagName	tbTagOpCustomOptionID	tbTagEntity	tbTagPopular	tbTagNameShort	tbTagPurpose	tbTagDescription	tbTagOwner	tbTagCustomerID	tbTagLastModified
Tags Data Store														Do not change
tbTagID	Picklist Name	Tag Name	Priority Order	OP Field Name	OP Internal Name	Tb Internal Name	OP Tag Name	OP Custom Option ID	tbTagEntity	tbTagPopular	tbTagNameShort	tbTagPurpose	tbTagDescription	tbTagOwner	tbTagCustomerID	tbTagLastModified
1	Business Advisor	Advisor 1	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 1	48	ProjList		Mike Ba	Project Tagging	NA	PMO		1-Nov-22
2	Business Advisor	Advisor 2	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 2	49	ProjList		Joe Ba	Project Tagging	NA	PMO		1-Nov-22
3	Business Advisor	Advisor 3	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 3	50	ProjList		Sally Ba	Project Tagging	NA	PMO		1-Nov-22
4	Business Advisor	Advisor 4	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 4	51	ProjList		Joe Ba	Project Tagging	NA	PMO		1-Nov-22
5	Business Advisor	Advisor 5	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 5	52	ProjList		Sally Ba	Project Tagging	NA	PMO		1-Nov-22
6	Calendar	4	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		4	For calculating wok on an Allocation	NA	PMO		1-Nov-22
7	Calendar	7.5	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		7.5	For calculating wok on an Allocation	NA	PMO		1-Nov-22
8	Calendar	8	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		8	For calculating wok on an Allocation	NA	PMO		1-Nov-22
9	Calendar	24	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		24	For calculating wok on an Allocation	NA	PMO		1-Nov-22
10	Category	Internal	1						General	General	Internal	for tagging a time bar category at all levels	NA
11	Category	External	2						General	General	External	for tagging a time bar category at all levels	NA
12	Category	Systems	3						General	General	Systems	for tagging a time bar category at all levels	NA
13	Category	Services	4						General	General	Services	for tagging a time bar category at all levels	NA
14	Cost Code	A26	1			tbResCostCode			ResList		A26	Resource or person tagging	NA	PMO		1-Nov-22
15	Cost Code	B44	2						ResList		B44	Resource or person tagging	NA	PMO		1-Nov-22
16	Cost Code	C99	3						ResList		C99	Resource or person tagging	NA	PMO		1-Nov-22
17	Cost Code	D11	4						ResList		D11	Resource or person tagging	NA	PMO		1-Nov-22
18	Cost Code	E11	5						ResList		E11	Resource or person tagging	NA	PMO		1-Nov-22
19	Cost Code	E112	6						ResList		E112	Resource or person tagging	NA	PMO		1-Nov-22
20	Cost Type	Equipment							ProjList		Equipment	Tagging of Project, Sub-Project or Task	NA	PMO
21	Cost Type	Hardware							ProjList		Hardware	Tagging of Project, Sub-Project or Task	NA	PMO
22	Cost Type	Software							ProjList		Software	Tagging of Project, Sub-Project or Task	NA	PMO
23	Delivery Manager	Manager of Engineering	1	Delivery Manager	customField6	tbMDDeliveryManager	Manager of Engineering	12	ProjList		MarioC	Project Tagging	NA	PMO		1-Nov-22
24	Delivery Manager	Manager of Integration	2	Delivery Manager	customField6	tbMDDeliveryManager	Manager of Integration	14	ProjList		SallyE	Project Tagging	NA	PMO		1-Nov-22
25	Delivery Manager	Manager of IT	2	Delivery Manager	customField6	tbMDDeliveryManager	Manager of IT	13	ProjList		SallyE	Project Tagging	NA	PMO		1-Nov-22
26	Department	Sales and Marketing	1	Department	customField5	tbMDDepartment	Sales and Marketing	5	ProjList		Marketing	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
27	Department	Engineering	2	Department	customField5	tbMDDepartment	Engineering	6	ProjList		Engineering	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
28	Department	Manufacturing	3	Department	customField5	tbMDDepartment	Manufacturing	7	ProjList		MFG	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
29	Department	Procurement	4	Department	customField5	tbMDDepartment	Procurement	8	ProjList		Purch	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
30	Department	Business Development	5	Department	customField5	tbMDDepartment	Business Development	9	ProjList		BD	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
31	Department	Research and Development	6	Department	customField5	tbMDDepartment	Research and Development	10	ProjList		R&D	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
32	Document Purpose	Approval Document	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
33	Document Purpose	Business Case	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
34	Document Purpose	Common Help	0						General		NA	Key for pages appearing on help accordions	NA	PMO		1-Nov-22
35	Document Purpose	Contact Us Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
36	Document Purpose	Gate Help	0						General		NA	Key for the Help pages on Gating forms	NA	System		1-Nov-22
37	Document Purpose	General Web Page	0						General		NA	To identify web pages	NA	PMO		1-Nov-22
38	Document Purpose	Kanban Help	0						General		NA	Key for pages appearing on help accordions	NA	PMO		1-Nov-22
39	Document Purpose	Main Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
40	Document Purpose	Marketing Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
41	Document Purpose	Project Charter	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
42	Document Purpose	Timebar Help	0						General		NA	Key for pages appearing on help accordions	NA	System		1-Nov-22
43	Document Status	Approved	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
44	Document Status	Canceled	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
45	Document Status	First Draft	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
46	Document Status	In Progress	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
47	Document Type	HTML	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
48	Document Type	MS Word	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
49	Document Type	PDF	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
50	Escalation Level	Executives	2			tbMDEscalationLevel	Executives		General		Executives		NA	PMO		1-Nov-22
51	Escalation Level	Directors	3			tbMDEscalationLevel	Directors		General		Directors		NA	PMO		1-Nov-22
52	Escalation Level	Project Office	4			tbMDEscalationLevel	Project Office		General		Project Office		NA	PMO		1-Nov-22
53	Escalation Level	Not Assessed	5			tbMDEscalationLevel	Not Assessed		General		Not Assessed		NA	PMO		1-Nov-22
54	Estimation Class	Class A	0	Estimation Class	customField18	tbMDEstimationClass	Class A	53	ProjList		Class A	Project Tagging	NA	PMO		1-Nov-22
55	Estimation Class	Class B	0	Estimation Class	customField18	tbMDEstimationClass	Class B	54	ProjList		Class B	Project Tagging	NA	PMO		1-Nov-22
56	Estimation Class	Class C	0	Estimation Class	customField18	tbMDEstimationClass	Class C	55	ProjList		Class C	Project Tagging	NA	PMO		1-Nov-22
57	Executive Sponsor	Sally Exec	0						ProjList		Exec Sponsor	Project Tagging	NA	PMO		1-Nov-22
58	ExpectedHoursPerWeek	5	0						ResList		5	Use for estimating work needs	NA	PMO		1-Nov-22
59	ExpectedHoursPerWeek	10	0						ResList		10	Use for estimating work needs	NA	PMO		1-Nov-22
60	ExtSystemResID	456M23	0						ResList		456M23	Use to tie into exsiting systems in the organization	NA	PMO		1-Nov-22
61	ExtSystemResID	456M24	0						ResList		456M24	Use to tie into exsiting systems in the organization	NA	PMO		1-Nov-22
62	Field Name	tbMDID	79						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
63	Field Name	tbMDName	80						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
64	Field Name	tbMDProjectType	81						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
65	Field Name	tbMDPortfolio	82						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
66	Field Name	tbMDProgram	83						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
67	Field Name	tbMDExecutiveSummary	84						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
68	Field Name	tbMDGate	85						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
69	Field Name	tbMDDeliveryManager	86						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
70	Field Name	tbMDBusinessAdvisor	87						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
71	Field Name	tbMDBusinessOwner	88						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
72	Field Name	tbMDEstimationClass	89						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
73	Field Name	tbMDROMEstimate	90						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
74	Field Name	tbMDInvestmentCategory	91						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
75	Field Name	tbMDInvestmentInitiative	92						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
76	Field Name	tbMDInvestmentObjective	93						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
77	Field Name	tbMDInvestmentStrategy	94						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
78	Field Name	tbMDPriorityStrategic	95						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
79	Field Name	tbMDCustomerID	96						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
80	Field Name	tbMDAzureID	97						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
81	Field Name	tbMDNameShort	98						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
82	Field Name	tbMDProjectNumber	99						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
83	Field Name	tbMDDescription	100						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
84	Field Name	tbMDNotes	101						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
85	Field Name	tbMDExtLink1	102						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
86	Field Name	tbMDExtSystemID1	103						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
87	Field Name	tbMDSortOrder	104						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
88	Field Name	tbMDtbLastModified	105						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
89	Field Name	tbMDPriority	106						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
90	Field Name	tbMDStatus	107						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
91	Field Name	tbMDState	108						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
92	Field Name	tbMDSeverity	109						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
93	Field Name	tbMDStage	110						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
94	Field Name	tbMDPhase	111						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
95	Field Name	tbMDCategory	112						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
96	Field Name	tbMDHealth	113						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
97	Field Name	tbMDResponsibility	114						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
98	Field Name	tbMDDepartment	115						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
99	Field Name	tbMDExSponsor	116						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
100	Field Name	tbMDPM	117						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
101	Field Name	tbMDShowIn	118						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
102	Field Name	tbMDYesNoSelector	119						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
103	Field Name	tbMDProduct	120						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
104	Field Name	tbMDContact	121						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
105	Field Name	tbMDWBS	122						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
106	Field Name	tbMDWeighting	123						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
107	Field Name	tbMDLocation	124						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
108	Field Name	tbMDPrimarySkill	125						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
109	Field Name	tbMDPrimaryRole	126						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
110	Field Name	tbMDOther2	127						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
111	Field Name	tbMDOther3	128						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
112	Field Name	tbMDOther4	129						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
113	Field Name	canvasNo	130						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
114	Field Name	tbMDProgActivityAlignment	131						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
115	Field Name	tbMDBackgroundInfo	132						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
116	Field Name	tbMDConsequence	133						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
117	Field Name	tbMDExpectedBenefits	134						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
118	Field Name	tbMDProblemOpportunity	135						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
119	Field Name	tbMDCapabilitiesNeeded	136						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
120	Field Name	tbMDSeniorLevelCommittment	137						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
121	Field Name	tbMDSprintName	138						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
122	Field Name	tbMDStakeholderDescription	139						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
123	Field Name	tbMDHealthCost	140						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
124	Field Name	tbMDHealthHours	141						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
125	Field Name	tbMDHealthIssues	142						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
126	Field Name	tbMDHealthOverall	143						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
127	Field Name	tbMDHealthRisk	144						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
128	Field Name	tbMDHealthSchedule	145						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
129	Field Name	tbMDHealthScope	146						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
130	Field Name	tbMDBenefitCostRatio	147						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
131	Field Name	tbMDConstraintsAssumptions	148						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
132	Field Name	tbMDContractNumber	149						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
133	Field Name	tbMDCostBenefitAnalysis	150						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
134	Field Name	tbMDEcnomicValueAdded	151						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
135	Field Name	tbMDInternalRateOfReturn	152						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
136	Field Name	tbMDNetPresentValue	153						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
137	Field Name	tbMDOpportunityCost	154						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
138	Field Name	tbMDOrgManager	155						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
139	Field Name	tbMDPaybackPeriod	156						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
140	Field Name	tbMDRiskVsSizeAndComplexity	157						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
141	Field Name	tbMDSize	158						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
142	Field Name	tbMDStageApprover	159						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
143	Field Name	tbMDSunkCosts	160						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
144	Field Name	tbMDWrittenBy	161						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
145	Field Name	tbMDPrimaryLineOfBusiness	162						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
146	Field Name	tbMDNotesWorkflow	163						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
147	Field Name	tbMDSyncNotes	164						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
148	Field Name	tbMDSponsoringDepartment	165						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
149	Field Name	tbMDPrimaryContact	166						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
150	Field Name	tbMDContactNumber	167						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
151	Field Name	tbMDResponsibleTeam	168						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
152	Field Name	tbMDNotesProject	169						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
153	Field Name	tbMDOther5	170						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
154	Field Name	tbMDOther6	171						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
155	Field Name	tbMDOther7	172						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
156	Field Name	tbMDOther8	173						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
157	Field Name	tbMDOther9	174						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
158	Field Name	tbMDOther10	175						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
159	Field Name	tbMDOther11	176						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
160	Field Name	tbMDOther12	177						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
161	Field Name	tbMDRefID	178						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
162	Field Name	tbID	179						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
163	Field Name	tbSelfKey2	180						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
164	Field Name	tbCoordTop	181						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
165	Field Name	tbCoordLeft	182						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
166	Field Name	tbHierarchyOrder	183						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
167	Field Name	tbName	184						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
168	Field Name	tbType	185						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
169	Field Name	tbL1	186						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
170	Field Name	tbL2	187						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
171	Field Name	tbL3	188						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
172	Field Name	tbL4	189						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
173	Field Name	tbL5	190						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
174	Field Name	tbOwner	191						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
175	Field Name	tbStart	192						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
176	Field Name	tbFinish	193						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
177	Field Name	tbDuration	194						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
178	Field Name	tbAStart	195						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
179	Field Name	tbAFinish	196						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
180	Field Name	tbRemainingDuration	197						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
181	Field Name	tbResID	198						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
182	Field Name	tbCalendar	199						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
183	Field Name	tbPercentTimeOn	200						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
184	Field Name	tbWork	201						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
185	Field Name	tbAWork	202						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
186	Field Name	tbWorkRemaining	203						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
187	Field Name	tbPercentComplete	204						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
188	Field Name	tbCost	205						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
189	Field Name	tbAcost	206						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
190	Field Name	tbCostRemaining	207						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
191	Field Name	tbPayRate	208						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
192	Field Name	tbCostType	209						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
193	Field Name	tbCostID	210						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
194	Field Name	tbConstraintType	211						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
195	Field Name	tbConstraintDate	212						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
196	Field Name	tbFloat	213						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
197	Field Name	tbFreeFloat	214						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
198	Field Name	tbExpHoursPerWeek	215						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
199	Field Name	canvasNo	216						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
200	Field Name	tbCustomerID	217						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
201	Field Name	tbMetaDataID	218						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
202	Field Name	tbBLID	219						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
203	Field Name	tbPredecessor	220						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
204	Field Name	tbAzureID	221						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
205	Field Name	tbCoordRight	222						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
206	Field Name	tbBarColor	223						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
207	Field Name	tbTextColor	224						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
208	Field Name	kbCoordLeft	225						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
209	Field Name	kbCoordTop	226						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
210	Field Name	focdItemCoordLeft	227						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
211	Field Name	focdItemCoordTop	228						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
212	Field Name	tbDocID	229						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
213	Field Name	tbDocName	230						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
214	Field Name	tbDocNameShort	231						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
215	Field Name	tbDocStatus	232						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
216	Field Name	tbDocPurpose	233						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
217	Field Name	tbDocWrittenBy	234						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
218	Field Name	tbDocBriefDescription	235						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
219	Field Name	tbDocCustomerID	236						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
220	Field Name	tbDocType	237						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
221	Field Name	tbDocHTMLContent	238						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
222	Field Name	tbDocGroup	239						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
223	Field Name	tbDocOwner	240						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
224	Field Name	tbDocPopular	241						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
225	Field Name	tbDocSortOrder	242						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
226	Field Name	tbDocLastModified	243						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
227	Field Name	tbDocApprovedBy	244						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
228	Field Name	tbDocL1	245						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
229	Field Name	tbDocL2	246						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
230	Field Name	tbDocL3	247						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
231	Field Name	tbDocL4	248						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
232	Field Name	tbDocL5	249						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
233	Field Name	tbDocCardImage	250						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
234	Field Name	tbResID	251						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
235	Field Name	tbResName	252						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
236	Field Name	tbResNameShort	253						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
237	Field Name	tbResPrimarySkill	254						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
238	Field Name	tbResPrimaryRole	255						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
239	Field Name	tbResDepartment	256						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
240	Field Name	tbResManager	257						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
241	Field Name	tbResPayRate	258						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
242	Field Name	tbResTeam	259						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
243	Field Name	tbResLocation	260						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
244	Field Name	tbResTeamLeader	261						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
245	Field Name	tbResSupervisor	262						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
246	Field Name	tbResPartTimeFullTime	263						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
247	Field Name	tbResResourceType	264						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
248	Field Name	tbResResourceClass	265						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
249	Field Name	tbResResourceCalendar	266						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
250	Field Name	tbResPercentGeneralAvailability	267						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
251	Field Name	tbResCostCode	268						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
252	Field Name	tbResCustomerID	269						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
253	Field Name	tbResExtSystemResID	270						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
254	Field Name	tbResSortOrder	271						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
255	Field Name	tbResLastModified	272						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
256	Field Name	tbResExtSystemResID	273						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
257	Field Name	tbResCoordTop	274						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
258	Field Name	tbResCoordLeft	275						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
259	Field Name	tbResLabourType	276						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
260	Field Name	tbResEmail	277						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
261	Field Name	tbResPasswordHash	278						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
262	Field Name	tbResPIN	279						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
263	Field Name	tbResAzureID	280						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
264	Field State	Disabled	1						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
265	Field State	Editable	2						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
266	Field Type	Editor	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
267	Field Type	NoPicklist	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
268	Field Type	WithPicklist	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
269	Field Type	Band	7						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
270	Form Name	ALLOC1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
271	Form Name	ALLOC2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
272	Form Name	DOC1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
273	Form Name	DOC2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
274	Form Name	other1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
275	Form Name	other2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
276	Form Name	PF1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
277	Form Name	PF2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
278	Form Name	PJ1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
279	Form Name	PJ2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
280	Form Name	PJ3	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
281	Form Name	SPJ1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
282	Form Name	Task1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
283	Form Name	Task2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
284	Gate	1 Approved to Design	0	Gate	customField19	tbMDGate	1 Approved to Design	57	ProjList		1 Approved to Design	Project Tagging	NA	PMO		1-Nov-22
285	Gate	2 Approved to Develop	0	Gate	customField19	tbMDGate	2 Approved to Develop	58	ProjList		2 Approved to Develop	To confirm that the business case is sufficiently compelling to justify, sustain and guide the project; to identify any shortcomings in readiness for action before approval; and to confirm that key identified risks can be managed.	NA	System		1-Nov-22
286	Gate	3 Approved to Implement	0	Gate	customField19	tbMDGate	3 Approved to Implement	59	ProjList		3 Approved to Implement	To ensure that the resources, support and governance necessary for successful execution are in place prior to deployment	NA	System		1-Nov-22
287	Gate	Not Applicable	0	Gate	customField19	tbMDGate	Not Applicable	60	ProjList		Not Applicable	To confirm completion, assess the extent to which the project has achieved its goals, and provide an assessment of value for money.	NA	System		1-Nov-22
288	Health	Attention	0	Health	customField152	tbMDHealth	Attention	222	ProjList		Attention	For Dashboard indicators	NA	PMO		1-Nov-22
289	Health	Blocked	0	Health	customField152	tbMDHealth	Blocked	220	ProjList		Blocked	For Dashboard indicators	NA	PMO		1-Nov-22
290	Health	Completed	0	Health	customField152	tbMDHealth	Completed	221	ProjList		Completed	For Dashboard indicators	NA	PMO		1-Nov-22
291	Health	Early	0	Health	customField152	tbMDHealth	Early	217	ProjList		Early	For Dashboard indicators	NA	PMO		1-Nov-22
292	Health	Late	0	Health	customField152	tbMDHealth	Late	219	ProjList		Late	For Dashboard indicators	NA	PMO		1-Nov-22
293	Health	On schedule	0	Health	customField152	tbMDHealth	On Schedule	216	ProjList		On schedule	For Dashboard indicators	NA	PMO		1-Nov-22
294	Health	Slipping	0	Health	customField152	tbMDHealth	Slipping	218	ProjList		Slipping	For Dashboard indicators	NA	PMO		1-Nov-22
295	Health Cost	Green	1	Health Cost	customField53	tbMDHealthCost	Green	151	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
296	Health Cost	Yellow	2	Health Cost	customField53	tbMDHealthCost	Yellow	152	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
297	Health Cost	Not Assessed	3	Health Cost	customField53	tbMDHealthCost	Not Assessed	194	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
298	Health Cost	Red	3	Health Cost	customField53	tbMDHealthCost	Red	153	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
299	Health Hours	Green	1	Health Hours	customField54	tbMDHealthHours	Green	154	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
300	Health Hours	Yellow	2	Health Hours	customField54	tbMDHealthHours	Yellow	155	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
301	Health Hours	Not Assessed	3	Health Hours	customField54	tbMDHealthHours	Not Assessed	195	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
302	Health Hours	Red	3	Health Hours	customField54	tbMDHealthHours	Red	156	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
303	Health Issues	Green	1	Health Issues	customField55	tbMDHealthIssues	Green	157	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
304	Health Issues	Yellow	2	Health Issues	customField55	tbMDHealthIssues	Yellow	158	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
305	Health Issues	Not Assessed	3	Health Issues	customField55	tbMDHealthIssues	Not Assessed	196	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
306	Health Issues	Red	3	Health Issues	customField55	tbMDHealthIssues	Red	159	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
307	Health Overall	Green	1	Health Overall	customField56	tbMDHealthOverall	Green	160	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
308	Health Overall	Yellow	2	Health Overall	customField56	tbMDHealthOverall	Yellow	161	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
309	Health Overall	Not Assessed	3	Health Overall	customField56	tbMDHealthOverall	Not Assessed	199	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
310	Health Overall	Red	3	Health Overall	customField56	tbMDHealthOverall	Red	162	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
311	Health Risk	Green	1	Health Risk	customField57	tbMDHealthRisk	Green	163	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
312	Health Risk	Yellow	2	Health Risk	customField57	tbMDHealthRisk	Yellow	164	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
313	Health Risk	Not Assessed	3	Health Risk	customField57	tbMDHealthRisk	Not Assessed	215	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
314	Health Risk	Red	3	Health Risk	customField57	tbMDHealthRisk	Red	165	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
315	Health Schedule	Green	1	Health Schedule	customField58	tbMDHealthSchedule	Green	166	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
316	Health Schedule	Yellow	2	Health Schedule	customField58	tbMDHealthSchedule	Yellow	167	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
317	Health Schedule	Not Assessed	3	Health Schedule	customField58	tbMDHealthSchedule	Not Assessed	198	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
318	Health Schedule	Red	3	Health Schedule	customField58	tbMDHealthSchedule	Red	168	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
319	Health Scope	Green	1	Health Scope	customField59	tbMDHealthScope	Green	169	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
320	Health Scope	Yellow	2	Health Scope	customField59	tbMDHealthScope	Yellow	170	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
321	Health Scope	Not Assessed	3	Health Scope	customField59	tbMDHealthScope	Not Assessed	197	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
322	Health Scope	Red	3	Health Scope	customField59	tbMDHealthScope	Red	171	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
323	HyperLinks	Link 1	0						ProjList		Link 1	for manually storing hyperlink to external info.	NA	PMO		1-Nov-22
324	HyperLinks	Link 2	0						ProjList		Link 2	for manually storing hyperlink to external info.	NA	PMO		1-Nov-22
325	Investment Category	Not Assessed	0	Investment Category	customField20	tbMDInvestmentCategory	Not Assessed	67	ProjList		Core Products	Project Tagging	NA	PMO		1-Nov-22
326	Investment Category	Business Systems	10	Investment Category	customField20	tbMDInvestmentCategory	Business Support	63	ProjList		IT Platform	Project Tagging	NA	PMO		1-Nov-22
327	Investment Category	Our Core Products	20	Investment Category	customField20	tbMDInvestmentCategory	Core Products	65	ProjList		Business Support	Project Tagging	NA	PMO		1-Nov-22
328	Investment Category	Productivity Tools	30	Investment Category	customField20	tbMDInvestmentCategory	Engineering Tools	64	ProjList		Office Environment	Project Tagging	NA	PMO		1-Nov-22
329	Investment Category	Innovation	40	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Engineering Tools	Project Tagging	NA	PMO		1-Nov-22
330	Investment Category	Digital Transformation	50	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Engineering Tools	Project Tagging	NA	PMO		1-Nov-22
331	Investment Initiative	Not Assessed	0	Investment Initiative	customField21	tbMDInvestmentInitiative	Support moden digital workplace	73	ProjList		Support moden digital workplace	Project Tagging	NA	PMO		1-Nov-22
332	Investment Initiative	Strengthen Cybersecurity Infrastructure	10	Investment Initiative	customField21	tbMDInvestmentInitiative	Cross-sell our Network Device products	69	ProjList		Cross-sell our Network Device products	Project Tagging	NA	PMO		1-Nov-22
333	Investment Initiative	Build AI/ML Capabilities	20	Investment Initiative	customField21	tbMDInvestmentInitiative	Engineering Tool Innovation	70	ProjList		Engineering Tool Innovation	Project Tagging	NA	PMO		1-Nov-22
334	Investment Initiative	Faster response to new business opportunities	30	Investment Initiative	customField21	tbMDInvestmentInitiative	Faster response to new business opportunities	71	ProjList		Faster response to new business opportunities	Project Tagging	NA	PMO		1-Nov-22
335	Investment Initiative	Improve employee skills	40	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve Employee Skills	74	ProjList		Improve Employee Skills	Project Tagging	NA	PMO		1-Nov-22
336	Investment Initiative	Improve product reliability	50	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve product reliability	68	ProjList		Improve product reliability	Project Tagging	NA	PMO		1-Nov-22
337	Investment Initiative	Improve productivity with Agile Teams	60	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve productivity with Agile Teams	75	ProjList		Improve productivity with Agile Teams	Project Tagging	NA	PMO		1-Nov-22
338	Investment Initiative	Source Cloud services for our Core products	70	Investment Initiative	customField21	tbMDInvestmentInitiative	Source Cloud services for our Core products	72	ProjList		Source Cloud services for our Core products	Project Tagging	NA	PMO		1-Nov-22
339	Investment Initiative	Support moden digital workplace	80	Investment Initiative	customField21	tbMDInvestmentInitiative	Support moden digital workplace	73	ProjList		Support moden digital workplace	Project Tagging	NA	PMO		1-Nov-22
340	Investment Objective	Not Assessed	0	Investment Objective	customField22	tbMDInvestmentObjective	Transform the Business	78	ProjList		Transform the Business	Project Tagging	NA	PMO		1-Nov-22
341	Investment Objective	Grow the Business	10	Investment Objective	customField22	tbMDInvestmentObjective	Grow the Business	77	ProjList		Grow the Business	Project Tagging	NA	PMO		1-Nov-22
342	Investment Objective	Run the Business	20	Investment Objective	customField22	tbMDInvestmentObjective	Run the Business	76	ProjList		Run the Business	Project Tagging	NA	PMO		1-Nov-22
343	Investment Objective	Modernize the Business	20	Investment Objective	customField22	tbMDInvestmentObjective	Run the Business	76	ProjList		Run the Business	Project Tagging	NA	PMO		1-Nov-22
344	Investment Objective	Transform the Business	30	Investment Objective	customField22	tbMDInvestmentObjective	Transform the Business	78	ProjList		Transform the Business	Project Tagging	NA	PMO		1-Nov-22
345	Investment Strategy	Not Assessed	0	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Tagging	NA	PMO		1-Nov-22
346	Investment Strategy	Attract and retain the best people	10	Investment Strategy	customField23	tbMDInvestmentStrategy	Attract and retain the best people	84	ProjList		Attract and retain the best people	Project Tagging	NA	PMO		1-Nov-22
347	Investment Strategy	Improve our core products	20	Investment Strategy	customField23	tbMDInvestmentStrategy	Best in market core products	80	ProjList		Best in market core products	Project Tagging	NA	PMO		1-Nov-22
348	Investment Strategy	Ensure compliance	30	Investment Strategy	customField23	tbMDInvestmentStrategy	Ensure compliance	83	ProjList		Ensure compliance	Project Tagging	NA	PMO		1-Nov-22
349	Investment Strategy	Accelerate Time-to-Market	40	Investment Strategy	customField23	tbMDInvestmentStrategy	Improve and maintain workplace safety	85	ProjList		Improve and maintain workplace safety	Project Tagging	NA	PMO		1-Nov-22
350	Investment Strategy	Improve customer service	50	Investment Strategy	customField23	tbMDInvestmentStrategy	Improve customer service	87	ProjList		Improve customer service	Project Tagging	NA	PMO		1-Nov-22
351	Investment Strategy	Build Recurring Revenue Streams	60	Investment Strategy	customField23	tbMDInvestmentStrategy	Increase revenue	81	ProjList		Increase revenue	Project Tagging	NA	PMO		1-Nov-22
352	Investment Strategy	Increase share of market	70	Investment Strategy	customField23	tbMDInvestmentStrategy	Increase share of market	82	ProjList		Increase share of market	Project Tagging	NA	PMO		1-Nov-22
353	Investment Strategy	Reduce waste	80	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Tagging	NA	PMO		1-Nov-22
354	Investment Strategy	Drive Contract Renewals	90	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Tagging	NA	PMO		1-Nov-22
355	Investment Strategy	Server more customers	100	Investment Strategy	customField23	tbMDInvestmentStrategy	Server more customers	79	ProjList		Server more customers	Project Tagging	NA	PMO		1-Nov-22
356	L1	TopLevel	0						ProjList		TopLevel	Can use to make custom hierarchy	NA	System		1-Nov-22
357	L2	Next Level Down	0						ProjList		Next Level Down	Can use to make custom hierarchy	NA	System		1-Nov-22
358	L3	Third Level Down	0						ProjList		Third Level Down	Can use to make custom hierarchy	NA	System		1-Nov-22
359	Labour Type	Generic	0	Labour Type	customfield145	tbResLabourType	Generic	201	ResList		Generic	Resource or person tagging	NA	PMO		1-Nov-22
360	Labour Type	Human	0	Labour Type	customfield145	tbResLabourType	Human	200	ResList		Human	Resource or person tagging	NA	PMO		1-Nov-22
361	Labour Type	Other	0	Labour Type	customfield145	tbResLabourType	Other	202	ResList		Other	Resource or person tagging	NA	PMO		1-Nov-22
362	Location	Edmonton	0	Location	customField15	tbResLocation	Edmonton	44	ResList		Gatineau	Where is resource located	NA	PMO		1-Nov-22
363	Location	Halifax	0	Location	customField15	tbResLocation	Halifax	45	ResList		Gatineau	Where is resource located	NA	PMO		1-Nov-22
364	Location	Ottawa	0	Location	customField15	tbResLocation	Ottawa	43	ResList		Ottawa	Where is resource located	NA	PMO		1-Nov-22
365	Manager	George Bush	0	Manager	customField11	tbResManager	George Bush	30	ResList		Kent Om	Project Tagging	NA	PMO		1-Nov-22
366	Manager	John Cougar	0	Manager	customField11	tbResManager	John Cougar	31	ResList		Perry Om	Project Tagging	NA	PMO		1-Nov-22
367	Manager	Sally Res	0	Manager	customField11	tbResManager	Sally Res	32	ResList		Perry Om	Project Tagging	NA	PMO		1-Nov-22
368	Mitigation Satus	Identified	1			tbMDMitigationStatus	Identified		General		Identified	The risk has been recognized	NA	PMO		1-Nov-22
369	Mitigation Satus	Assessed	2			tbMDMitigationStatus	Assessed		General		Assessed	The risk has been analyzed for its impact and probability	NA	PMO		1-Nov-22
370	Mitigation Satus	Mitigation Planned	3			tbMDMitigationStatus	Mitigation Planned		General		Mitigation Planned	A mitigation strategy has been developed and documented but not yet implemented.	NA	PMO		1-Nov-22
371	Mitigation Satus	In Progress				tbMDMitigationStatus	In Progress		General		In Progress	The mitigation actions are actively being implemented to address the risk.
372	Mitigation Satus	Mitigated				tbMDMitigationStatus	Mitigated		General		Mitigated	The planned mitigation actions have been completed
373	Mitigation Satus	Under Review				tbMDMitigationStatus	Under Review		General		Under Review	The risk and its mitigation are being evaluated to determine if further action is needed.
374	Mitigation Satus	Accepted				tbMDMitigationStatus	Accepted		General		Accepted	The risk is acknowledged but will not be mitigated
375	Mitigation Satus	Transferred				tbMDMitigationStatus	Transferred		General		Transferred	The responsibility of the risk has been assigned to a third party
376	Mitigation Satus	Escalated				tbMDMitigationStatus	Escalated		General		Escalated	The risk has been moved to higher management or another department for resolution due to its complexity or impact level.
377	Mitigation Satus	Closed				tbMDMitigationStatus	Closed		General		Closed	The risk is no longer relevant or has been fully resolved; no further action is required.
378	Mitigation Satus	Deferred				tbMDMitigationStatus	Deferred		General		Deferred	The risk has been identified but will be monitored over time before deciding on mitigation.
379	Non Project Tag	No	0						ProjList		No	Project Tagging	NA	PMO		1-Nov-22
380	Non Project Tag	Yes	0						ProjList		Yes	Project Tagging	NA	PMO		1-Nov-22
381	OOM Estimates	0 to 100K	1	ROM Estimate	customField25	tbMDROMEstimate	0 to 100K	91	ProjList		0 to 100K	Project Tagging	NA	PMO		1-Nov-22
382	OOM Estimates	101K to 300K	2	ROM Estimate	customField25	tbMDROMEstimate	101K to 300K	93	ProjList		101K to 300K	Project Tagging	NA	PMO		1-Nov-22
383	OOM Estimates	301K to 1000K	3	ROM Estimate	customField25	tbMDROMEstimate	301K to 1000K	94	ProjList		301K to 1000K	Project Tagging	NA	PMO		1-Nov-22
384	OOM Estimates	1001K to 5000K	4	ROM Estimate	customField25	tbMDROMEstimate	1001K to 5000K	92	ProjList		1001K to 5000K	Project Tagging	NA	PMO		1-Nov-22
385	OOM Estimates	1000K Plus	5	ROM Estimate	customField25	tbMDROMEstimate	1000K Plus	95	ProjList		1000K Plus	Project Tagging	NA	PMO		1-Nov-22
386	Parttime Fulltime	Full Time	1	Part or Full Time	customField16	tbResPartTimeFullTime	Full Time	46	ResList		Full Time	Resource or person tagging	NA	PMO		1-Nov-22
387	Parttime Fulltime	Part Time	2	Part or Full Time	customField16	tbResPartTimeFullTime	Part Time	47	ResList		Part Time	Resource or person tagging	NA	PMO		1-Nov-22
388	Percent Available	10	0						ResList		10	For taggin an allocation for resource management	NA	PMO		1-Nov-22
389	Percent Available	25	0						ResList		25	For taggin an allocation for resource management	NA	PMO		1-Nov-22
390	Percent Available	50	0						ResList		50	For taggin an allocation for resource management	NA	PMO		1-Nov-22
391	Percent Available	75	0						ResList		75	For taggin an allocation for resource management	NA	PMO		1-Nov-22
392	Percent Available	100	0						ResList		100	For taggin an allocation for resource management	NA	PMO		1-Nov-22
393	PercentTimeAllocated	10	0						ResList		10	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
394	PercentTimeAllocated	25	0						ResList		25	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
395	PercentTimeAllocated	50	0						ResList		50	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
396	PercentTimeAllocated	75	0						ResList		75	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
397	PercentTimeAllocated	100	0						ResList		100	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
398	Phase	Closing	0	Phase	customField26	tbMDPhase	Closing	98	General		Closing	Highlevel Phase of Project or Program	NA	PMO		1-Nov-22
399	Phase	Executing	0	Phase	customField26	tbMDPhase	Executing	97	General		Executing	Highlevel Phase of Project or Program	NA	PMO		1-Nov-22
400	Phase	Initiating	0	Phase	customField26	tbMDPhase	Initiating	96	General		Initiating	Highlevel Phase of Project or Program	NA	PMO		1-Nov-22
401	Phase	Planning	0	Phase	customField26	tbMDPhase	Planning	99	General		Planning	Highlevel Phase of Project or Program	NA	PMO		1-Nov-22
402	Portfolios	Building Services	0	Portfolio	customField27	tbMDPortfolio	Building Services	104	ProjList		Building Services	Project Tagging	NA	PMO		1-Nov-22
403	Portfolios	Business Support Systems	0	Portfolio	customField27	tbMDPortfolio	Business Support Systems	102	ProjList		Business Support Systems	Project Tagging	NA	PMO		1-Nov-22
404	Portfolios	Core Product Delivery	0	Portfolio	customField27	tbMDPortfolio	Core Product Delivery	101	ProjList		Core Product Delivery	Project Tagging	NA	PMO		1-Nov-22
405	Portfolios	IT Platform	0	Portfolio	customField27	tbMDPortfolio	IT Platform	103	ProjList		IT Platform	Project Tagging	NA	PMO		1-Nov-22
406	Portfolios	R&D New Technology	0	Portfolio	customField27	tbMDPortfolio	R&D New Technology	100	ProjList		R&D New Technology	Project Tagging	NA	PMO		1-Nov-22
407	Primary LOB	Business Development	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Business Development	106	ProjList		Research and Development	Project Tagging	NA	PMO		1-Nov-22
408	Primary LOB	Business Technology Solutions	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Business Technology Solutions	108	ProjList		Corporate Affairs	Project Tagging	NA	PMO		1-Nov-22
409	Primary LOB	Corporate Affairs	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Corporate Affairs	107	ProjList		Business Development	Project Tagging	NA	PMO		1-Nov-22
410	Primary LOB	Engineering and Product Delivery	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Engineering and Product Delivery	109	ProjList		Business Technology Solutions	Project Tagging	NA	PMO		1-Nov-22
411	Primary LOB	Human Resources	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Human Resources	110	ProjList		Engineering and Product Delivery	Project Tagging	NA	PMO		1-Nov-22
412	Primary LOB	Research and Development	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Research and Development	105	ProjList		Finance	Project Tagging	NA	PMO		1-Nov-22
413	Primary Role	SME	1	Primary Role	customField12	tbResPrimaryRole	SME	33	ResList		NA	Tag resources for resource demand calculations	NA	system		1-Nov-22
414	Primary Role	Developer Lead	2	Primary Role	customField12	tbResPrimaryRole	Developer Lead	34	ResList		NA	Tag resources for resource demand calculations	NA	system		1-Nov-22
415	Primary Role	Tester	3	Primary Role	customField12	tbResPrimaryRole	Tester	35	ResList		NA	Tag resources for resource demand calculations	NA	system		1-Nov-22
416	Primary Role	Developer	4	Primary Role	customField12	tbResPrimaryRole	Developer	36	ResList		NA	Tag resources for resource demand calculations	NA	system		1-Nov-22
417	Primary Skill	IT Architecture	1	Primary Skill	customField9	tbResPrimarySkill	IT Architecture	22	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
418	Primary Skill	Testing	2	Primary Skill	customField9	tbResPrimarySkill	Testing	23	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
419	Primary Skill	Design	3	Primary Skill	customField9	tbResPrimarySkill	Design	24	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
420	Primary Skill	Project Management	4	Primary Skill	customField9	tbResPrimarySkill	Project Management	25	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
421	Primary Skill	Procurement	5	Primary Skill	customField9	tbResPrimarySkill	Procurement	26	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
422	Product	Access Point	1	Product	customField146	tbMDProduct	Access Point	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
423	Product	Analyzers	2	Product	customField146	tbMDProduct	Analyzers	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
424	Product	Antenna	3	Product	customField146	tbMDProduct	Antenna	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
425	Product	Billing System	4	Product	customField146	tbMDProduct	Billing System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
426	Product	CEP	5	Product	customField146	tbMDProduct	CEP	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
427	Product	DM System	6	Product	customField146	tbMDProduct	DM System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
428	Product	Hot spot	7	Product	customField146	tbMDProduct	Hot spot	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
429	Product	HR System	8	Product	customField146	tbMDProduct	HR System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
430	Product	NA	9	Product	customField146	tbMDProduct	NA	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
431	Product	Network	10	Product	customField146	tbMDProduct	Network	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
432	Product	SAP System	11	Product	customField146	tbMDProduct	SAP System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
433	Product	Secure Cloud System	12	Product	customField146	tbMDProduct	Secure Cloud System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
434	Product	Security System	13	Product	customField146	tbMDProduct	Security System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
435	Product	Ticketing system	14	Product	customField146	tbMDProduct	Ticketing system	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
436	Product	Tools	15	Product	customField146	tbMDProduct	Tools	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
437	Product	VNS System	16	Product	customField146	tbMDProduct	VNS System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
438	Product	WIFI	17	Product	customField146	tbMDProduct	WIFI	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
439	Program Activity Alignment (PAA)	1 1 1 1 Sub-Sub-Program: Banks support of One-Benefit distribution	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
440	Program Activity Alignment (PAA)	1 1 1 2 Sub-Sub-Program: Tax System changes to suit new One-Benefit.	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
441	Program Activity Alignment (PAA)	1 1 1 Sub-Program: One Canada wide monthly payment to each Canadian	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
442	Program Activity Alignment (PAA)	1 1 Program: Common One-Benefit service for all Canadians	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
443	Programs	Building and Office Modernization	0						ProjList		Building and Office Modernization	Project Tagging	NA	PMO		1-Nov-22
444	Programs	Business Continuity Management Program	0						ProjList		Business Continuity Management Program	Project Tagging	NA	PMO		1-Nov-22
445	Programs	Centralized Billing and Receivables	0						ProjList		Centralized Billing and Receivables	Project Tagging	NA	PMO		1-Nov-22
446	Programs	Continuous Improvement Transformation	0						ProjList		Continuous Improvement Transformation	Project Tagging	NA	PMO		1-Nov-22
447	Programs	Continuous Internal Delivery Enablement	0						ProjList		Continuous Internal Delivery Enablement	Project Tagging	NA	PMO		1-Nov-22
448	Programs	Core Operations Program	0						ProjList		Core Operations Program	Project Tagging	NA	PMO		1-Nov-22
449	Programs	Digital Workplace - Transformation	0						ProjList		Digital Workplace - Transformation	Project Tagging	NA	PMO		1-Nov-22
450	Programs	ERP Transformation	0						ProjList		ERP Transformation	Project Tagging	NA	PMO		1-Nov-22
451	Programs	HR Service Delivery	0						ProjList		HR Service Delivery	Project Tagging	NA	PMO		1-Nov-22
452	Programs	IM Policy and Guidelines	0						ProjList		IM Policy and Guidelines	Project Tagging	NA	PMO		1-Nov-22
453	Programs	Information Solutions Resiliency	0						ProjList		Information Solutions Resiliency	Project Tagging	NA	PMO		1-Nov-22
454	Programs	Infrastructure as a Service (IaaS) Program	0						ProjList		Infrastructure as a Service (IaaS) Program	Project Tagging	NA	PMO		1-Nov-22
455	Programs	Integration API Development Program	0						ProjList		Integration API Development Program	Project Tagging	NA	PMO		1-Nov-22
456	Programs	Market Information Management	0						ProjList		Market Information Management	Project Tagging	NA	PMO		1-Nov-22
457	Programs	NA	0						ProjList		NA	Project Tagging	NA	PMO		1-Nov-22
458	Programs	SAP System Upgrade	0						ProjList		SAP System Upgrade	Project Tagging	NA	PMO		1-Nov-22
459	Programs	SharePoint 2016 Upgrade	0						ProjList		SharePoint 2016 Upgrade	Project Tagging	NA	PMO		1-Nov-22
460	Programs	Standalone Project with No Program	0						ProjList		Standalone Project with No Program	Project Tagging	NA	PMO		1-Nov-22
461	Programs	TBS Compliance	0						ProjList		TBS Compliance	Project Tagging	NA	PMO		1-Nov-22
462	Programs	Ticketing System and Requirements Management	0						ProjList		Ticketing System and Requirements Management	Project Tagging	NA	PMO		1-Nov-22
463	Project Status	at_risk	0	status	status	tbStatus	at_risk	at_risk	ProjList		On-Hold	Project Tagging	NA	PMO		1-Nov-22
464	Project Status	off_track	0	status	status	tbStatus	off_track	off_track	ProjList		Canceled	Project Tagging	NA	PMO		1-Nov-22
465	Project Status	on_track	0	status	status	tbStatus	on_track	on_track	ProjList		Active	Project Tagging	NA	PMO		1-Nov-22
466	Project Status	discontinued		status	status	tbStatus	discontinued	discontinued	ProjList
467	Project Status	finished		status	status	tbStatus	finished	finished	ProjList
468	Project Status	not_started		status	status	tbStatus	not_started	not_started	ProjList
469	RandIStage	1 Proposed	1						ProjList		Proposed	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
470	RandIStage	2 Triaged	2						ProjList		Triaged	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
471	RandIStage	3 Prioritized	3						ProjList		Prioritized	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
472	RandIStage	4 Assigned	4						ProjList		Assigned	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
473	RandIStage	5 Solving	5						ProjList		Solving	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
474	RandIStage	6 Mitigating	6						ProjList		Mitigation	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
475	RandIStage	7 Closed	7						ProjList		Closed	Controlling Risk and Issue lifecycle workflow	NA	PMO		1-Nov-22
476	RandIState	Active	1						ProjList		Active	Workflow Lifecycle tag	NA	PMO		1-Nov-22
477	RandIState	On Hold	2						ProjList		On Hold	Workflow Lifecycle tag	NA	PMO		1-Nov-22
478	RandIState	Completed	3						ProjList		Completed	Workflow Lifecycle tag	NA	PMO		1-Nov-22
479	RandIState	Canceled	3						ProjList		Canceled	Workflow Lifecycle tag	NA	PMO		1-Nov-22
480	RandIStatus	Managing	1						General		Managing	Timebar Task, Issue, Risk Status.	NA	PMO		1-Nov-22
481	RandIStatus	Concerned	2						General		Concerned	Timebar Task, Issue, Risk Status.	NA	PMO		1-Nov-22
482	RandIStatus	Critical	3						General		Critical	Timebar Task, Issue, Risk Status.	NA	PMO		1-Nov-22
483	RandIStatus	Completed	3						General		Completed	Timebar Task, Issue, Risk Status.	NA	PMO		1-Nov-22
484	Resource Class	External	0	Class	customField10	tbResResourceClass	External	27	ResList		Contractor	Resource or person tagging	NA	PMO		1-Nov-22
485	Resource Class	Permenant	0	Class	customField10	tbResResourceClass	Permenant	28	ResList		Perm	Resource or person tagging	NA	PMO		1-Nov-22
486	Resource Class	Seasonal	0	Class	customField10	tbResResourceClass	Seasonal	29	ResList		Seasonal	Resource or person tagging	NA	PMO		1-Nov-22
487	Resource Department	Mechanical	1	Department	customField148	tbResDepartment	Mechanical	206	ResList	ResList	Mechanical		NA	PMO		1-Nov-22
488	Resource Department	Electrical	2	Department	customField148	tbResDepartment	Electrical	207	ResList	ResList	Electrical		NA	PMO		1-Nov-22
489	Resource Department	Delivery	3	Department	customField148	tbResDepartment	Delivery	208	ResList	ResList	Delivery		NA	PMO		1-Nov-22
490	Resource Type	Equipment	0	Resource Type	customfield150	tbResResourceType	Equipment	213	ResList		Other	Resource or person tagging	NA	PMO		1-Nov-22
491	Resource Type	Labour	0	Resource Type	customfield150	tbResResourceType	Labour	212	ResList		Generic	Resource or person tagging	NA	PMO		1-Nov-22
492	Resource Type	Material	0	Resource Type	customfield150	tbResResourceType	Material	214	ResList		Material	Resource or person tagging	NA	PMO		1-Nov-22
493	Responsible Person	from tbResources table	0	Op Iinternal user field	responsible	tbMDResponsibility			General		Jim	Define who is responsible for Timebar when in trouble	NA	PMO		1-Nov-22
494	Responsible Team	Product Engineering	1	Responsible Team	customField33	tbMDResponsibleTeam	Product Engineering	117	ProjList		Ateam	Project Tagging	NA	PMO		1-Nov-22
495	Responsible Team	Information Technology	2	Responsible Team	customField33	tbMDResponsibleTeam	Information Technology	118	ProjList		Bteam	Project Tagging	NA	PMO		1-Nov-22
496	Responsible Team	Accounting	3	Responsible Team	customField33	tbMDResponsibleTeam	Accounting	119	ProjList		Cteam	Project Tagging	NA	PMO		1-Nov-22
497	Responsible Team	Finance	4	Responsible Team	customField33	tbMDResponsibleTeam	Finance	120	ProjList		Dteam	Project Tagging	NA	PMO		1-Nov-22
498	Responsible Team	Procurement	5	Responsible Team	customField33	tbMDResponsibleTeam	Procurement	121	ProjList		Fteam	Project Tagging	NA	PMO		1-Nov-22
499	Risk Impact	High	1			tbMDImpact	High		General		High		NA	PMO		1-Nov-22
500	Risk Impact	Medium	2			tbMDImpact	Medium		General		Medium		NA	PMO		1-Nov-22
501	Risk Impact	Low	3			tbMDImpact	Low		General		Low		NA	PMO		1-Nov-22
502	Risk Impact	Very Low	4			tbMDImpact	Normal		General		Very Low		NA	PMO		1-Nov-22
503	Risk Impact	Not Assessed	5			tbMDImpact	Not Assessed		General		Not Assessed		NA	PMO		1-Nov-22
504	Risk Probability	High	1			tbMDProbability	High		General		High		NA	PMO		1-Nov-22
505	Risk Probability	Immediate	2			tbMDProbability	Intermediate		General		Intermediate		NA	PMO		1-Nov-22
506	Risk Probability	Low	3			tbMDProbability	Low		General		Low		NA	PMO		1-Nov-22
507	Risk Probability	Normal	4			tbMDProbability	Normal		General		Normal		NA	PMO		1-Nov-22
508	Risk Probability	Not Assessed	5			tbMDProbability	Not Assessed		General		Not Assessed		NA	PMO		1-Nov-22
509	Risk Vs Size	1	1						ProjList		Small, Not Complex	Supports bubble charts	NA	PMO		1-Nov-22
510	Risk Vs Size	2	2						ProjList		Medium, Not Complex	Supports bubble charts	NA	PMO		1-Nov-22
511	Risk Vs Size	3	3						ProjList		Large, Not Complex	Supports bubble charts	NA	PMO		1-Nov-22
512	Risk Vs Size	4	4						ProjList		Small/Medium Complex	Supports bubble charts	NA	PMO		1-Nov-22
513	Risk Vs Size	5	5						ProjList		Large and Complex	Supports bubble charts	NA	PMO		1-Nov-22
514	Selected	Yes	0	Yes		tbMDSelectedYesNo	Yes	17	ProjList	General	Yes	For PPM Selected yn indicators	NA	PMO		1-Nov-22
515	Selected	No	0	No		tbMDSelectedYesNo	No	17	ProjList	General	No	For PPM Selected yn indicators	NA	PMO		1-Nov-22
516	Selected	Not Assessed	0	Not Assessed		tbMDSelectedYesNo	Not Assessed	17	ProjList	General	Not Assessed	For PPM Selected yn indicators	NA	PMO		1-Nov-22
517	Severity	Critical	0						General		1	Indicates how severe a priority itme is, in terms of impact	NA	PMO		1-Nov-22
518	Severity	Important	0						General		2	Indicates how severe a priority itme is, in terms of impact	NA	PMO		1-Nov-22
519	Severity	Normal	0						General		3	Indicates how severe a priority itme is, in terms of impact	NA	PMO		1-Nov-22
520	Show In Reports	Executive Dashboard	0	Show In	customField34	tbMDShowIn	Executive Dashboard	122	ProjList		Executive Dashboard	Project Tagging	NA	PMO		1-Nov-22
521	Show In Reports	PM Dashboard	0	Show In	customField34	tbMDShowIn	PM Dashboard	123	ProjList		PM Dashboard	Project Tagging	NA	PMO		1-Nov-22
522	Show In Reports	Project Sites	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList		Project Sites	Project Tagging	NA	PMO		1-Nov-22
523	Size	Small	1						ProjList		Small	Project Tagging	NA	PMO		1-Nov-22
524	Size	Medium	2						ProjList		Medium	Project Tagging	NA	PMO		1-Nov-22
525	Size	Large	3						ProjList		Large	Project Tagging	NA	PMO		1-Nov-22
526	Size	Release	4						ProjList		Release	Project Tagging	NA	PMO		1-Nov-22
527	Sponsoring Department	Customer Support Department	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Customer Support Department	125	ProjList		IT Department	Project Tagging	NA	PMO		1-Nov-22
528	Sponsoring Department	IT Department	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	IT Department	127	ProjList		Presidents Office	Project Tagging	NA	PMO		1-Nov-22
529	Sponsoring Department	Presidents Office	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Presidents Office	126	ProjList		Customer Support Department	Project Tagging	NA	PMO		1-Nov-22
530	Stage	1 Proposed	0	Stage	customField37	tbMDStage	1 Proposed	132	ProjList	ProjList	Proposed	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
531	Stage	2 Triaged	0	Stage	customField37	tbMDStage	2 Triaged	133	ProjList	ProjList	Triaged	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
532	Stage	3 Prioritized	0	Stage	customField37	tbMDStage	3 Prioritized	134	ProjList	ProjList	Prioritized	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
533	Stage	4 Selected	0	Stage	customField37	tbMDStage	4 Selected	135	ProjList	ProjList	Selected	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
534	Stage	5 Assigned	0	Stage	customField37	tbMDStage	5 Assigned	136	ProjList	ProjList	Assigned	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
535	Stage	6 Delivering	0	Stage	customField37	tbMDStage	6 Delivering	137	ProjList	ProjList	Delivering	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
536	Stage	7 Delivered	0	Stage	customField37	tbMDStage	7 Delivered	138	ProjList	ProjList	Delivered	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
537	Stage	8 Closed	0	Stage	customField37	tbMDStage	8 Closed	139	ProjList	ProjList	Closed	Controlling project lifecycle workflow	NA	PMO		1-Nov-22
538	stdTasks	Design	0						StdTasks	StdTasks	Design	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
539	stdTasks	Develop	0						StdTasks	StdTasks	Dev	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
540	stdTasks	Project Finish	0						StdTasks	StdTasks	Finish	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
541	stdTasks	Project Start	0						StdTasks	StdTasks	Start	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
542	stdTasks	Test	0						StdTasks	StdTasks	Test	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
543	stdTasks	UAT	0						StdTasks	StdTasks	UAT	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
544	Strategic Priority	High	0	Priority Strategic	customField30	tbMDPriorityStrategic	High	111	ProjList		Improve intiitative visibility	Project Tagging	NA	PMO		1-Nov-22
545	Strategic Priority	Low	0	Priority Strategic	customField30	tbMDPriorityStrategic	Low	113	ProjList		Fewer meetings	Project Tagging	NA	PMO		1-Nov-22
546	Strategic Priority	Medium	0	Priority Strategic	customField30	tbMDPriorityStrategic	Medium	112	ProjList		Reduce complexity of process	Project Tagging	NA	PMO		1-Nov-22
547	SubType	Issue	0						ProjList	ProjList	Issue	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
548	SubType	Other	0						ProjList	ProjList	Other	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
549	SubType	Risk	0						ProjList	ProjList	Risk	Risk or Issue or Other tagging at the task level	NA	PMO		1-Nov-22
550	SubType	Task	0						ProjList	ProjList	Task	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
551	Supervisor	John Hammond	1	Supervisor	customField13	tbResSupervisor	John Hammond	37	ResList		WileyC	Resource or person tagging	NA	PMO		1-Nov-22
552	Supervisor	Jim Key	2	Supervisor	customField13	tbResSupervisor	Jim Key	38	ResList		BugsB	Resource or person tagging	NA	PMO		1-Nov-22
553	Supervisor	Helen Hunt	3	Supervisor	customField13	tbResSupervisor	Helen Hunt	39	ResList		WileyC	Resource or person tagging	NA	PMO		1-Nov-22
554	Tag Group	Business Advisors	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
555	Tag Group	Business Owners	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
556	Tag Group	Calendar	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
557	Tag Group	Category	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
558	Tag Group	Contact	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
559	Tag Group	Cost Code	7						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
560	Tag Group	Delivery Managers	8						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
561	Tag Group	Department	9						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
562	Tag Group	Document Purpose	10						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
563	Tag Group	Document Status	11						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
564	Tag Group	Document Type	12						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
565	Tag Group	Estimation Class	13						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
566	Tag Group	ExpectedHoursPerWeek	14						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
567	Tag Group	ExSponsor	15						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
568	Tag Group	ExtSystemResID	16						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
569	Tag Group	Gates Large	17						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
570	Tag Group	Gates Medium	18						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
571	Tag Group	Gates Release	19						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
572	Tag Group	Gates Small	20						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
573	Tag Group	Health	21						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
574	Tag Group	Health Indicators	22						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
575	Tag Group	HyperLinks	23						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
576	Tag Group	Investment Category	24						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
577	Tag Group	Investment Initiative	25						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
578	Tag Group	Investment Objective	26						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
579	Tag Group	Investment Strategy	27						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
580	Tag Group	L1	28						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
581	Tag Group	L2	29						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
582	Tag Group	L3	30						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
583	Tag Group	Labour Type	31						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
584	Tag Group	Lifecycle Phase	32						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
585	Tag Group	Location	33						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
586	Tag Group	Non Project Tag	34						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
587	Tag Group	OOM Estimates	35						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
588	Tag Group	Organizational Manager	36						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
589	Tag Group	Parttime Fulltime	37						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
590	Tag Group	PartTimeFullTime	38						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
591	Tag Group	PercentTimeAllocated	39						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
592	Tag Group	PerecentAvailable	40						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
593	Tag Group	Phase	41						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
594	Tag Group	Portfolios	42						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
595	Tag Group	Primary Contact	43						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
596	Tag Group	Primary Line of Business	44						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
597	Tag Group	Primary Skill	45						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
598	Tag Group	Primary Strategic Priority	46						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
599	Tag Group	Priority	47						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
600	Tag Group	Product	48						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
601	Tag Group	Program Activity Alignment (PAA)	49						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
602	Tag Group	Programs	50						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
603	Tag Group	Project Managers	51						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
604	Tag Group	Project Status	52						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
605	Tag Group	ProjectManager	53						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
606	Tag Group	ProjectNumber	54						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
607	Tag Group	Resource Class	55						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
608	Tag Group	Resource Manager	56						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
609	Tag Group	Resource Role	57						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
610	Tag Group	Resource Supervisor	58						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
611	Tag Group	ResourceCalendar	59						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
612	Tag Group	Responsibility	60						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
613	Tag Group	Responsible Teams	61						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
614	Tag Group	Severity	62						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
615	Tag Group	Show In Reports	63						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
616	Tag Group	ShowIn	64						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
617	Tag Group	Size	65						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
618	Tag Group	Sponsoring Department	66						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
619	Tag Group	Sponsors	67						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
620	Tag Group	Stage	68						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
621	Tag Group	Stage (Manual)	69						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
622	Tag Group	State	70						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
623	Tag Group	Status	71						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
624	Tag Group	stdTasks	72						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
625	Tag Group	tbType	73						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
626	Tag Group	Team Leader	74						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
627	Tag Group	Type Of Initiative	75						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
628	Tag Group	YesNo	76						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
629	Tag Group	Field Type	77						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
630	Tag Group	Form Name	78						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
631	tbType	ActionItem	0						NewBars	General	Actn	Future - drop anywhere to create an Action Item	NA	system		1-Nov-22
632	tbType	Allocation	0						NewBars	General	Alloc	Not used, see Resource Allocator to assign a new Resource	NA	system		1-Nov-22
633	tbType	Issue	0						NewBars	General	Issue	Future - drop anywhere to create a Issue	NA	system		1-Nov-22
634	tbType	Program	0						NewBars	General	Prog	Drag and Drop on Portfilio to create new Program	NA	system		1-Nov-22
635	tbType	Risk	0						NewBars	General	Risk	Future - drop anywhere to create a Risk	NA	system		1-Nov-22
636	tbType	Gate	1							NewBarsNo	Gate	Drag and Drop on Canvas to create new Portfolio	NA	System		1-Nov-22
637	tbType	Portfolio	2	Timebar Type	customfield39	tbMDTypes	L1 Portfolio	146		NewBars	L1 Portfolio	Drag and Drop on on Portfolio or Program to create new Project	NA	System		1-Nov-22
638	tbType	Project	3	Timebar Type	customfield39	tbMDTypes	L2 Project	147		NewBars	L2 Project	Drag and Drop on project to create sub project	NA	System		1-Nov-22
639	tbType	Sub-Project	4	Timebar Type	customfield39	tbMDTypes	L3 Sub-Project	148		NewBars	L3 Sub-Project	Drag and Drop on, another Task to clone it, a Project or Release to create new Task	NA	System		1-Nov-22
640	tbType	Milestone	5	Timebar Type	customfield39	tbMDTypes	L4 Milestone			NewBars	Milestone	Drag and Drop on Canvas to create new Portfolio	NA	System		1-Nov-22
641	tbType	Task	5	Timebar Type	customfield39	tbMDTypes	L4 Task	149		NewBars	Task	Drag and Drop on, another Milestone to clone it, a Project or Release to create new Milestone	NA	System		1-Nov-22
642	tbType	Allocation	6	Timebar Type	customfield39	tbMDTypes	Allocation	150		NewBars	Allocation	Drop to create a gate object on canvas	NA	System		1-Nov-22
643	tbType	Tile	7							NewBarsNo	Tile	Drag and Drop on Canvas to create new Release	NA	System		1-Nov-22
644	tbTypeInternal	Portfolio	1								L1 Portfolio		NA	System		1-Nov-22
645	tbTypeInternal	Project	2								L2 Project		NA	System		1-Nov-22
646	tbTypeInternal	Sub-Project	3								L3 Sub-Project		NA	System		1-Nov-22
647	tbTypeInternal	Task	4								L4 Task		NA	System		1-Nov-22
648	tbTypeInternal	Milestone	5								L4 Milestone		NA	System		1-Nov-22
649	tbTypeInternal	Allocation	6								Allocation		NA	System		1-Nov-22
650	Team Leader	App Team	0	Team Leader	customField14	tbResTeamLeader	App Team	41	ResList	ResList	Erica tl	Resource or person tagging	NA	system		1-Nov-22
651	Team Leader	CRM Team	0	Team Leader	customField14	tbResTeamLeader	CRM Team	40	ResList	ResList	Ben tl	Resource or person tagging	NA	system		1-Nov-22
652	Team Leader	Desktop Team	0	Team Leader	customField14	tbResTeamLeader	Desktop Team	42	ResList	ResList	Julia tl	Resource or person tagging	NA	system		1-Nov-22
653	Timebar Priority	High	0	priority	priority	tbMDPriority	High	9	General		High	Set timebar priority	NA	PMO		1-Nov-22
654	Timebar Priority	Immediate	0	priority	priority	tbMDPriority	Immediate	10	General		Med	Set timebar priority	NA	PMO		1-Nov-22
655	Timebar Priority	Low	0	priority	priority	tbMDPriority	Low	7	General		Low	Set timebar priority	NA	PMO		1-Nov-22
656	Timebar Priority	Normal	0	priority	priority	tbMDPriority	Normal	8	General		Med	Set timebar priority	NA	PMO		1-Nov-22
657	Timebar Priority	Not Assessed	0	priority	priority	tbMDPriority	Not Assessed	14	General		Low	Set timebar priority	NA	PMO		1-Nov-22
6421	Timebar Status	Rejected		status	status	tbMDStatus	Rejected	14
658	Timebar Status	In progress	0	status	status	tbMDStatus	In progress	7	ProjList		Canceled	Project Tagging	NA	PMO		1-Nov-22
659	Timebar Status	New	0	status	status	tbMDStatus	New	1	ProjList		Active	Project Tagging	NA	PMO		1-Nov-22
660	Timebar Status	Closed		status	status	tbMDStatus	Closed	12
661	Timebar Status	On Hold		status	status	tbMDStatus	On Hold	13
662	Type Of Initiative	Other	0	Type Of Initiative	customField36	tbMDProjectType	Other	131	ProjList	ProjList	Other	Project Tagging	NA	system		1-Nov-22
663	Type Of Initiative	Program	0	Type Of Initiative	customField36	tbMDProjectType	Program	129	ProjList	ProjList	Sprint	Project Tagging	NA	system		1-Nov-22
664	Type Of Initiative	Project	0	Type Of Initiative	customField36	tbMDProjectType	Project	128	ProjList	ProjList	Project	Project Tagging	NA	system		1-Nov-22
665	Type Of Initiative	Proposal	0	Type Of Initiative	customField36	tbMDProjectType	Sprint	130	ProjList	ProjList	Program	Project Tagging	NA	system		1-Nov-22
666	WF State	Spawned	0	State	customField38	tbMDState	Spawned	144	ProjList	ProjList	Spawned	Workflow Lifecycle tag	NA	PMO		1-Nov-22
667	WF State	Awaiting Input	1	State	customField38	tbMDState	Awaiting Input	141	ProjList	ProjList	Awaiting Input	Workflow Lifecycle tag	NA	PMO		1-Nov-22
668	WF State	Requested Approval	2	State	customField38	tbMDState	Requested Approval	142	ProjList	ProjList	Requested Approval	Workflow Lifecycle tag	NA	PMO		1-Nov-22
669	WF State	Awaiting Approval	3	State	customField38	tbMDState	Awaiting Approval	140	ProjList	ProjList	Awaiting Approval	Workflow Lifecycle tag	NA	PMO		1-Nov-22
670	WF State	Approved	4	State	customField38	tbMDState	Approved	143	ProjList	ProjList	Approved	Workflow Lifecycle tag	NA	PMO		1-Nov-22
671	WF State	Awaiting Review	5	State	customField38	tbMDState	Awaiting Review	145	ProjList	ProjList	Awaiting Review	Workflow Lifecycle tag	NA	PMO		1-Nov-22
672	WP Health	Attention	0	WP Health	customField8	tbMDHealth	Attention	21	ProjList		Attention	For Dashboard indicators	NA	PMO		1-Nov-22
673	WP Health	Blocked	0	WP Health	customField8	tbMDHealth	Blocked	19	ProjList		Blocked	For Dashboard indicators	NA	PMO		1-Nov-22
674	WP Health	Completed	0	WP Health	customField8	tbMDHealth	Completed	20	ProjList		Completed	For Dashboard indicators	NA	PMO		1-Nov-22
675	WP Health	Early	0	WP Health	customField8	tbMDHealth	Early	16	ProjList		Early	For Dashboard indicators	NA	PMO		1-Nov-22
676	WP Health	Late	0	WP Health	customField8	tbMDHealth	Late	18	ProjList		Late	For Dashboard indicators	NA	PMO		1-Nov-22
677	WP Health	On schedule	0	WP Health	customField8	tbMDHealth	On Schedule	15	ProjList		On schedule	For Dashboard indicators	NA	PMO		1-Nov-22
678	WP Health	Slipping	0	WP Health	customField8	tbMDHealth	Slipping	17	ProjList		Slipping	For Dashboard indicators	NA	PMO		1-Nov-22
679	YesNo	No	0						General	General	No	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
680	YesNo	Yes	0						General	General	Yes	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
681	YesNo	NA	6						General	General	NA	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
Import Data

## Documents
tbDocID	tbDocL1	tbDocL2	tbDocL3	tbDocL4	tbDocL5	tbDocCardImage	tbDocName	tbDocNameShort	tbDocHTMLContent	tbDocStatus	tbDocPurpose	tbDocWrittenBy	tbDocBriefDescription	tbDocCustomerID	tbDocType	tbDocGroup	tbDocOwner	tbDocPopular	tbDocSortOrder	tbDocLastModified	tbDocApprovedBy	id
Documents	Must be the tbID of the parent timebar.	Used to generate Chips in Document Cards Page					Mandatory and brief		Main content for the doc, populated by editor or by hand here	Uses picklist Document Status
tbDocID	tbDocL1	tbDocL2	tbDocL3	tbDocL4	tbDocL5	tbDocCardImage	tbDocName	tbDocNameShort	tbDocHTMLContent	tbDocStatus	tbDocPurpose	tbDocWrittenBy	tbDocBriefDescription	tbDocCustomerID	tbDocType	tbDocGroup	tbDocOwner	tbDocPopular	tbDocSortOrder	tbDocLastModified	tbDocApprovedBy	id
2	A012	Business Case					Business Case for ID 20		This is my content	Approved		Jim Cox	my brief2	44	HTML		Jim Cox	Yes		21-Oct-22	JC	10
3	B013	Business Case					Business Case for ID 40		This is my content	First Draft		Jim Cox	my brief3	44	HTML		Jim Cox	Yes		21-Oct-22	JC	11
4	A012	Project Charter					Business Case for ID 20		This is my content	Approved		Jim Cox	my brief4	44	HTML		Jim Cox	Yes		21-Oct-22	JC	12
5	B013	Project Charter					Business Case for ID 40		This is my content	Approved		Jim Cox	my brief5	44	HTML		Jim Cox	Yes		21-Oct-22	JC	13
Import Data

## Baseline
tbID	tbSelfKey2	tbPredecessor	tbTaskParent	tbCoordTop	tbHierarchyOrder	tbName	tbType	tbL1	tbL2	tbL3	tbL4	tbL5	tbStatus	tbState	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbPriority	tbPhase	tbStart	tbFinish	tbDuration	tbOwner	tbRemainingDuration	tbAStart	tbAFinish	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStage	tbPine	tbBalsam	tbFir	tbSpruce	tbArea	tbSize	tbPercent2	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	tbExpHoursPerWeek	tbCostID	tbCost	tbCostRemaining	tbACost	tbPayRate	tbCostType	canvasNo	tbAzureID	kbCoordTop	kbCoordLeft	tbHierarchyOrder	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbCoordLeft	tbMetaDataID	tbBLID	tbVolume	tbAWork	tbWorkRemaining	tbPercentComplete	tbCost	tbAcost	tbCostRemaining	tbResID	tbCalendar	tbPercentTimeOn	tbCustomerID	tbT1	tbT2	tbWbsDescription
Baseline Data Store				Mandatory		Mandatory	Mandatory														Mandatory	Mandatory
tbID	Parent	Predecessor	TaskParent	Top Pos	HierarchyOrder	Name	Type	Portfolio	Project	Sub-Project	Task	Allocation	Status	State	Step	StepStatus	WfReasonNote	Stage	Priority	Phase	Start	Finish	Duration	Owner	Rem Dur	Astart	Afinish	Hours	Awork	Work Rem	% Compl	Stage	Pine	Balsam	Fir	Spruce	Area	Sizexxx	%Pulp	Constr Type	Constr Date	Float	FreeFloat	Exp Hours Per Week	Cost ID	Cost	Cost Rem	Acost	Pay Rate	Cost Type	Cavas No	CloudID	KB Top PX	KB Left PX	Hierarchy Order	focdItemCoordLeft	focdItemCoordTop	Bar Color	Text Color	LeftPX	MDID	BLID	Vol/HA	AWork	WorkRemaining	PercentComplete	Cost	Acost	CostRemaining	ResID	Calendar	PercentTimeOn	CustID	tbT1	tbT2	tbWbsDescription
Import Data

## ResCalcs
tbResCalcID	tbResCalcTbResID	tbResCalcName	tbResCalcCustomerID	tbResCalcWeek	tbResCalcWdays	tbResCalcStartWeekNo	tbResCalcTbWeekNo	tbResCalcWeekSumHours	tbResCalcWeekSumCost	tbResCalcLastModified	tbResCalcTbID	id
Rescalcs Data Store		(Burndown Chart Data)
tbResCalcID	tbResCalcTbResID	tbResCalcName	tbResCalcCustomerID	tbResCalcWeek	tbResCalcWdays	tbResCalcStartWeekNo	tbResCalcTbWeekNo	tbResCalcWeekSumHours	tbResCalcWeekSumCost	tbResCalcLastModified	tbResCalcTbID	id
Import Data

## ResCalcs2
tbResCalcID	tbResCalcTbID	tbResCalcResID	tbResCalcWeekNo	tbResCalcName	tbName	tbType	tbResCalcMonday	tbResCalcWeek	tbResCalcFriday	tbResCalcHours	tbResCalcCost	tbResCalcWdays	apStatusDate	tbResCalcCustomerID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDNameShort	tbMDLocation	tbMDDepartment	tbL1	tbL2	tbL3	tbL4	tbL5	tbOwner
Rescalcs2 Data Store		(Resource Stacked Chart Data)
tbResCalcID	tbResCalcTbID	tbResCalcResID	tbResCalcWeekNo	tbResCalcName	tbName	tbType	tbResCalcMonday	tbResCalcWeek	tbResCalcFriday	tbResCalcHours	tbResCalcCost	tbResCalcWdays	apStatusDate	tbResCalcCustomerID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDNameShort	tbMDLocation	tbMDDepartment	tbL1	tbL2	tbL3	tbL4	tbL5	tbOwner
Import Data

## Charts
tbChartID	tbChartTbId	tbChartName	tbChartType	tbChartLabels	tbChartDataset1	tbChartDataset2	tbChartDataset3	tbChartDataset4	tbChartConfig1	tbChartConfig2	tbChartCustomerID	id
Charts Data Store
tbChartID	tbChartTbId	tbChartName	tbChartType	tbChartLabels	tbChartDataset1	tbChartDataset2	tbChartDataset3	tbChartDataset4	tbChartConfig1	tbChartConfig2	tbChartCustomerID	id
1	2	Burndown Chart	Bar	["Wk1","Wk2","Wk3","Wk4","Wk5","Wk6","Wk7"]	[65,59,80,81,56,55,40]	[65,50,70,88,66,55,20]					44	3
Import Data

## ResCalcsUsage
id	tbResCalcProject	tbResCalcResID	tbResCalcWeek1	tbResCalcWeek2	tbResCalcWeek3	tbResCalcWeek4	tbResCalcWeek5	tbResCalcWeek6	tbResCalcWeek7	tbResCalcWeek8	tbResCalcWeek9	tbResCalcWeek10	tbResCalcWeek11	tbResCalcWeek12	tbResCalcWeek13	tbResCalcWeek14	tbResCalcWeek15	tbResCalcWeek16	tbResCalcWeek17	tbResCalcWeek18	tbResCalcWeek19	tbResCalcWeek20	tbResCalcWeek21	tbResCalcWeek22	tbResCalcWeek23	tbResCalcWeek24	tbResCalcWeek25	tbResCalcWeek26	tbResCalcWeek27	tbResCalcWeek28	tbResCalcWeek29	tbResCalcWeek30	tbResCalcWeek31	tbResCalcWeek32	apStatusDate	tbResCalcLastModified	tbResCalcResName
ResCalcUsage Data Store (Weekly Usage)
id	tbResCalcProject	tbResCalcResID	tbResCalcWeek1	tbResCalcWeek2	tbResCalcWeek3	tbResCalcWeek4	tbResCalcWeek5	tbResCalcWeek6	tbResCalcWeek7	tbResCalcWeek8	tbResCalcWeek9	tbResCalcWeek10	tbResCalcWeek11	tbResCalcWeek12	tbResCalcWeek13	tbResCalcWeek14	tbResCalcWeek15	tbResCalcWeek16	tbResCalcWeek17	tbResCalcWeek18	tbResCalcWeek19	tbResCalcWeek20	tbResCalcWeek21	tbResCalcWeek22	tbResCalcWeek23	tbResCalcWeek24	tbResCalcWeek25	tbResCalcWeek26	tbResCalcWeek27	tbResCalcWeek28	tbResCalcWeek29	tbResCalcWeek30	tbResCalcWeek31	tbResCalcWeek32	apStatusDate	tbResCalcLastModified	tbResCalcResName
Import Data

## Dashboard
tbID	tbSelfKey2	tbPredecessor	tbTaskParent	tbName	tbType	tbSubType	tbCoordTop	kbCoordTop	kbCoordLeft	tbStart	tbFinish	tbDuration	tbStatus	tbState	tbL1	tbL2	tbL3	tbL4	tbL5	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbPriority	tbPhase	tbRemainingDuration	tbAStart	tbAFinish	tbOwner	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	tbExpHoursPerWeek	tbCostID	tbCost	tbCostRemaining	tbACost	tbPayRate	tbCostType	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbAcost	tbResID	tbCalendar	tbPercentTimeOn	tbCustomerID	tbHierarchyOrder	id	tbMDID	tbMDName	tbMDTypes	tbMDProjectNumber	tbMDDescription	tbMDNotes	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDResponsibility	tbMDDepartment	tbMDExSponsor	tbMDHealth	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDROMEstimate	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSize	tbMDStageApprover	tbMDWrittenBy	tbMDBusinessAdvisor	tbMDBusinessOwner	tbMDDeliveryManager	tbMDOrgManager	tbMDPriorityStrategic	tbMDSponsoringDepartment	tbMDPrimaryContact	tbMDBenefitCostRatio	tbMDContactNumber	tbMDResponsibleTeam	tbMDRiskVsSizeAndComplexity	tbMDEcnomicValueAdded	tbMDEstimationClass	tbMDInternalRateOfReturn	tbMDSprintName	tbMDSunkCosts	tbMDSyncNotes	tbMDNotesProject	tbMDContractNumber	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDPrimaryLineOfBusiness	tbMDBackgroundInfo	tbMDCapabilitiesNeeded	tbMDConsequence	tbMDExpectedBenefits	tbMDProblemOpportunity	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommittment	tbMDStakeholderDescription	tbMDNotesWorkflow	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDSortOrder	tbMDtbLastModified	tbMDPM	tbMDProjectType	tbMDShowIn	tbMDYesNoSelector	tbMDProduct	tbMDContact	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDPrimarySkill	tbMDPrimaryRole	tbMDOther2	tbMDOther3	tbMDExtLink1	tbMDExtSystemID1	tbMDRefID	tbMDSeverity
Dashboard Data (Derived Data Store - tbMDJoined)								Total of 150 columns of data based on a join of Timebars and MetaData Stores.
tbID	tbSelfKey2	tbPredecessor	tbTaskParent	tbName	tbType	tbSubType	tbCoordTop	kbCoordTop	kbCoordLeft	tbStart	tbFinish	tbDuration	tbStatus	tbState	tbL1	tbL2	tbL3	tbL4	tbL5	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbPriority	tbPhase	tbRemainingDuration	tbAStart	tbAFinish	tbOwner	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	tbExpHoursPerWeek	tbCostID	tbCost	tbCostRemaining	tbACost	tbPayRate	tbCostType	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbAcost	tbResID	tbCalendar	tbPercentTimeOn	tbCustomerID	tbHierarchyOrder	id	tbMDID	tbMDName	tbMDTypes	tbMDProjectNumber	tbMDDescription	tbMDNotes	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDResponsibility	tbMDDepartment	tbMDExSponsor	tbMDHealth	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDROMEstimate	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSize	tbMDStageApprover	tbMDWrittenBy	tbMDBusinessAdvisor	tbMDBusinessOwner	tbMDDeliveryManager	tbMDOrgManager	tbMDPriorityStrategic	tbMDSponsoringDepartment	tbMDPrimaryContact	tbMDBenefitCostRatio	tbMDContactNumber	tbMDResponsibleTeam	tbMDRiskVsSizeAndComplexity	tbMDEcnomicValueAdded	tbMDEstimationClass	tbMDInternalRateOfReturn	tbMDSprintName	tbMDSunkCosts	tbMDSyncNotes	tbMDNotesProject	tbMDContractNumber	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDPrimaryLineOfBusiness	tbMDBackgroundInfo	tbMDCapabilitiesNeeded	tbMDConsequence	tbMDExpectedBenefits	tbMDProblemOpportunity	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommittment	tbMDStakeholderDescription	tbMDNotesWorkflow	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDSortOrder	tbMDtbLastModified	tbMDPM	tbMDProjectType	tbMDShowIn	tbMDYesNoSelector	tbMDProduct	tbMDContact	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDPrimarySkill	tbMDPrimaryRole	tbMDOther2	tbMDOther3	tbMDExtLink1	tbMDExtSystemID1	tbMDRefID	tbMDSeverity
Import Data

## FormatSheets
ID	SheetName	FieldName	DataType	Alignment	Width
1	Timebars	tbID	Text	Left	15
2	Timebars	tbSelfKey2	Text	Left	15
3	Timebars	tbPredecessor	Text	Left	15
4	Timebars	tbName	Text	Left	100
5	Timebars	tbType	Text	Left	20
6	Timebars	tbSubType	Text	Left	15
7	Timebars	tbHierarchyOrder	Text	Left	26
8	Timebars	tbCoordTop	Number	Center	10
9	Timebars	kbCoordTop	Number	Center	1
10	Timebars	kbCoordLeft	Number	Center	1
11	Timebars	tbCoordTopP3Menu	Text	Left	1
12	Timebars	tbResID	Text	Left	15
13	Timebars	tbOwner	Text	Left	25
14	Timebars	tbWork	Number	Left	18
15	Timebars	tbAWork	Number	Left	18
16	Timebars	tbWorkRemaining	Number	Left	18
17	Timebars	tbPercentComplete	Number	Left	18
18	Timebars	tbStart	Date	Left	25
19	Timebars	tbFinish	Date	Left	25
20	Timebars	tbAStart	Date	Left	25
21	Timebars	tbAFinish	Date	Left	25
22	Timebars	tbDuration	Number	Left	15
23	Timebars	tbRemainingDuration	Number	Left	15
24	Timebars	tbCost	Currency	Left	18
25	Timebars	tbACost	Currency	Left	18
26	Timebars	tbCostRemaining	Currency	Left	18
27	Timebars	tbCalendar	Text	Left	12
28	Timebars	tbExpHoursPerWeek	Text	Left	12
29	Timebars	tbPercentTimeOn	Text	Left	12
30	Timebars	tbPayRate	Text	Left	12
31	Timebars	tbCostID	Text	Left	12
32	Timebars	tbCostType	Text	Left	12
33	Timebars	tbPhase	Text	Left	12
34	Timebars	tbL1	Text	Left	50
35	Timebars	tbL2	Text	Left	50
36	Timebars	tbL3	Text	Left	50
37	Timebars	tbL4	Text	Left	50
38	Timebars	tbL5	Text	Left	50
39	Timebars	tbWbsDescription	Text	Left	10
40	Timebars	tbConstraintType	Text	Left	10
41	Timebars	tbConstraintDate	Text	Left	10
42	Timebars	tbFloat	Text	Left	10
43	Timebars	tbFreeFloat	Text	Left	10
44	Timebars	canvasNo	Text	Left	10
45	Timebars	focdItemCoordLeft	Text	Left	10
46	Timebars	focdItemCoordTop	Text	Left	10
47	Timebars	tbBarColor	Text	Left	10
48	Timebars	tbTextColor	Text	Left	10
49	Timebars	tbBarHeight	Text	Left	10
50	Timebars	tbBLID	Text	Left	10
51	Timebars	tbCustomerID	Text	Left	10
52	Timebars	tbSchEngOverride	Text	Left	10
53	Timebars	tbT1	Text	Left	10
54	Timebars	tbT2	Text	Left	10
55	Timebars	tbStep	Text	Left	10
56	Timebars	tbStepStatus	Text	Left	10
57	Timebars	tbWfReasonNote	Text	Left	2
58	Timebars	tbStage	Text	Left	10
59	Timebars	tbStatus	Text	Left	10
60	Timebars	tbState	Text	Left	10
61	Timebars	tbPriority	Text	Left	18
62	Timebars	tbTaskParent	Text	Left	10
63	MetaData	tbMDID	Text	Left	15
64	MetaData	tbMDParent	Text	Left	15
65	MetaData	tbMDName	Text	Left	60
66	MetaData	tbMDTypes	Text	Left	20
67	MetaData	tbMDSubtype	Text	Left	20
68	MetaData	tbMDHierarchy	Text	Left	26
69	MetaData	tbMDProduct	Text	Left	24
70	MetaData	tbMDNotesProject	Text	Left	15
71	MetaData	tbMDDescription	Text	Left	30
72	MetaData	tbMDExecutiveSummary	Text	Left	30
73	MetaData	tbMDPriority	Text	Left	18
74	MetaData	tbMDStatus	Text	Left	20
75	MetaData	tbMDHealth	Text	Left	18
76	MetaData	tbMDState	Text	Left	20
77	MetaData	tbMDStage	Text	Left	20
78	MetaData	tbMDPhase	Text	Left	20
79	MetaData	tbMDGate	Text	Left	20
80	MetaData	tbMDCategory	Text	Left	20
81	MetaData	tbMDEscalationLevel	Text	Left	20
82	MetaData	tbMDProjectNumber	Text	Left	20
83	MetaData	tbMDPM	Text	Left	30
84	MetaData	tbMDExSponsor	Text	Left	30
85	MetaData	tbMDNotes	Text	Left	50
86	MetaData	tbMDPrimaryContact	Text	Left	30
87	MetaData	tbMDDepartment	Text	Left	25
88	MetaData	tbMDHealthOverall	Text	Left	18
89	MetaData	tbMDHealthScope	Text	Left	18
90	MetaData	tbMDHealthCost	Text	Left	18
91	MetaData	tbMDHealthIssues	Text	Left	18
92	MetaData	tbMDHealthRisk	Text	Left	18
93	MetaData	tbMDHealthSchedule	Text	Left	18
94	MetaData	tbMDHealthHours	Text	Left	18
95	MetaData	tbMDProjectType	Text	Left	20
96	MetaData	tbMDRiskVsSizeAndComplexity	Text	Left	20
97	MetaData	tbMDROMEstimate	Text	Left	26
98	MetaData	tbMDEstimationClass	Text	Left	20
99	MetaData	tbMDSize	Text	Left	20
100	MetaData	tbMDInvestmentCategory	Text	Left	30
101	MetaData	tbMDInvestmentInitiative	Text	Left	30
102	MetaData	tbMDInvestmentObjective	Text	Left	30
103	MetaData	tbMDInvestmentStrategy	Text	Left	30
104	MetaData	tbMDYesNoSelector	Text	Left	30
105	MetaData	tbMDPriorityStrategic	Text	Left	18
106	MetaData	tbMDCostbarsScore	Text	Left	18
107	MetaData	tbMDFinancialScore	Text	Left	18
108	MetaData	tbMDDecisionStrategic	Text	Left	30
109	MetaData	tbMDDecisionNotes	Text	Left	50
110	MetaData	tbMDPrimaryLineOfBusiness	Text	Left	30
111	MetaData	tbMDSponsoringDepartment	Text	Left	25
112	MetaData	tbMDContact	Text	Left	30
113	MetaData	tbMDContactNumber	Text	Left	30
114	MetaData	tbMDResponsibleTeam	Text	Left	30
115	MetaData	tbMDBusinessAdvisor	Text	Left	30
116	MetaData	tbMDDeliveryManager	Text	Left	30
117	MetaData	tbMDOrgManager	Text	Left	30
118	MetaData	tbMDBenefitCostRatio	Text	Left	20
119	MetaData	tbMDEcnomicValueAdded	Text	Left	20
120	MetaData	tbMDInternalRateOfReturn	Text	Left	20
121	MetaData	tbMDSunkCosts	Text	Left	20
122	MetaData	tbMDNetPresentValue	Text	Left	20
123	MetaData	tbMDOpportunityCost	Text	Left	20
124	MetaData	tbMDPaybackPeriod	Text	Left	20
125	MetaData	tbMDOther2	Text	Left	20
126	MetaData	tbMDBusinessOwner	Text	Left	30
127	MetaData	tbMDBackgroundInfo	Text	Left	30
128	MetaData	tbMDCapabilitiesNeeded	Text	Left	30
129	MetaData	tbMDConsequence	Text	Left	30
130	MetaData	tbMDExpectedBenefits	Text	Left	30
131	MetaData	tbMDProblemOpportunity	Text	Left	30
132	MetaData	tbMDConstraintsAssumptions	Text	Left	30
133	MetaData	tbMDCostBenefitAnalysis	Text	Left	30
134	MetaData	tbMDSeniorLevelCommittment	Text	Left	30
135	MetaData	tbMDStakeholderDescription	Text	Left	30
136	MetaData	tbMDWrittenBy	Text	Left	20
137	MetaData	tbMDWBS	Text	Left	20
138	MetaData	tbMDWeighting	Text	Left	20
139	MetaData	tbMDLocation	Text	Left	20
140	MetaData	tbMDResID	Text	Left	15
141	MetaData	tbMDPrimarySkill	Text	Left	20
142	MetaData	tbMDPrimaryRole	Text	Left	20
143	MetaData	tbMDResponsibility	Text	Left	20
144	MetaData	tbMDExtSystemID1	Text	Left	10
145	MetaData	tbMDSyncNotes	Text	Left	2
146	MetaData	tbMDStageApprover	Text	Left	2
147	MetaData	tbMDSprintName	Text	Left	2
148	MetaData	tbMDExtLink1	Text	Left	2
149	MetaData	tbMDOther3	Text	Left	2
150	MetaData	canvasNo	Text	Left	2
151	MetaData	tbMDRefID	Text	Left	10
152	MetaData	tbMDSortOrder	Text	Left	20
153	MetaData	tbMDtbLastModified	Text	Left	20
154	MetaData	tbMDShowIn	Text	Left	20
155	MetaData	tbMDCustomerID	Text	Left	10
156	MetaData	tbMDAzureID	Text	Left	10
157	MetaData	tbMDNameShort	Text	Left	20
158	MetaData	tbMDNotesWorkflow	Text	Left	2
159	MetaData	tbMDContractNumber	Text	Left	20
160	MetaData	tbMDPortfolio	Text	Left	20
161	MetaData	tbMDProgram	Text	Left	20
162	MetaData	tbMDProgActivityAlignment	Text	Left	20
163	MetaData	tbMDSeverity	Text	Left	20
164	MetaData	tbMDContingency	Text	Left	30
165	MetaData	tbMDMitigationPlan	Text	Left	30
166	MetaData	tbMDMitigationStatus	Text	Left	30
167	MetaData	tbMDProbability	Text	Left	30
168	MetaData	tbMDImpact	Text	Left	30
169	MetaData	tbMDRiskResponseStrategy	Text	Left	30
170	MetaData	tbMDContingencyPlan	Text	Left	30
171	MetaData	tbMDTriggerEvent	Text	Left	30
172	MetaData	tbMDEarlyWarningIndicators	Text	Left	30
173	MetaData	tbMDScore	Text	Left	18
174	Resources	tbResID	Text	Center	15
175	Resources	tbResResourceCalendar	Text	Center	10
176	Resources	tbResQuantity	Text	Center	10
177	Resources	tbResPayRate	Text	Center	10
178	Resources	tbResExtSystemResID	Text	Center	10
179	Resources	tbResName	Text	Left	40
180	Resources	tbResPrimaryRole	Text	Left	25
181	Resources	tbResPrimarySkill	Text	Left	25
182	Resources	tbResNameShort	Text	Left	20
183	Resources	tbResLabourType	Text	Left	18
184	Resources	tbResPercentGeneralAvailability	Text	Center	18
185	Resources	tbResEmail	Text	Left	30
186	Resources	tbResDepartment	Text	Left	25
187	Resources	tbResManager	Text	Left	25
188	Resources	tbResTeam	Text	Left	20
189	Resources	tbResLocation	Text	Left	20
190	Resources	tbResTeamLeader	Text	Left	20
191	Resources	tbResSupervisor	Text	Left	20
192	Resources	tbResPartTimeFullTime	Text	Left	20
193	Resources	tbResResourceType	Text	Left	20
194	Resources	tbResResourceClass	Text	Left	20
195	Resources	tbResCostCode	Text	Left	20
196	Resources	tbResCustomerID	Text	Left	10
197	Resources	tbResSortOrder	Text	Left	20
198	Resources	tbResLastModified	Text	Left	20
199	Resources	tbResPasswordHash	Text	Left	20
200	Resources	tbResPIN	Text	Left	20
201	Resources	tbResEmail2	Text	Left	20
202	Resources	tbResFirstName	Text	Left	20
203	Resources	tbResLastName	Text	Left	20
204	Resources	tbResMiddleName	Text	Left	10
205	Resources	tbResStreet	Text	Left	20
206	Resources	tbResCity	Text	Left	20
207	Resources	tbResStateProvince	Text	Left	20
208	Resources	tbResZipPostalCode	Text	Left	20
209	Resources	tbResPhoneNo	Text	Left	20
210	Resources	tbResPhoneNo2	Text	Left	20
211	Resources	tbResCellPhoneNo	Text	Left	20
212	Resources	tbResCountry	Text	Left	20
213	Resources	tbResCompany	Text	Left	20
214	Resources	tbResBirthday	Text	Left	20
215	Resources	tbResLanguage	Text	Left	20
216	Resources	tbResSocialLinks	Text	Left	20
217	Resources	tbResCourse	Text	Left	20
218	Resources	tbResCourseFinishDate	Text	Left	20
219	Resources	tbResPhoto	Text	Left	20
220	Resources	tbResPOBoxNo	Text	Left	20
221	Resources	tbResAptNo	Text	Left	20
222	Resources	tbResPostalStation	Text	Left	20
223	Resources	tbResOccupation	Text	Left	20
224	Resources	tbResSignature	Text	Left	20
225	Resources	tbResCertNo	Text	Left	20
226	Resources	tbResStatus	Text	Left	20
227	Resources	tbResState	Text	Left	20
228	Resources	tbResStage	Text	Left	20
229	Resources	tbResStep	Text	Left	20
230	Resources	tbResStepNotes	Text	Left	2
231	Resources	tbResOffice	Text	Left	20
232	Resources	tbResTransDate	Text	Left	20
233	Resources	tbResStartDate	Text	Left	20
234	Resources	tbResTermDate	Text	Left	20
235	Resources	tbResRemarks	Text	Left	20

## Fields
dfID	dfCoordTop	dfCoordLeft	dfWidth	dfName	dfType	dfFormName	dfLabel	dfTitle	dfPicklist	dfOther1	dfOther2	dfShowYN	dfOther3	dfOther4	dfOther5
Dynamic Fields Data Store								Hover title
ID	Coord Top	Coord Left	Width	Name	Type	Form Name	Label	Title	Picklist Name	Store	Status	Show YN	dfOther3	dfOther4	dfOther5
1	192.43	289.95	75	tbID	NoPicklist	ALLOC1	UID			tbTimebars	disabled	Yes			41.36364
2	46.00	8.00	567	pfBand	Band	ALLOC1	Allocation Key Metadata			tbMetaData		Yes			466
3	100.00	8.00	225	tbName	NoPicklist	ALLOC1	Allocation Name			tbTimebars		Yes
3a	100.00	290.00	450	tbResID	NoPicklist	ALLOC1	Resource ID			tbTimebars	disabled	Yes
4	206.45	8.00	125	tbStart	NoPicklist	ALLOC1	Start			tbTimebars	disabled	Yes			91.36364
5	206.45	136.45	125	tbFinish	NoPicklist	ALLOC1	Finish			tbTimebars	disabled	Yes			91.36364
6	192.43	383.90	75	tbSelfKey2	NoPicklist	ALLOC1	Parent ID			tbTimebars	disabled	Yes			41.36364
7	319.91	7.35	122.72764	tbCalendar	NoPicklist	ALLOC1	Availability/Calendar			tbTimebars		Yes			89.09064
8	319.92	136.33	92.72724	tbPercentTimeOn	NoPicklist	ALLOC1	% Allocated			tbTimebars		Yes			59.07674
8a	319.92	289.00	200	tbOwner	NoPicklist	ALLOC1	Owner			tbTimebars	disabled	Yes			59.07674
9	228.00	106.00	420	tbDocName	TextArea	dfFormalDoc	Document Name			tbDocuments		Yes	3		386
10	302.00	541.00	273	tbDocNameShort	TextArea	dfFormalDoc	Document Name Short			tbDocuments		Yes	5		239
11	389.00	115.00	600	tbDocHTMLContent	Editor	dfFormalDoc	Edit Content			tbDocuments		Yes	5		566
12	280.00	115.00	387	tbDocStatus	WithPicklist	dfFormalDoc	Document Status		Document Status	tbDocuments		Yes	5		566
13	460.38	821.58	144	tbMDEscalationLevel	WithPicklist	dfIssue	Escalation Level	Escalation Level	Escalation Level	tbMetaData		Yes			110
14	345.38	61.91	477	tbName	NoPicklist	dfIssue	Name	Issue Name		tbTimebars		Yes	3		386
15	458.50	60.00	700	tbMDDescription	TextArea	dfIssue	Description	Issue Description		tbMetaData		Yes	5		666
16	235.56	964.33	728	tbMDExecutiveSummary	Editor	dfIssue	Edit Executive Summary	Issue Executive Summary		tbMetaData		Yes	5		694
17	236.77	609.16	75	tbID	NoPicklist	dfIssue	UID	ItemID		tbTimebars	disabled	Yes			41
18	344.06	555.09	125	tbStart	NoPicklist	dfIssue	Created On	Date issue resolution began.		tbTimebars	disabled	Yes			91
19	344.06	689.44	125	tbFinish	NoPicklist	dfIssue	Finish	Anticipated resolution date		tbTimebars	disabled	Yes			91
20	236.77	698.59	75	tbSelfKey2	NoPicklist	dfIssue	ParentID	ParentID		tbTimebars	disabled	Yes			41
21	243.44	63.31	117	tbSubType	WithPicklist	dfIssue	SubType	Sub Type is used to to change Task into Risk or Issue.	SubType	tbTimebars		Yes			83
22	243.44	193.25	137	tbMDStatus	WithPicklist	dfIssue	Status	Issue Status	RandIStatus	tbMetData		Yes			103
23	243.44	337.59	100	tbMDState	WithPicklist	dfIssue	State	Issue State	RandIState	tbMetData		Yes			66
24	236.27	488.03	100	tbMDStage	WithPicklist	dfIssue	Stage	Issue Stage	RandIStage	tbMetaData		Yes			66
25	623.69	83.75	700	tbMDNotes	TextArea	dfIssue	Issue Actions and Tracking Notes	Issue Tracking Notes		tbMetaData		Yes	5		666
26	345.38	61.91	477	tbName	NoPicklist	dfRisk	Risk Name	Risk Name		tbTimebars		Yes	3		386
27	251.69	1045.94	597	tbMDDescription	TextArea	dfRisk	Risk Description	Risk Description		tbMetaData		Yes	5		563
28	346.56	849.11	154	tbMDEscalationLevel	WithPicklist	dfRisk	Escalation Level	Escalation Level	Escalation Level	tbMetaData		Yes			119
29	227.27	699.16	75	tbID	NoPicklist	dfRisk	UID	Unique ID		tbTimebars	disabled	Yes			41
30	344.06	555.09	125	tbStart	NoPicklist	dfRisk	Start	Anticipated date of Risk materializing		tbTimebars	disabled	Yes			91
31	344.06	689.44	125	tbFinish	NoPicklist	dfRisk	Finish	When would Risk monitoring end		tbTimebars	disabled	Yes			91
32	227.27	806.34	92	tbSelfKey2	NoPicklist	dfRisk	ParentID	ParentID		tbTimebars	disabled	Yes			41
33	227.27	111.61	117	tbSubType	WithPicklist	dfRisk	SubType	SubType	SubType	tbTimebars		Yes			83
34	754.33	867.41	194	tbMDMitigationStatus	WithPicklist	dfRisk	Mitigation Status	Risk Mitigation Status	Mitigation Satus	tbMetaData		Yes			159
35	227.77	439.48	100	tbMDState	WithPicklist	dfRisk	State	State	RandIState	tbMetaData		Yes			66
36	226.77	565.78	100	tbMDStage	WithPicklist	dfRisk	Stage	Stage	RandIStage	tbMetaData		Yes			66
37	595.08	886.45	117	tbMDProbability	WithPicklist	dfRisk	Probability	Likelyhood of Risk happening	Risk Probability	tbMetaData		Yes			83
38	596.08	1018.91	137	tbMDImpact	WithPicklist	dfRisk	Impact	Impact to the project	Risk Impact	tbMetaData		Yes			103
39	593.89	1184.16	125	tbMDScore	NoPicklist	dfRisk	Score	Score: Internally Calculated by the probability and impact in a percentage value		tbMetaData	disabled	Yes			91
40	921.08	91.70	325	tbMDContingencyPlan	Editor	dfRisk	Contingency Plan	Contingency Plan		tbMetaData		Yes	5		291
41	915.08	441.81	365	tbMDRiskResponseStrategy	Editor	dfRisk	Risk Response Strategy	Risk Response Strategy		tbMetaData		Yes	5		331
42	342.69	1045.94	700	tbMDTriggerEvent	TextArea	dfRisk	Trigger Event	Trigger Event		tbMetaData		Yes	5		666
43	459.27	1070.97	700	tbMDEarlyWarningIndicators	TextArea	dfRisk	Early Warning Indicators	Early Warning Indicators		tbMetaData		Yes	5		666
44	909.58	836.25	621	tbMDMitigationPlan	Editor	dfRisk	Edit Mitigation Plan	Risk Mitigation Plan		tbMetaData		Yes	5		587
45	612.95	85.94	728	tbMDExecutiveSummary	Editor	dfRisk	Edit Executive Summary	Risk Executive Summary short description please		tbMetaData		Yes	5		694
46	481.08	85.94	724	tbMDNotes	TextArea	dfRisk	Risk Actions and Tracking Notes	Risk Tracking Notes		tbMetaData		Yes	5		666
47	234.33	237.41	137	tbMDStatus	WithPicklist	dfRisk	Risk Status	Risk Status	RandIStatus	tbMetData		Yes			103
48	170.00	150.00	100	tbMDPriority	WithPicklist	FOCDPJ1	Priority		Timebar Priority	tbMetaData		Yes
49	600.00	30.00	600	tbMDExpectedBenefits	Editor	LdbFinancialPage	Expected Benefits			tbMetaData		Yes	5		566
50	280.00	370.00	207	tbMDHealthCost	NoPicklist	LdbFinancialPage	Cost Health			tbMetaData		Yes	6		172
51	280.00	30.00	300	tbName	NoPicklist	LdbFinancialPage	Name			tbTimebars		Yes	3		266
52	182.00	370.00	150	tbMDID	NoPicklist	LdbFinancialPage	ItemID			tbMetaData	disabled	Yes	2		116
53	280.00	610.00	200	tbMDPrimaryContact	NoPicklist	LdbFinancialPage	Primary Contact			tbMetaData		Yes	4		166
54	369.00	30.00	600	tbMDCostBenefitAnalysis	Editor	LdbFinancialPage	Cost Analysis			tbMetaData		Yes	5		566
55	380.00	30.00	273	tbMDDescription	TextArea	LdbSummaryPage	Description			tbMetaData		Yes	5		256
56	380.00	330.00	274	tbMDExecutiveSummary	TextArea	LdbSummaryPage	Executive Summary			tbMetaData		Yes	6		240
57	260.00	30.00	277	tbName	NoPicklist	LdbSummaryPage	Portfolio Name			tbTimebars		Yes	3		266
58	260.00	650.00	150	tbMDID	NoPicklist	LdbSummaryPage	UID			tbMetaData	disabled	Yes	2		116
59	260.00	330.00	269	tbMDPM	NoPicklist	LdbSummaryPage	PM			tbMetaData		Yes	4		188
60	146.00	437.86	100	tbMDID	NoPicklist	PF1	UID			tbMetaData	disabled	Yes			66
61	60.00	-4.57	557	pfBand	Band	PF1	Portfolio Information					Yes			523
62	143.00	1.14	200	tbName	NoPicklist	PF1	Portfolio Name			tbTimebars		Yes			166
63	372.00	1.14	400	tbMDExecutiveSummary	TextArea	PF1	Executive Summary			tbMetaData		Yes			366
64	246.00	1.14	400	tbMDDescription	TextArea	PF1	Description			tbMetaData		Yes			366
65	143.00	228.29	200	tbMDPM	NoPicklist	PF1	PM			tbMetaData		Yes			166
66	6.00	505.43	50	tbID	NoPicklist	PJ1	UID			tbTimebars	disabled	Yes			16
67	85.00	-14.00	500	pfBand	Band	PJ1	Project Key Metadata			tbMetaData		Yes			473.5
68	129.00	2.72	380	tbName	NoPicklist	PJ1	ProjectName			tbTimebars		Yes			353.5
69	347.00	11.30	400	tbMDDescription	TextArea	PJ1	Brief Description			tbMetaData		Yes			373.5
70	212.00	-2.70	125	tbMDProjectNumber	NoPicklist	PJ1	Project Number			tbMetaData		Yes			98.5
70a	270.00	-2.70	247	tbPredecessor	NoPicklist	PJ1	Predecessor Project ID			tbTimebars		Yes			220.5
71	208.00	141.28	125	tbMDStatus	WithPicklist	PJ1	Status		Project Status	tbMetaData		Yes			98.5
72	208.00	270.00	237	tbMDProduct	WithPicklist	PJ1	Product		Product	tbMetaData		Yes			98.5
73	447.00	10.83	600	tbMDNotesProject	TextArea	PJ1	Project Notes			tbMetaData		Yes			573.5
74	100.00	10.00	75	tbID	NoPicklist	SPJ1	UID			tbTimebars	disabled	Yes
75	35.00	1.00	500	pfBand	Band	SPJ1	Sub Project Key Metadata			tbMetaData		Yes
76	100.00	85.00	380	tbName	NoPicklist	SPJ1	Sub Project Name			tbTimebars		Yes
77	298.95	19.35	400	tbMDDescription	TextArea	SPJ1	Brief Description			tbMetaData		Yes			366.36364
78	186.97	19.35	125	tbMDProjectNumber	NoPicklist	SPJ1	Project Number			tbMetaData		Yes			91.36364
79	189.92	159.34	100	tbMDPriority	WithPicklist	SPJ1	Priority		Timebar Priority	tbMetaData		Yes			66.36364
80	189.92	279.34	100	tbMDStatus	WithPicklist	SPJ1	Status		Project Status	tbMetaData		Yes			66.36364
81	99.98	332.24	92.72724	tbID	NoPicklist	TASK1	UID			tbTimebars	disabled	Yes			59.07674
82	55.00	-5.00	495.44064	pfBand	Band	TASK1	Task Key Metadata			tbMetaData		Yes			468.938
83	100.00	10.00	337.72764	tbName	NoPicklist	TASK1	Task Name			tbTimebars		Yes
84	302.36	14.35	125	tbStart	NoPicklist	TASK1	Start			tbTimebars	disabled	Yes			91.36364
85	302.35	139.34	125	tbFinish	NoPicklist	TASK1	Finish			tbTimebars	disabled	Yes			91.36364
86	99.95	410.94	90.44034	tbSelfKey2	NoPicklist	TASK1	ParentID			tbTimebars	disabled	Yes			56.80394
87	500.67	10.11	472	tbMDDescription	TextArea	TASK1	Description			tbMetaData		Yes			366.36364
88	206.45	16.92	100	tbSubType	WithPicklist	TASK1	SubType		SubType	tbTimebars		Yes			66.36364
89	206.45	126.45	100	tbMDStatus	WithPicklist	TASK1	Status		RandIStatus	tbMetaData		Yes			66.36364
90	206.45	331.45	100	tbMDState	WithPicklist	TASK1	State		RandIState	tbMetaData		Yes			73.5
91	400.00	16.92	125	tbWork	NoPicklist	TASK1	Work			tbTimebars		Yes			91.36364
92	401.00	126.45	125	tbAWork	NoPicklist	TASK1	Actual Work			tbTimebars		Yes			91.36364
93	402.00	256.45	125	tbWorkRemaining	NoPicklist	TASK1	Work Remaining			tbTimebars		Yes			91.36364
94	302.00	265.00	125	tbOwner	NoPicklist	TASK1	Owner			tbTimebars		Yes			98.5
95	630.67	10.09	482	tbMDNotes	TextArea	TASK1	Risk Actions and Tracking Notes			tbMetaData		Yes			455.5
96	302.00	390.00	125	tbMDEscalationLevel	WithPicklist	TASK1	Escalation Level		Escalation Level	tbMetaData		Yes			455.5
97	206.45	221.45	100	tbMDPriority	WithPicklist	TASK1	Priority		Timebar Priority	tbMetaData		Yes			73.5
Import Data

## CoreReport
tbCRID	tbCRSection	tbCRFieldName	tbCRPortfolio	tbCRProject	tbCRSubProject	tbCRTask	tbCRAllocation	tbCRNoOfColumns
	Core Report Settings
CRID	MD Form Section	Field ID	Portfolio	Project	Sub-Project	Task	Allocation	NoOfColumns
1	coreFormSection1-Notes	tbID	show	show	show	show	show	3
2	coreFormSection1-Notes	tbSubType	show	show	show	show	show	3
3	coreFormSection1-Notes	tbMDNameShort	show	show	show	show	show	3
4	coreFormSection1-Notes	tbHierarchyOrder	show	show	show	show	show	3
5	coreFormSection1-Notes	tbOwner	show	show	show	show	show	3
6	coreFormSection1-Notes	tbMDPM		show	show			3
7	coreFormSection1-Notes	tbName	show	show	show	show	show	2
8	coreFormSection1-Notes	tbMDDescription	show	show	show	show		2
9	coreFormSection1-Notes	tbMDNotes	show	show	show	show		2
10	coreFormSection1-Notes	tbMDExecutiveSummary	show	show	show	show		2
11	coreFormSection2-Progress	tbMDStatus	show	show	show	show	show	3
12	coreFormSection2-Progress	tbMDHealth		show	show	show	show	3
13	coreFormSection2-Progress	tbMDState	show	show	show	show	show	3
14	coreFormSection2-Progress	tbMDPriority	show	show	show	show	show	3
15	coreFormSection2-Progress	tbMDCategory		show	show	show	show	3
16	coreFormSection2-Progress	tbMDStage		show	show	show	show	3
17	coreFormSection2-Progress	tbMDPhase		show	show	show	show	3
18	coreFormSection2-Progress	tbMDExtSystemID1		show	show	show	show	3
19	coreFormSection3-Common	tbMDExSponsor		show	show			3
20	coreFormSection3-Common	tbMDResponsibleTeam		show	show			3
21	coreFormSection3-Common	tbMDProjectNumber		show	show			3
22	coreFormSection3-Common	tbOwner	show	show	show	show	show	3
23	coreFormSection3-Common	tbMDProduct		show	show			3
24	coreFormSection3-Common	tbMDContact		show	show			3
25	coreFormSection3-Common	tbMDResponsibility				show		3
26	coreFormSection3-Common	tbMDSeverity				show		3
27	coreFormSection3-Common	tbMDDepartment		show	show	show	show	3
28	coreFormSection3-Common	tbMDShowIn						3
29	coreFormSection3-Common	tbMDDeliveryManager						3
30	coreFormSection3-Common	tbMDtbLastModified				show	show	3
31	coreFormSection4-Health	tbMDHealthOverall	show	show	show			3
32	coreFormSection4-Health	tbMDHealthCost	show	show	show			3
33	coreFormSection4-Health	tbMDHealthRisk	show	show	show			3
34	coreFormSection4-Health	tbMDHealthSchedule	show	show	show			3
35	coreFormSection4-Health	tbMDHealthScope	show	show	show			3
36	coreFormSection4-Health	tbMDHealthIssues	show	show	show			3
37	coreFormSection5-Estimates	tbMDSize		show	show			3
38	coreFormSection5-Estimates	tbMDEstimationClass		show	show			3
39	coreFormSection5-Estimates	tbMDROMEstimate		show	show			3
40	coreFormSection5-Estimates	tbMDRiskVsSizeAndComplexity		show	show			3
41	coreFormSection5-Estimates	tbMDWeighting				show		3
42	coreFormSection5-Estimates	tbMDGate		show	show			3
43	coreFormSection6-Hierarchy	tbL1		show	show	show	show	3
44	coreFormSection6-Hierarchy	tbL2			show	show	show	3
45	coreFormSection6-Hierarchy	tbL3				show	show	3
46	coreFormSection6-Hierarchy	tbL4					show	3
47	coreFormSection6-Hierarchy	tbL5						3
48	coreFormSection6-Hierarchy	tbMDWBS				show		3
49	coreFormSection6-Hierarchy	tbWbsDescription				show		3
50	coreFormSection7-Strategy	tbMDInvestmentObjective		show				3
51	coreFormSection7-Strategy	tbMDInvestmentStrategy		show				3
52	coreFormSection7-Strategy	tbMDInvestmentInitiative		show				3
53	coreFormSection7-Strategy	tbMDPriorityStrategic		show				3
54	coreFormSection7-Strategy	tbMDInvestmentCategory		show				3
55	coreFormSection8-InvestmentPlan	tbMDBusinessAdvisor		show				3
56	coreFormSection8-InvestmentPlan	tbMDPrimaryLineOfBusiness		show				3
57	coreFormSection8-InvestmentPlan	tbMDBusinessOwner		show				3
58	coreFormSection8-InvestmentPlan	tbMDSponsoringDepartment		show				3
59	coreFormSection8-InvestmentPlan	tbMDPortfolio		show				3
60	coreFormSection8-InvestmentPlan	tbMDProjectType		show				3
61	coreFormSection8-InvestmentPlan	tbMDNotesProject		show				3
62	coreFormSection8-InvestmentPlan	tbMDContractNumber		show				3
63	coreFormSection8-InvestmentPlan	tbMDPrimaryContact		show				3
64	coreFormSection8-InvestmentPlan	tbMDContactNumber		show				3
65	coreFormSection8-InvestmentPlan	tbMDNetPresentValue		show				3
66	coreFormSection8-InvestmentPlan	tbMDOpportunityCost		show				3
67	coreFormSection8-InvestmentPlan	tbMDSunkCosts		show				3
68	coreFormSection8-InvestmentPlan	tbMDPaybackPeriod		show				3
69	coreFormSection8-InvestmentPlan	tbMDInternalRateOfReturn		show				3
70	coreFormSection8-InvestmentPlan	tbMDEcnomicValueAdded		show				3
71	coreFormSection8-InvestmentPlan	tbMDBenefitCostRatio		show				3
72	coreFormSection8-InvestmentPlan	tbMDProgram						3
73	coreFormSection9-BusinessCase	tbMDBackgroundInfo		show				2
74	coreFormSection9-BusinessCase	tbMDStakeholderDescription		show				2
75	coreFormSection9-BusinessCase	tbMDConsequence		show				2
76	coreFormSection9-BusinessCase	tbMDExpectedBenefits		show				2
77	coreFormSection9-BusinessCase	tbMDProblemOpportunity		show				2
78	coreFormSection9-BusinessCase	tbMDCapabilitiesNeeded		show				2
79	coreFormSection9-BusinessCase	tbMDSeniorLevelCommittment		show				2
80	coreFormSection9-BusinessCase	tbMDConstraintsAssumptions		show				2
81	coreFormSection9-BusinessCase	tbMDCostBenefitAnalysis		show				2
82	coreFormSection9-BusinessCase	tbMDWrittenBy		show				2
83	coreFormSection10-Other	tbMDSprintName						3
84	coreFormSection10-Other	tbMDSortOrder	show	show	show	show	show	3
85	coreFormSection10-Other	tbMDYesNoSelector	show	show	show	show	show	3
86	coreFormSection10-Other	tbMDCustomerID	show	show	show	show	show	3
87	coreFormSection10-Other	tbMDAzureID						3
88	coreFormSection10-Other	tbMDOther2						3
89	coreFormSection10-Other	tbMDRefID						3
90	coreFormSection10-Other	tbMDOther3						3
91	coreFormSection10-Other	tbMDNotesWorkflow						3
92	coreFormSection10-Other	tbMDStageApprover						3
93	coreFormSection10-Other	tbMDSyncNotes						3
Import Data

## Setup
Import / Export Configuration Sheet
Importing					Validation and Formatting
Target Sheet	Location	File Name	Import	Setting		Target Sheet	Validate YN	ReFormat YN
Timebars	/home/jcox/Downloads	tbTimebars.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Timebars	Yes	No
MetaData	/home/jcox/Downloads	tbMetaData.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		MetaData	No	No
AdminPanel	/home/jcox/Downloads	tbAdminPanel.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Go!
Fields	/home/jcox/Downloads	tbFields.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Dashboard	/home/jcox/Downloads	tbMdJoined.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Tags	/home/jcox/Downloads	tbTags.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Check Missing ID’s in tbMetaData
Resources	/home/jcox/Downloads	tbResources.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Documents	/home/jcox/Downloads	tbDocuments.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
ResCalcs	/home/jcox/Downloads	tbResCalcs.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Check Duplicate ID’s tbTimebars and tbMetaData sheets
ResCalcs2	/home/jcox/Downloads	tbResCalcs2.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
ResCalcsUsage	/home/jcox/Downloads	tbResCalcsUsage.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Baseline	/home/jcox/Downloads	tbBaseline.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Charts	/home/jcox/Downloads	tbCharts.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
CoreReport	/home/jcox/Downloads	tbCoreReport.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		ID Checks Results
Exporting					ID	Is in this Sheet, not the other
Target Sheet	Location	File Name	ExportName	Setting		No missing IDs found.
Timebars	/home/jcox/Downloads/ssoutputs	tbTimebars.csv	No	59/44,34,76,1,,0,false,false,true,false,false
MetaData	/home/jcox/Downloads/ssoutputs	tbMetaData.csv	No	59/44,34,76,1,,0,false,false,true,false,false
Portfolio	/home/jcox/Downloads/ssoutputs	tbPortfolioExportDec21.csv	No	59/44,34,76,1,,0,false,false,true,false,false
CoreReport	/home/jcox/Downloads/ssoutputs	tbCoreReport.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
AdminPanel	/home/jcox/Downloads/ssoutputs	tbAdminPanel.csv	Yes	60/44,34,76,1,,0,false,false,true,false,false
Fields	/home/jcox/Downloads/ssoutputs	tbFields.csv	No	61/44,34,76,1,,0,false,false,true,false,false
Dashboard	/home/jcox/Downloads/ssoutputs	tbMdJoined.csv	No	62/44,34,76,1,,0,false,false,true,false,false
Tags	/home/jcox/Downloads/ssoutputs	tbTags.csv	No	63/44,34,76,1,,0,false,false,true,false,false
Resources	/home/jcox/Downloads/ssoutputs	tbResources.csv	No	64/44,34,76,1,,0,false,false,true,false,false
Documents	/home/jcox/Downloads/ssoutputs	tbDocuments.csv	No	65/44,34,76,1,,0,false,false,true,false,false
ResCalcs	/home/jcox/Downloads/ssoutputs	tbResCalcs.csv	No	66/44,34,76,1,,0,false,false,true,false,false
ResCalcs2	/home/jcox/Downloads/ssoutputs	tbResCalcs2.csv	No	67/44,34,76,1,,0,false,false,true,false,false
ResCalcsUsage	/home/jcox/Downloads/ssoutputs	tbResCalcsUsage.csv	No	69/44,34,76,1,,0,false,false,true,false,false
Baseline	/home/jcox/Downloads/ssoutputs	tbBaseline.csv	No	68/44,34,76,1,,0,false,false,true,false,false
Charts	/home/jcox/Downloads/ssoutputs	tbCharts.csv	No	69/44,34,76,1,,0,false,false,true,false,false

	Export!
				Takes 50 seconds to export small dataset

	Mandatory Rules for Timebars and MetaData Sheets
	Must have Title in cell A2 – Enter any text to suit your needs to identify this data
	Must have the text: “UID” in cell A3 on Timebars tab
	Must have the text: “MDUID” in cell A3 on MetaData tab
	Colors for bars http://materialuicolors.co

## Bar Creator Sheet
tbID	tbSelfKey2	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	kbCoordLeft	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbPredecessor	tbTaskParent	tbOwner	tbCost	tbACost	tbCostRemaining	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbResID	tbCostID	tbCostType	tbStatus	tbState	tbPriority	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage
Timebars Data Store					Renumber Ids				Calc Finish
UID	Parent	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Lane	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	tbPredecessor	tbTaskParent	Owner	Cost	Actual Cost	Cost Remaining	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbResID	tbCostID	Cost Type	Status	State	Priority	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage
2500	2100	LOV Service	Project		01.02.00.00.00	366			02-Oct-2023	16-Apr-2024			137	137			Stefan	0	0	0	0	0	0	0								Active	Spawned		Phase 1	OAG Replacement Project	LOV Service														30		44
2501	2101	Design:Docs Upload Service	Sub-Project		01.01.01.00.00	134	187	0	02-Oct-2023	04-Nov-2023			24	24				3843.7	0	3843.7	45.1	0	45.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: Death Notification Service						0	0	1					30		44
2502	2501	Interface Design – Docs Upload Service	Task		01.01.01.01.00	178	100	0	02-Oct-2023	14-Oct-2023			9	9				1265.6	0	1265.6	16.9	0	16.9	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	Interface Design -Docs Upload Service					0	0	1					30		44
2503	2502	SME Cloud	Allocation		01.01.01.01.01	208			02-Oct-2023	14-Oct-2023			9	9			SME Cloud Technologies	1265.6	0	1265.6	16.9	0	16.9	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2504	2501	MAR Design – Docs Upload Service	Task		01.01.01.02.00	178	100	0	16-Oct-2023	28-Oct-2023			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	MAR Design -Docs Upload Service					0	0	1					30		44
2505	2504	Dev SQL	Allocation		01.01.01.02.01	210			16-Oct-2023	28-Oct-2023			10	10			Developer SQL	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2506	2501	Testing Design – Docs Upload Service	Task		01.01.01.03.00	184	100	0	30-Oct-2023	04-Nov-2023			5	5				703.1	0	703.1	9.4	0	9.4	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	Testing Design -Docs Upload Service					0	0	1					30		44
2507	2506	Dev Web	Allocation		01.01.01.03.01	220			30-Oct-2023	04-Nov-2023			5	5			Developer Web	703.1	0	703.1	9.4	0	9.4	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2508	2101	Migration:Docs Upload Service	Sub-Project		01.01.02.00.00	140	194	0	06-Nov-2023	25-Nov-2023			15	15				3609.4	0	3609.4	43.1	0	43.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service						0	0	1					30		44
2509	2508	Interface Migration - Docs Upload Service	Task		01.01.02.01.00	184	100	0	06-Nov-2023	11-Nov-2023			5	5				984.4	0	984.4	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	Interface Migration -Docs Upload Service					0	0	1					30		44
2510	2509	SME Cloud	Allocation		01.01.02.01.01	214			06-Nov-2023	11-Nov-2023			4	4			SME Cloud Technologies	984.4	0	984.4	13.1	0	13.1	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2511	2508	Testing Migration -Docs Upload Service	Task		01.01.02.02.00	184	100	0	20-Nov-2023	25-Nov-2023			5	5				1125	0	1125	15	0	15	0					0			Active				OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	Testing Migration -Docs Upload Service					0	0	1					30		44
2512	2511	Dev Web	Allocation		01.01.02.02.01	214			20-Nov-2023	25-Nov-2023			4	4			Developer Web	1125	0	1125	15	0	15	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2513	2508	MAR Migration – Docs Upload Service	Task		01.01.02.03.00	186	100	0	13-Nov-2023	18-Nov-2023			5	5				1500	0	1500	15	0	15	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	MAR Migration -Docs Upload Service					0	0	1					30		44
2514	2513	Dev SQL	Allocation		01.01.02.03.01	216			13-Nov-2023	18-Nov-2023			4	4			Developer SQL	1500	0	1500	15	0	15	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2515	2101	Deployment:Docs Upload Service	Sub-Project		01.01.03.00.00	148	176	0	27-Nov-2023	09-Dec-2023			10	10				2343.9	0	2343.9	37.6	0	37.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Deployment:Docs Upload Service						0	0	1					30		44
2516	2515	LOB Interface Deployment - Docs Upload Service	Task		01.01.03.01.00	192	100	0	27-Nov-2023	02-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0				0	0			Active			Phase 1									0	0	1							44
2517	2516	Chris Java	Allocation		01.01.03.01.01	222			27-Nov-2023	02-Dec-2023			5	5			Chris Java	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	719		External	Active												0	0	1							44
2518	2515	Mar Deployment – Docs Upload Service	Task		01.01.03.02.00	192	100	0	04-Dec-2023	09-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0					0			Active												0	0	1					30		44
2519	2518	Dev ERP	Allocation		01.01.03.02.01	222			04-Dec-2023	09-Dec-2023			5	5			Developer ERP System	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	811		External	Active												0	0	1					30		44
2520	2515	Testing Deployment – Docs Upload Service	Task		01.01.03.03.00	258	100	0	27-Nov-2023	09-Dec-2023			10	10				1406.3	0	1406.3	18.8	0	18.8	0					0			Active												0	0	1					30		44
2521	2520	Dev Web	Allocation		01.01.03.03.01	288			27-Nov-2023	09-Dec-2023			10	10			Developer Web	1406.3	0	1406.3	18.8	0	18.8	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2522	2101	Implementation:Docs Upload Service	Sub-Project		01.01.04.00.00	164	176	0	11-Dec-2023	26-Dec-2023			10	10				1406.3	0	1406.3	20.6	0	20.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service						0	0	1					30		44
2523	2522	Interface Implementation - Docs Upload Service	Task		01.01.04.01.00	208	100	0	11-Dec-2023	19-Dec-2023			7	7				656.3	0	656.3	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	Interface Implementation - Docs Upload Service					0	0	1					30		44
2524	2523	Dev General	Allocation		01.01.04.01.01	238			11-Dec-2023	19-Dec-2023			7	7			Developer General	656.3	0	656.3	13.1	0	13.1	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2525	2522	MAR Implementation – Death Notification Service	Task		01.01.04.02.00	208	100	0	19-Dec-2023	25-Dec-2023			4	4				750	0	750	7.5	0	7.5	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	MAR Implementation -Death Notification Service					0	0	1							44
2526	2525	Dev SQL	Allocation		01.01.04.02.01	238			19-Dec-2023	25-Dec-2023			4	4			Developer SQL	750	0	750	7.5	0	7.5	0	7.5	1.875	25	100	810		External	Active												0	0	1							44
2527	2522	Testing Implementation - Docs Upload Service	Task		01.01.04.03.00	208	100	0	25-Dec-2023	26-Dec-2023			0	0				0	0	0	0	0	0	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	Testing Implementation - Docs Upload Service					0	0	1					30		44
2528	2527	Dev Web	Allocation		01.01.04.03.01	238			25-Dec-2023	26-Dec-2023			0	0			Developer Web	0	0	0	0	0	0	0	7.5	1.875	25	75	809		External	Active												0	0	1							44
2529	2101	Post-Deployment:Docs Upload Service	Sub-Project		01.01.05.00.00	174	184	0	27-Dec-2023	03-Feb-2024			27	27				4031.3	0	4031.3	50.7	0	50.7	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Post-Deployment:Docs Upload Service						0	0	1					30		44
2530	2529	Interface Post-Deployment - Docs Upload Service	Task		01.01.05.01.00	218	100	0	27-Dec-2023	10-Jan-2024			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1									0	0	1					30		44
2531	2530	SME SA	Allocation		01.01.05.01.01	248			27-Dec-2023	10-Jan-2024			10	10			SME Solution Architecture	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	807		External	Active												0	0	1					30		44
2532	2529	API Post Deployment Fixes - Docs Upload Service	Task		01.01.05.02.00	218	100	0	11-Jan-2024	25-Jan-2024			11	11				1031.3	0	1031.3	20.6	0	20.6	0					0			Active												0	0	1					30		44
2533	2532	Dev General	Allocation		01.01.05.02.01	248			11-Jan-2024	25-Jan-2024			11	11			Developer General	1031.3	0	1031.3	20.6	0	20.6	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2534	2529	Testing Post Deployment - Docs Upload Service	Task		01.01.05.03.00	218	100	0	26-Jan-2024	03-Feb-2024			6	6				1125	0	1125	11.3	0	11.3	0					0			Active												0	0	1					30		44
2535	2534	Tester EDC	Allocation		01.01.05.03.01	254			26-Jan-2024	03-Feb-2024			6	6			Tester Platforms and Datacenter	1125	0	1125	11.3	0	11.3	0	7.5	1.875	25	100	813		External	Active												0	0	1					30		44
2536	2100	Docs Upload Service	Project		01.03.00.00.00	454			02-Oct-2023	07-Apr-2024			130	130			Stefan	0	0	0	0	0	0	0								Active	Spawned		Phase 1	OAG Replacement Project	Docs Upload Service Docs														29.9826		44
2537	2101	Design: LOV Service	Sub-Project		01.01.01.00.00	134	187	0	02-Oct-2023	04-Nov-2023			24	24				3843.7	0	3843.7	45.1	0	45.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service						0	0	1					30		44
2538	2501	Interface Design - LOV Service	Task		01.01.01.01.00	178	100	0	02-Oct-2023	14-Oct-2023			9	9				1265.6	0	1265.6	16.9	0	16.9	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	Interface Design - LOV Service					0	0	1					30		44
2539	2502	SME Cloud	Allocation		01.01.01.01.01	208			02-Oct-2023	14-Oct-2023			9	9			SME Cloud Technologies	1265.6	0	1265.6	16.9	0	16.9	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2540	2501	MAR Design - LOV Service	Task		01.01.01.02.00	178	100	0	16-Oct-2023	28-Oct-2023			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	MAR Design - LOV Service					0	0	1					30		44
2541	2504	Dev SQL	Allocation		01.01.01.02.01	210			16-Oct-2023	28-Oct-2023			10	10			Developer SQL	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2542	2501	Testing Design - LOV Service	Task		01.01.01.03.00	184	100	0	30-Oct-2023	04-Nov-2023			5	5				703.1	0	703.1	9.4	0	9.4	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	Testing Design - LOV Service					0	0	1					30		44
2543	2506	Dev Web	Allocation		01.01.01.03.01	220			30-Oct-2023	04-Nov-2023			5	5			Developer Web	703.1	0	703.1	9.4	0	9.4	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2544	2101	Migration: LOV Service	Sub-Project		01.01.02.00.00	140	194	0	06-Nov-2023	25-Nov-2023			15	15				3609.4	0	3609.4	43.1	0	43.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service						0	0	1					30		44
2545	2508	Interface Migration - LOV Service	Task		01.01.02.01.00	184	100	0	06-Nov-2023	11-Nov-2023			5	5				984.4	0	984.4	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service	Interface Migration - LOV Service					0	0	1					30		44
2546	2509	SME Cloud	Allocation		01.01.02.01.01	214			06-Nov-2023	11-Nov-2023			4	4			SME Cloud Technologies	984.4	0	984.4	13.1	0	13.1	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2547	2508	Testing Migration - LOV Service	Task		01.01.02.02.00	184	100	0	20-Nov-2023	25-Nov-2023			5	5				1125	0	1125	15	0	15	0					0			Active				OAG Replacement Project	Death Notification Service	Migration: LOV Service	Testing Migration - LOV Service					0	0	1					30		44
2548	2511	Dev Web	Allocation		01.01.02.02.01	214			20-Nov-2023	25-Nov-2023			4	4			Developer Web	1125	0	1125	15	0	15	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2549	2508	MAR Migration - LOV Service	Task		01.01.02.03.00	186	100	0	13-Nov-2023	18-Nov-2023			5	5				1500	0	1500	15	0	15	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service	MAR Migration - LOV Service					0	0	1					30		44
2550	2513	Dev SQL	Allocation		01.01.02.03.01	216			13-Nov-2023	18-Nov-2023			4	4			Developer SQL	1500	0	1500	15	0	15	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2551	2101	Deployment: LOV Service	Sub-Project		01.01.03.00.00	148	176	0	27-Nov-2023	09-Dec-2023			10	10				2343.9	0	2343.9	37.6	0	37.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Deployment: LOV Service						0	0	1					30		44
2552	2515	LOB Interface Deployment - LOV Service	Task		01.01.03.01.00	192	100	0	27-Nov-2023	02-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0				0	0			Active			Phase 1									0	0	1							44
2553	2516	Chris Java	Allocation		01.01.03.01.01	222			27-Nov-2023	02-Dec-2023			5	5			Chris Java	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	719		External	Active												0	0	1							44
2554	2515	Mar Deployment - LOV Service	Task		01.01.03.02.00	192	100	0	04-Dec-2023	09-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0					0			Active												0	0	1					30		44
2555	2518	Dev ERP	Allocation		01.01.03.02.01	222			04-Dec-2023	09-Dec-2023			5	5			Developer ERP System	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	811		External	Active												0	0	1					30		44
2556	2515	Testing Deployment - LOV Service	Task		01.01.03.03.00	258	100	0	27-Nov-2023	09-Dec-2023			10	10				1406.3	0	1406.3	18.8	0	18.8	0					0			Active												0	0	1					30		44
2557	2520	Dev Web	Allocation		01.01.03.03.01	288			27-Nov-2023	09-Dec-2023			10	10			Developer Web	1406.3	0	1406.3	18.8	0	18.8	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2558	2101	Implementation: LOV Service	Sub-Project		01.01.04.00.00	164	176	0	11-Dec-2023	26-Dec-2023			10	10				1406.3	0	1406.3	20.6	0	20.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service						0	0	1					30		44
2559	2522	Interface Implementation - LOV Service	Task		01.01.04.01.00	208	100	0	11-Dec-2023	19-Dec-2023			7	7				656.3	0	656.3	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	Interface Implementation - LOV Service					0	0	1					30		44
2560	2523	Dev General	Allocation		01.01.04.01.01	238			11-Dec-2023	19-Dec-2023			7	7			Developer General	656.3	0	656.3	13.1	0	13.1	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2561	2522	MAR Implementation - LOV Service	Task		01.01.04.02.00	208	100	0	19-Dec-2023	25-Dec-2023			4	4				750	0	750	7.5	0	7.5	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	MAR Implementation -Death Notification Service					0	0	1							44
2562	2525	Dev SQL	Allocation		01.01.04.02.01	238			19-Dec-2023	25-Dec-2023			4	4			Developer SQL	750	0	750	7.5	0	7.5	0	7.5	1.875	25	100	810		External	Active												0	0	1							44
2563	2522	Testing Implementation - LOV Service	Task		01.01.04.03.00	208	100	0	25-Dec-2023	26-Dec-2023			0	0				0	0	0	0	0	0	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	Testing Implementation - LOV Service					0	0	1					30		44
2564	2527	Dev Web	Allocation		01.01.04.03.01	238			25-Dec-2023	26-Dec-2023			0	0			Developer Web	0	0	0	0	0	0	0	7.5	1.875	25	75	809		External	Active												0	0	1							44
2565	2101	Post-Deployment: LOV Service	Sub-Project		01.01.05.00.00	174	184	0	27-Dec-2023	03-Feb-2024			27	27				4031.3	0	4031.3	50.7	0	50.7	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Post-Deployment: LOV Service						0	0	1					30		44
2566	2529	Interface Post-Deployment - LOV Service	Task		01.01.05.01.00	218	100	0	27-Dec-2023	10-Jan-2024			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1									0	0	1					30		44
2567	2530	SME SA	Allocation		01.01.05.01.01	248			27-Dec-2023	10-Jan-2024			10	10			SME Solution Architecture	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	807		External	Active												0	0	1					30		44
2568	2529	API Post Deployment Fixes - LOV Service	Task		01.01.05.02.00	218	100	0	11-Jan-2024	25-Jan-2024			11	11				1031.3	0	1031.3	20.6	0	20.6	0					0			Active												0	0	1					30		44
2569	2532	Dev General	Allocation		01.01.05.02.01	248			11-Jan-2024	25-Jan-2024			11	11			Developer General	1031.3	0	1031.3	20.6	0	20.6	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2570	2529	Testing Post Deployment - LOV Service	Task		01.01.05.03.00	218	100	0	26-Jan-2024	03-Feb-2024			6	6				1125	0	1125	11.3	0	11.3	0					0			Active												0	0	1					30		44
2571	2534	Tester EDC	Allocation		01.01.05.03.01	254			26-Jan-2024	03-Feb-2024			6	6			Tester Platforms and Datacenter	1125	0	1125	11.3	0	11.3	0	7.5	1.875	25	100	813		External	Active												0	0	1					30		44

2137	2100	Biometrics Info Sharing POC	Project		01.04.00.00.00	546	159	0	04-Apr-2024	17-Sep-2024			115	115				0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics Info Sharing POC							0	0	1							44
2138	2100	Biometrics – data sharing Phase 2	Project		01.05.00.00.00	620	195	0	04-Jun-2024	19-Nov-2024			117	117			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics – data sharing Phase 2							0	0	1							44
2139	2100	Is Employee Validation	Project		01.06.00.00.00	688	191	0	25-Jul-2024	09-Jan-2025			117	117			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Is Employee Validation							0	0	1							44
2140	2100	Legacy Biographic daata sharing	Project		01.07.00.00.00	756	196	0	03-Oct-2024	20-Mar-2025			119	119				0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Legacy Biographic daata sharing							0	0	1							44
2141	2100	Biometrics - Infosharing Phase 1	Project		01.08.00.00.00	836	182	0	07-Nov-2024	24-Apr-2025			120	120			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics - Infosharing Phase 1							0	0	1							44
2142	2100	Birth Certification Validation	Project		01.09.00.00.00	898	154	0	16-Dec-2024	02-Jun-2025			120	120			Michael	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Birth Certification Validation							0	0	1							44
2143	2100	Facial Recognition FRS	Project		01.10.00.00.00	960	186	0	06-Feb-2025	24-Jul-2025			121	121			Yves	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Facial Recognition FRS							0	0	1							44
2144	2100	Portfolio Project Compliance	Project		01.11.00.00.00	1064	157	0	07-Apr-2025	20-Sep-2025			120	120			Yves	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Portfolio Project Compliance							0	0	1							44
Import Data
Format

## Field Formats
Field Formats					Current Form Names : PF1, PF2, PJ1, PJ2, PJ3, SPJ1, Task1, Task2, ALLOC1, DOC1, DOC1, other1, other2, tbform
ID	MD Sheet	DataType	ID	TBCore Sht	DataType
0	tbMDID	text	0	tbID	text			Dynamic Field Helper
1	tbMDName	text	1	tbSelfKey2	text			Preconfigured FOCD Form Fields. Instructions: Copy and paste into Fields Sheet to suit.
2	tbMDProjectType	text	2	tbCoordTop	number			UID	Coord Top	Coord Left	Width	Name	Type	Title	Form Name	Label	Picklist	Show In Form	Store Name	not used	not used	not used	not used
3	tbMDPortfolio	text	3	tbCoordLeft	number			1	130	10	350	tbMDID	NoPicklist	Item ID		UID		Yes	tbMetaData
4	tbMDProgram	text	4	tbHierarchyOrder	number			2	200	10		tbMDName	NoPicklist	Please enter name or title		Portfolio Title		Yes	tbMetaData
5	tbMDExecutiveSummary	text	5	tbName	text			3	270	10		tbMDProjectType	WithPicklist	Is this a Program, Project or Sub-project?		Project Type	Project Type	Yes	tbMetaData
6	tbMDGate	date	6	tbType	text			4	340	10		tbMDPortfolio	WithPicklist	Please enter the name of the Portfolio this belongs to		Investment Portfolio	Portfolios	Yes	tbMetaData
7	tbMDDeliveryManager	text	7	tbL1	text			5	410	10		tbMDProgram	WithPicklist	Enter Program name if applicable		Program	Programs	No	tbMetaData
8	tbMDBusinessAdvisor	text	8	tbL2	text			6	480	10		tbMDExecutiveSummary	NoPicklist	Please enter summary status of the initiative		Executive Summary			tbMetaData
9	tbMDBusinessOwner	text	9	tbL3	text			7	130	10	350	tbMDID	NoPicklist	Item ID		UID2		Yes	tbMetaData
10	tbMDEstimationClass	text	10	tbL4	text			8	200	10	350	tbMDName	NoPicklist	Please enter name or title		Portfolio Title2		Yes	tbMetaData
11	tbMDROMEstimate	text	11	tbL5	text			9	270	10	350	tbMDProjectType	WithPicklist	Is this a Program, Project or Sub-project?		Project Type2	Project Type	Yes	tbMetaData
12	tbMDInvestmentCategory	text	12	tbOwner	text			10	340	10	350	tbMDPortfolio	WithPicklist	Please enter the name of the Portfolio this belongs to		Investment Portfolio2	Portfolios	Yes	tbMetaData
13	tbMDInvestmentInitiative	text	13	tbStart	text			11	410	10	350	tbMDProgram	WithPicklist	Enter Program name if applicable		Program2	Programs	No	tbTimebars
14	tbMDInvestmentObjective	text	14	tbFinish	date			13	970	10	350	tbMDInvestmentCategory	WithPicklist			Investment Category	Investment Category		tbMetaData
15	tbMDInvestmentStrategy	text	15	tbDuration	text			14	1040	10	350	tbMDInvestmentInitiative	WithPicklist			Investment Initiative	Investment Initiative		tbMetaData
16	tbMDPriorityStrategic	text	16	tbAStart	text			15	1110	10	350	tbMDInvestmentObjective	WithPicklist			Investment Objective	Investment Objective		tbMetaData
17	tbMDCustomerID	text	17	tbAFinish	text			16	850	10	350	tbMDInvestmentStrategy	WithPicklist			Investment Strategy	Investment Strategy		tbMetaData
18	tbMDAzureID	text	18	tbRemainingDuration	number			17	900	10	350	tbMDPriorityStrategic	WithPicklist			Primary Strategic Priority	Primary Strategic Priority		tbMetaData
19	tbMDNameShort	text	19	tbResID	text			18	950	10	350	tbMDCustomerID	NoPicklist					tbMetaData
20	tbMDProjectNumber	text	20	tbCalendar	number			19	1000	10	350	tbMDAzureID	NoPicklist					tbMetaData
21	tbMDDescription	text	21	tbPercentTimeOn	number			20	1050	10	350	tbMDNameShort	NoPicklist					tbMetaData
22	tbMDNotes	text	22	tbWork	number			21	1100	10	350	tbMDProjectNumber	NoPicklist			Project Number			tbMetaData
23	tbMDExtLink1	text	23	tbAWork	number			22	440	10	350	tbMDDescription	NoPicklist	Please enter just few lines not a thesis		Brief Description		Yes	tbMetaData
24	tbMDExtSystemID1	text	24	tbWorkRemaining	number			23	520	10	350	tbMDNotes	Editor			General Notes		Yes	tbMetaData
25	tbMDSortOrder	number	25	tbPercentComplete	number			24	1250	10	350	tbMDExtLink1	NoPicklist					tbMetaData
26	tbMDtbLastModified	date	26	tbCost	number			25	1300	10	350	tbMDExtSystemID1	NoPicklist					tbMetaData
27	tbMDPriority	text	27	tbAcost	number			26	1350	10	350	tbMDSortOrder	NoPicklist					tbMetaData
28	tbMDStatus	text	28	tbCostRemaining	number			27	1050	10	350	tbMDtbLastModified	NoPicklist					tbMetaData
29	tbMDState	text	29	tbPayRate	number			28	1090	10	350	tbMDPriority	WithPicklist			Priority	Priority		tbMetaData
30	tbMDSeverity	text	30	tbCostType	text			29	1130	10	350	tbMDStatus	WithPicklist			Status	Project Status		tbMetaData
31	tbMDStage	text	31	tbCostID	text			30	1170	10	350	tbMDState	WithPicklist			State	State		tbMetaData
32	tbMDPhase	text	32	tbConstraintType	text			31	1210	10	350	tbMDSeverity	NoPicklist					tbMetaData
33	tbMDCategory	text	33	tbConstraintDate	date			32	1250	10	350	tbMDStage	WithPicklist			Stage	Stage		tbMetaData
34	tbMDHealth	text	34	tbFloat	number			33	1290	10	350	tbMDPhase	WithPicklist			Phase	Phase		tbMetaData
35	tbMDResponsibility	text	35	tbFreeFloat	number			34	1330	10	350	tbMDCategory	WithPicklist			Category	Category		tbMetaData
36	tbMDDepartment	text	36	tbExpHoursPerWeek	number			35	1370	10	350	tbMDHealth	WithPicklist					tbMetaData
37	tbMDExSponsor	text	37	canvasNo	number			36	1410	10	350	tbMDResponsibility	WithPicklist			Responsibility	Responsibility		tbMetaData
38	tbMDPM	text	38	tbCustomerID	text			37	1450	10	350	tbMDDepartment	WithPicklist			Department	Deparment		tbMetaData
39	tbMDShowIn	text	39	tbMetaDataID	text			38	1490	10	350	tbMDExSponsor	WithPicklist			Exec Sponsor			tbMetaData
40	tbMDYesNoSelector	text	40	tbBLID	text			39	1530	10	350	tbMDPM	WithPicklist			PM			tbMetaData
41	tbMDProduct	text	41	tbPredecessor	text			40	1570	10	350	tbMDShowIn	WithPicklist					tbMetaData
42	tbMDContact	text	42	tbAzureID	text			41	1610	10	350	tbMDYesNoSelector	WithPicklist					tbMetaData
43	tbMDWBS	text	43	tbCoordRight	text			42	1650	10	350	tbMDProduct	WithPicklist			Product	Product		tbMetaData
44	tbMDWeighting	number	44	tbBarColor	text			43	1690	10	350	tbMDContact	WithPicklist			Product Contact			tbMetaData
45	tbMDLocation	text	45	tbTextColor	text			44	1730	10	350	tbMDWBS	WithPicklist			WBS	WBS		tbMetaData
46	tbMDPrimarySkill	text	46	kbCoordLeft	number			45	1770	10	350	tbMDWeighting	WithPicklist					tbMetaData
47	tbMDPrimaryRole	text	47	kbCoordTop	number			46	1810	10	350	tbMDLocation	WithPicklist					tbMetaData
48	tbMDOther2	text	48	focdItemCoordLeft	number			47	1850	10	350	tbMDPrimarySkill	WithPicklist					tbMetaData
49	tbMDOther3	text	49	focdItemCoordTop	number			48	1890	10	350	tbMDPrimaryRole	WithPicklist					tbMetaData
50	tbMDOther4	text	50	tbCountry	text			49	1930	10	350	tbMDOther2	NoPicklist					tbMetaData
51	canvasNo	number	51	tbCompany	text			50	1970	10	350	tbMDOther3	NoPicklist					tbMetaData
52	tbMDProgActivityAlignment	text	52	tbLanguage	text			51	2010	10	350	tbMDOther4	NoPicklist					tbMetaData
53	tbMDBackgroundInfo	text	53	tbPriority	text			52	2050	10	350	canvasNo	NoPicklist					tbMetaData
54	tbMDConsequence	text	54	tbStatus	text			53	2090	10	350	tbMDProgActivityAlignment	WithPicklist					tbMetaData
55	tbMDExpectedBenfits	text	55	tbStep	text			54	2130	10	350	tbMDBackgroundInfo	Editor			Backround Info			tbMetaData
56	tbMDProblemOpportunity	text	56	tbStepStatus	text			55	2170	10	350	tbMDConsequence	Editor			Consequences of Inaction			tbMetaData
57	tbMDCapabilitiesNeeded	text	57	tbState	text			56	2210	10	350	tbMDExpectedBenefits	Editor			Expected Benefits			tbMetaData
58	tbMDSeniorLevelCommittment	text	58	tbWfReasonNote	text			57	2250	10	350	tbMDProblemOpportunity	Editor			Problem Opportunity			tbMetaData
59	tbMDSprintName	text	59	tbStage	text			58	2290	10	350	tbMDCapabilitiesNeeded	Editor			Capabilities Needed			tbMetaData
60	tbMDStakeholderDescription	text	60	tbPhase	text			59	2330	10	350	tbMDSeniorLevelCommittment	Editor					tbMetaData
61	tbMDHealthCost	text	61	tbPine	number			60	2370	10	350	tbMDSprintName	NoPicklist					tbMetaData
62	tbMDHealthHours	text	62	tbBalsam	number			61	2410	10	350	tbMDStakeholderDescription	NoPicklist			Stakeholder Description			tbMetaData
63	tbMDHealthIssues	text	63	tbFir	number			62	2450	10	350	tbMDHealthCost	WithPicklist			Health Cost	Health Indicators		tbMetaData
64	tbMDHealthOverall	text	64	tbSpruce	number			63	2490	10	350	tbMDHealthHours	NoPicklist					tbMetaData
65	tbMDHealthRisk	text	65	tbArea	number			64	2530	10	350	tbMDHealthIssues	WithPicklist			Health Issues	Health Indicators		tbMetaData
66	tbMDHealthSchedule	text	66	tbSize	number			65	2570	10	350	tbMDHealthOverall	WithPicklist			Health Overall	Health Indicators		tbMetaData
67	tbMDHealthScope	text	67	tbPercent2	number			66	2610	10	350	tbMDHealthRisk	WithPicklist			Health Risk	Health Indicators		tbMetaData
68	tbMDBenefitCostRatio	number	68	tbVolume	number			67	2650	10	350	tbMDHealthSchedule	WithPicklist			Health Schedule	Health Indicators		tbMetaData
69	tbMDConstraintsAssumptions	text	69	tbT1	text			68	2690	10	350	tbMDHealthScope	WithPicklist			Health Scope	Health Indicators		tbMetaData
70	tbMDContractNumber	text	70	tbT2	text			69	2730	10	350	tbMDBenefitCostRatio	NoPicklist			Benefit/Cost Ratio			tbMetaData
71	tbMDCostBenefitAnalysis	text	71	tbT3	text			70	2770	10	350	tbMDConstraintsAssumptions	Editor			Constraints And Assumptions			tbMetaData
72	tbMDEcnomicValueAdded	number	72	tbT4	text			71	2810	10	350	tbMDContractNumber	NoPicklist			Contract Number			tbMetaData
73	tbMDInternalRateOfReturn	number	73	tbT5	text			72	2850	10	350	tbMDCostBenefitAnalysis	Editor					tbMetaData
74	tbMDNetPresentValue	number	74	tbTaskParent	text			73	2890	10	350	tbMDEcnomicValueAdded	NoPicklist			Ecnomic Value Added			tbMetaData
75	tbMDOpportunityCost	number					74	2930	10	350	tbMDInternalRateOfReturn	NoPicklist			Internal Rate Of Return			tbMetaData
76	tbMDOrgManager	text					75	2970	10	350	tbMDNetPresentValue	NoPicklist			Return			tbMetaData
77	tbMDPaybackPeriod	number					76	3010	10	350	tbMDOpportunityCost	NoPicklist			Opportunity Cost			tbMetaData
78	tbMDRiskVsSizeAndComplexity	text					77	3050	10	350	tbMDOrgManager	WithPicklist			Org Manager			tbMetaData
79	tbMDSize	text					78	3090	10	350	tbMDPaybackPeriod	NoPicklist			Payback Period			tbMetaData
80	tbMDStageApprover	text					79	3130	10	350	tbMDRiskVsSizeAndComplexity	WithPicklist			Risk Vs Size And Complexity	Risk Vs Size		tbMetaData
81	tbMDSunkCosts	number					80	3170	10	350	tbMDSize	WithPicklist			Size	Size		tbMetaData
82	tbMDWrittenBy	text					81	3210	10	350	tbMDStageApprover	WithPicklist			Stage Approver			tbMetaData
83	tbMDPrimaryLineOfBusiness	text					82	3250	10	350	tbMDSunkCosts	NoPicklist			Sunk Costs			tbMetaData
84	tbMDNotesWorkflow	text					83	3290	10	350	tbMDWrittenBy	NoPicklist					tbMetaData
85	tbMDSyncNotes	text					84	3330	10	350	tbMDPrimaryLineOfBusiness	WithPicklist			Primary Line Of Business	Primary Line Of Business		tbMetaData
86	tbMDSponsoringDepartment	text					85	550	10	350	tbMDNotesWorkflow	WithPicklist			Workflow Notes		No	tbMetaData
87	tbMDPrimaryContact	text					86	3410	10	350	tbMDSyncNotes	NoPicklist					tbMetaData
88	tbMDContactNumber	text					87	3450	10	350	tbMDSponsoringDepartment	WithPicklist			Sponsoring Department	Sponsoring Department		tbMetaData
89	tbMDResponsibleTeam	text					88	3490	10	350	tbMDPrimaryContact	WithPicklist			Primary Contact			tbMetaData
90	tbMDNotesProject	text					89	3530	10	350	tbMDContactNumber	NoPicklist	Enter numbers or text or both		Contact Info			tbMetaData
91	tbMDOther5	text					90	3570	10	350	tbMDResponsibleTeam	WithPicklist			Responsible Team	Resonsible Teams		tbMetaData
92	tbMDOther6	text					91	3610	10	350	tbMDNotesProject	NoPicklist					tbMetaData
93	tbMDOther7	text					92	3650	10	350	tbMDOther5	NoPicklist					tbMetaData
94	tbMDOther8	text					93	3690	10	350	tbMDOther6	NoPicklist					tbMetaData
95	tbMDOther9	text					94	3730	10	350	tbMDOther7	NoPicklist					tbMetaData
96	tbMDOther10	text					95	3770	10	350	tbMDOther8	NoPicklist					tbMetaData
97	tbMDOther11	text					96	3810	10	350	tbMDOther9	NoPicklist					tbMetaData
98	tbMDOther12	text					97	3850	10	350	tbMDOther10	NoPicklist					tbMetaData
99	tbMDRefID	text					98	3890	10	350	tbMDOther11	NoPicklist					tbMetaData
				99	3930	10	350	tbMDOther12	NoPicklist					tbMetaData
				100	3970	10	350	tbMDRefID	NoPicklist					tbMetaData
				101	100	10	350		Band			Business Case		Yes	tbMetaData
				102	530	10	350	tbName	NoPicklist	Name of Timebar		Timebar Name		Yes	tbTimebars
				103	570	10	350	tbType	NoPicklist	Type of Timebar (Pf, Project Etc)		Type		Yes	tbTimebars
				104	620	10	350	tbL1	WithPicklist	Level 1, Portfolio		Portfolio Name	Portfolios	Yes	tbTimebars
				105	700	10	350	tbL2	NoPicklist	Level 2, Project or Program		L2 Description		Yes	tbTimebars

## Log
2024-12-30 14:19:46	The CSV Imported Successfully to AdminPanel
2024-12-30 14:19:55	The CSV Imported Successfully to Timebars
2024-12-30 14:21:29	The CSV Imported Successfully to MetaData
2024-12-30 14:22:27	The CSV Imported Successfully to MetaData
2024-12-30 15:38:00	The CSV Imported Successfully to Timebars
2024-12-30 15:38:08	The CSV Imported Successfully to MetaData
2024-12-30 15:38:32	Merge Operation Started!
2024-12-30 15:38:32	Double Title Found in 'MetaData'!
2024-12-30 15:38:32	Double Title Found in 'MetaData'!
2024-12-30 15:38:32	The record with UID 'A008' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 100.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 100.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A008' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID 'A013' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 88.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 4, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 59, Decision: Consider Terminating | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 88.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 4, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 59, Decision: Consider Terminating |'
2024-12-30 15:38:32	The record with UID 'A013' updated from 'Timebars'! Details: Field['Cost'] :: '26484.4' ----> '552000'
2024-12-30 15:38:32	The record with UID 'A012' updated from 'MetaData'! Details: Field['Description'] :: 'Enabling an employee experience that is simple, relevant and caring.' ----> 'The <strong>Digital Desktop Transformation</strong> project is closely aligned, emphasizing the modernization of employee workstations through digital tools, cloud integration, and streamlined user interfaces. This initiative is designed to enhance productivity, collaboration, and user experience by providing a cohesive and efficient digital workspace.'
2024-12-30 15:38:32	The record with UID 'A026' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 68.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 0, Work Avg Score: 100,Final Score: 75, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 68.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 0, Work Avg Score: 100,Final Score: 75, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A026' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:32	The record with UID 'A011' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'This is my Brief Description' ----> 'The <strong>Core Operations Program</strong> is a strategic initiative designed to enhance the efficiency, reliability, and scalability of our organization’s core operations. This program focuses on optimizing workflows, integrating advanced technologies, and standardizing processes across departments to support the growing demands of our business. By addressing operational bottlenecks and improving resource utilization, the program aims to drive sustained performance improvements and reduce operational risks.'
2024-12-30 15:38:32	The record with UID 'A011' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:32	The record with UID 'A009' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.' ----> 'The <strong>Continuous Improvement Transformation</strong> and <strong>Digital Desktop Transformation</strong> projects are interrelated initiatives aimed at driving operational excellence and employee productivity. Continuous Improvement lays the foundation by streamlining workflows and promoting agility, while Digital Desktop Transformation equips employees with modern tools and a seamless digital workspace to execute these enhanced processes effectively. Together, these projects create a synergy that empowers the workforce, optimizes resource utilization, and positions the organization for sustained innovation and growth.'
2024-12-30 15:38:32	The record with UID 'A007' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'Upgrade the collaboration sites in conjunction with business owners.' ----> 'The <strong>Business Continuity Management</strong> project is a strategic initiative to safeguard the organization against operational disruptions. By creating a robust framework that includes risk analysis, contingency plans, and recovery strategies, this project ensures the company’s ability to continue delivering critical services during crises. This proactive approach not only mitigates risks but also enhances stakeholder trust, operational stability, and long-term resilience, ensuring the company is prepared for any eventuality.'
2024-12-30 15:38:32	The record with UID 'A007' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '0'
2024-12-30 15:38:32	The record with UID 'A010' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'This program shall roll up all investments regarding our buildings and office space.' ----> 'The <strong>Constant Internal Delivery Enablement</strong> project is designed to streamline the execution of internal initiatives by building a robust framework for delivery excellence. By standardizing processes, optimizing resource utilization, and adopting proven methodologies, this project will ensure timely and high-quality outcomes for internal projects. This initiative not only improves operational efficiency but also fosters a culture of continuous improvement, enabling the organization to respond quickly and effectively to internal needs and strategic objectives.'
2024-12-30 15:38:32	The record with UID 'A017' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 58.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 93, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 58.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 93, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A017' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A020' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 65.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 65.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A020' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A023' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 87.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 87.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A023' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:32	The record with UID 'A024' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 69.38DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 70, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 69.38DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 70, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A024' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:32	The record with UID 'A018' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A027' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 77.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 77.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A027' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A033' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 62.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 62.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A033' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:32	The record with UID 'A019' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A019' updated from 'Timebars'! Details: Field['Cost'] :: '49937.6' ----> '0'
2024-12-30 15:38:32	The record with UID 'A036' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A021' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 38.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 38.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A022' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 46.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 50, Work Avg Score: 0,Final Score: 55, Decision: Consider Terminating | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 46.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 50, Work Avg Score: 0,Final Score: 55, Decision: Consider Terminating |'
2024-12-30 15:38:32	The record with UID 'A031' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A029' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A030' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A002' updated from 'Timebars'! Details: Field['Cost'] :: '352875' ----> '5548000'
2024-12-30 15:38:32	The record with UID '16114' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID '16156' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID '16115' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.02.01.00.00' ----> '02.03.01.00.00'
2024-12-30 15:38:32	The record with UID '16157' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.02.01.01.00' ----> '02.03.01.01.00'
2024-12-30 15:38:32	The record with UID '16157' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '382500'
2024-12-30 15:38:32	The record with UID '16117' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.03.01.00.00' ----> '01.02.01.00.00'
2024-12-30 15:38:32	The record with UID '16117' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:32	The record with UID '16159' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.03.01.01.00' ----> '01.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16159' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:33	The record with UID '16118' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.04.01.00.00' ----> '02.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16160' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.04.01.01.00' ----> '02.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16160' updated from 'Timebars'! Details: Field['Cost'] :: '48750' ----> '375000'
2024-12-30 15:38:33	The record with UID '16126' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.05.01.00.00' ----> '01.03.01.00.00'
2024-12-30 15:38:33	The record with UID '16126' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:33	The record with UID '16168' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.05.01.01.00' ----> '01.03.01.01.00'
2024-12-30 15:38:33	The record with UID '16168' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:33	The record with UID '16127' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.06.01.00.00' ----> '01.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16127' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:33	The record with UID '16169' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.06.01.01.00' ----> '01.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16169' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:33	The record with UID '16128' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.07.01.00.00' ----> '01.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16128' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:33	The record with UID '16170' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.07.01.01.00' ----> '01.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16170' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:33	The record with UID '16133' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.08.01.00.00' ----> '01.06.01.00.00'
2024-12-30 15:38:33	The record with UID '16133' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:33	The record with UID '16175' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.08.01.01.00' ----> '01.06.01.01.00'
2024-12-30 15:38:33	The record with UID '16175' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:33	The record with UID 'TT-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.00.00.00' ----> '03.02.00.00.00'
2024-12-30 15:38:33	The record with UID '16135' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.01.00.00' ----> '02.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16177' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.01.01.00' ----> '02.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16177' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '318750'
2024-12-30 15:38:33	The record with UID 'BS-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.00.00.00' ----> '02.05.00.00.00'
2024-12-30 15:38:33	The record with UID '16137' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.01.00.00' ----> '01.07.01.00.00'
2024-12-30 15:38:33	The record with UID '16137' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID '16179' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.01.01.00' ----> '01.07.01.01.00'
2024-12-30 15:38:33	The record with UID '16179' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID 'TT-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.00.00.00' ----> '03.03.00.00.00'
2024-12-30 15:38:33	The record with UID '16148' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.01.00.00' ----> '03.01.01.00.00'
2024-12-30 15:38:33	The record with UID '16190' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.01.01.00' ----> '03.01.01.01.00'
2024-12-30 15:38:33	The record with UID '16190' updated from 'Timebars'! Details: Field['Cost'] :: '22500' ----> '450000'
2024-12-30 15:38:33	The record with UID 'BS-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.00.00.00' ----> '01.07.00.00.00'
2024-12-30 15:38:33	The record with UID 'BS-2024-003' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID '16152' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.01.00.00' ----> '03.02.01.00.00'
2024-12-30 15:38:33	The record with UID '16194' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.01.01.00' ----> '03.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16194' updated from 'Timebars'! Details: Field['Cost'] :: '20437.5' ----> '412500'
2024-12-30 15:38:33	The record with UID 'TT-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.00.00.00' ----> '03.04.00.00.00'
2024-12-30 15:38:33	The record with UID '16153' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.01.00.00' ----> '03.03.01.00.00'
2024-12-30 15:38:33	The record with UID '16195' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.01.01.00' ----> '03.03.01.01.00'
2024-12-30 15:38:33	The record with UID '16195' updated from 'Timebars'! Details: Field['Cost'] :: '16500' ----> '326250'
2024-12-30 15:38:33	The record with UID 'NP-2024-008' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.00.00.00' ----> '03.01.00.00.00'
2024-12-30 15:38:33	The record with UID '16154' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.01.00.00' ----> '03.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16196' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.01.01.00' ----> '03.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16196' updated from 'Timebars'! Details: Field['Cost'] :: '19125' ----> '390000'
2024-12-30 15:38:33	The record with UID '16116' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.00.00' ----> '02.06.01.00.00'
2024-12-30 15:38:33	The record with UID '16158' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.01.00' ----> '02.06.01.01.00'
2024-12-30 15:38:33	The record with UID '16158' updated from 'Timebars'! Details: Field['Cost'] :: '24750' ----> '498750'
2024-12-30 15:38:33	The record with UID '16119' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.00.00' ----> '01.11.01.00.00'
2024-12-30 15:38:33	The record with UID '16119' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '552000'
2024-12-30 15:38:33	The record with UID '16161' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.01.00' ----> '01.11.01.01.00'
2024-12-30 15:38:33	The record with UID '16161' updated from 'Timebars'! Details: Field['Cost'] :: '26062.5' ----> '552000'
2024-12-30 15:38:33	The record with UID '16120' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.00.00' ----> '01.12.01.00.00'
2024-12-30 15:38:33	The record with UID '16120' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16162' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.01.00' ----> '01.12.01.01.00'
2024-12-30 15:38:33	The record with UID '16162' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2024-12-30 15:38:33	The record with UID '16121' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.00.00' ----> '02.07.01.00.00'
2024-12-30 15:38:33	The record with UID '16163' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.01.00' ----> '02.07.01.01.00'
2024-12-30 15:38:33	The record with UID '16163' updated from 'Timebars'! Details: Field['Cost'] :: '20437.5' ----> '405000'
2024-12-30 15:38:33	The record with UID '16129' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.00.00' ----> '01.13.01.00.00'
2024-12-30 15:38:33	The record with UID '16129' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16171' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.01.00' ----> '01.13.01.01.00'
2024-12-30 15:38:33	The record with UID '16171' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2024-12-30 15:38:33	The record with UID '16132' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.00.00' ----> '02.08.01.00.00'
2024-12-30 15:38:33	The record with UID '16174' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.01.00' ----> '02.08.01.01.00'
2024-12-30 15:38:33	The record with UID '16174' updated from 'Timebars'! Details: Field['Cost'] :: '22500' ----> '450000'
2024-12-30 15:38:33	The record with UID '16134' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.00.00' ----> '02.09.01.00.00'
2024-12-30 15:38:33	The record with UID '16176' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.01.00' ----> '02.09.01.01.00'
2024-12-30 15:38:33	The record with UID '16176' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '217500'
2024-12-30 15:38:33	The record with UID '16113' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.01.01.00.00' ----> '02.01.01.00.00'
2024-12-30 15:38:33	The record with UID '16155' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.01.01.01.00' ----> '02.01.01.01.00'
2024-12-30 15:38:33	The record with UID '16155' updated from 'Timebars'! Details: Field['Cost'] :: '30750' ----> '656000'
2024-12-30 15:38:33	The record with UID '16122' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.02.01.00.00' ----> '02.02.01.00.00'
2024-12-30 15:38:33	The record with UID '16164' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.02.01.01.00' ----> '02.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16164' updated from 'Timebars'! Details: Field['Cost'] :: '16125' ----> '348000'
2024-12-30 15:38:33	The record with UID '16123' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.03.01.00.00' ----> '01.08.01.00.00'
2024-12-30 15:38:33	The record with UID '16123' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16165' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.03.01.01.00' ----> '01.08.01.01.00'
2024-12-30 15:38:33	The record with UID '16165' updated from 'Timebars'! Details: Field['Cost'] :: '16125' ----> '340000'
2024-12-30 15:38:33	The record with UID '16125' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.04.01.00.00' ----> '03.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16167' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.04.01.01.00' ----> '03.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16167' updated from 'Timebars'! Details: Field['Cost'] :: '19312.5' ----> '390000'
2024-12-30 15:38:33	The record with UID '16131' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.05.01.00.00' ----> '02.10.01.00.00'
2024-12-30 15:38:33	The record with UID '16173' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.05.01.01.00' ----> '02.10.01.01.00'
2024-12-30 15:38:33	The record with UID '16173' updated from 'Timebars'! Details: Field['Cost'] :: '18187.5' ----> '371250'
2024-12-30 15:38:33	The record with UID 'NP-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.00.00.00' ----> '03.06.00.00.00'
2024-12-30 15:38:33	The record with UID '16136' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.01.00.00' ----> '01.09.01.00.00'
2024-12-30 15:38:33	The record with UID '16136' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '460000'
2024-12-30 15:38:33	The record with UID '16178' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.01.01.00' ----> '01.09.01.01.00'
2024-12-30 15:38:33	The record with UID '16178' updated from 'Timebars'! Details: Field['Cost'] :: '21937.5' ----> '460000'
2024-12-30 15:38:34	The record with UID 'NP-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.00.00.00' ----> '03.07.00.00.00'
2024-12-30 15:38:34	The record with UID '16138' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.01.00.00' ----> '01.10.01.00.00'
2024-12-30 15:38:34	The record with UID '16138' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '604000'
2024-12-30 15:38:34	The record with UID '16180' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.01.01.00' ----> '01.10.01.01.00'
2024-12-30 15:38:34	The record with UID '16180' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '604000'
2024-12-30 15:38:34	The record with UID 'NP-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.00.00.00' ----> '03.08.00.00.00'
2024-12-30 15:38:34	The record with UID '16139' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.01.00.00' ----> '02.11.01.00.00'
2024-12-30 15:38:34	The record with UID '16181' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.01.01.00' ----> '02.11.01.01.00'
2024-12-30 15:38:34	The record with UID '16181' updated from 'Timebars'! Details: Field['Cost'] :: '30937.5' ----> '615000'
2024-12-30 15:38:34	The record with UID 'BS-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.00.00.00' ----> '01.09.00.00.00'
2024-12-30 15:38:34	The record with UID 'BS-2024-002' updated from 'Timebars'! Details: Field['Cost'] :: '26484.4' ----> '460000'
2024-12-30 15:38:34	The record with UID '16140' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.01.00.00' ----> '02.12.01.00.00'
2024-12-30 15:38:34	The record with UID '16182' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.01.01.00' ----> '02.12.01.01.00'
2024-12-30 15:38:34	The record with UID '16182' updated from 'Timebars'! Details: Field['Cost'] :: '60187.5' ----> '558750'
2024-12-30 15:38:34	The record with UID 'NP-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.00.00.00' ----> '03.09.00.00.00'
2024-12-30 15:38:34	The record with UID '16141' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.01.00.00' ----> '03.06.01.00.00'
2024-12-30 15:38:34	The record with UID '16183' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.01.01.00' ----> '03.06.01.01.00'
2024-12-30 15:38:34	The record with UID '16183' updated from 'Timebars'! Details: Field['Cost'] :: '48375' ----> '967500'
2024-12-30 15:38:34	The record with UID 'BS-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.00.00.00' ----> '01.10.00.00.00'
2024-12-30 15:38:34	The record with UID 'BS-2024-004' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '604000'
2024-12-30 15:38:34	The record with UID '16142' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.01.00.00' ----> '03.07.01.00.00'
2024-12-30 15:38:34	The record with UID '16184' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.01.01.00' ----> '03.07.01.01.00'
2024-12-30 15:38:34	The record with UID '16184' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '318750'
2024-12-30 15:38:34	The record with UID 'BS-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.00.00.00' ----> '02.11.00.00.00'
2024-12-30 15:38:34	The record with UID '16143' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.01.00.00' ----> '03.08.01.00.00'
2024-12-30 15:38:34	The record with UID '16185' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.01.01.00' ----> '03.08.01.01.00'
2024-12-30 15:38:34	The record with UID '16185' updated from 'Timebars'! Details: Field['Cost'] :: '16312.5' ----> '318750'
2024-12-30 15:38:34	The record with UID 'BS-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.00.00.00' ----> '02.12.00.00.00'
2024-12-30 15:38:34	The record with UID '16145' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.01.00.00' ----> '03.09.01.00.00'
2024-12-30 15:38:34	The record with UID '16187' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.01.01.00' ----> '03.09.01.01.00'
2024-12-30 15:38:34	The record with UID '16187' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '761250'
2024-12-30 15:38:34	The record with UID '16166' updated from 'Timebars'! Details: Field['Cost'] :: '7312.5' ----> '281250'
2024-12-30 15:38:34	The record with UID '16130' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.02.01.00.00' ----> '02.13.01.00.00'
2024-12-30 15:38:34	The record with UID '16172' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.02.01.01.00' ----> '02.13.01.01.00'
2024-12-30 15:38:34	The record with UID '16172' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '405000'
2024-12-30 15:38:34	The record with UID 'NP-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.00.00.00' ----> '04.02.00.00.00'
2024-12-30 15:38:34	The record with UID '16144' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.01.00.00' ----> '04.02.01.00.00'
2024-12-30 15:38:34	The record with UID '16186' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.01.01.00' ----> '04.02.01.01.00'
2024-12-30 15:38:34	The record with UID '16186' updated from 'Timebars'! Details: Field['Cost'] :: '25875' ----> '517500'
2024-12-30 15:38:34	The record with UID 'TT-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.00.00.00' ----> '04.05.00.00.00'
2024-12-30 15:38:34	The record with UID '16146' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.01.00.00' ----> '04.03.01.00.00'
2024-12-30 15:38:34	The record with UID '16188' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.01.01.00' ----> '04.03.01.01.00'
2024-12-30 15:38:34	The record with UID '16188' updated from 'Timebars'! Details: Field['Cost'] :: '24750' ----> '502500'
2024-12-30 15:38:34	The record with UID 'TT-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.00.00.00' ----> '04.06.00.00.00'
2024-12-30 15:38:34	The record with UID '16147' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.01.00.00' ----> '04.04.01.00.00'
2024-12-30 15:38:34	The record with UID '16189' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.01.01.00' ----> '04.04.01.01.00'
2024-12-30 15:38:34	The record with UID '16189' updated from 'Timebars'! Details: Field['Cost'] :: '14250' ----> '288750'
2024-12-30 15:38:34	The record with UID 'TT-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.00.00.00' ----> '04.07.00.00.00'
2024-12-30 15:38:34	The record with UID '16149' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.01.00.00' ----> '04.05.01.00.00'
2024-12-30 15:38:34	The record with UID '16191' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.01.01.00' ----> '04.05.01.01.00'
2024-12-30 15:38:34	The record with UID '16191' updated from 'Timebars'! Details: Field['Cost'] :: '10125' ----> '202500'
2024-12-30 15:38:34	The record with UID 'NP-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.00.00.00' ----> '04.03.00.00.00'
2024-12-30 15:38:34	The record with UID '16150' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.01.00.00' ----> '04.06.01.00.00'
2024-12-30 15:38:34	The record with UID '16192' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.01.01.00' ----> '04.06.01.01.00'
2024-12-30 15:38:34	The record with UID '16192' updated from 'Timebars'! Details: Field['Cost'] :: '11437.5' ----> '232500'
2024-12-30 15:38:34	The record with UID 'NP-2024-007' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.00.00.00' ----> '04.04.00.00.00'
2024-12-30 15:38:34	The record with UID '16151' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.01.00.00' ----> '04.07.01.00.00'
2024-12-30 15:38:34	The record with UID '16193' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.01.01.00' ----> '04.07.01.01.00'
2024-12-30 15:38:34	The record with UID '16193' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '322500'
2024-12-30 15:38:34	Merge Operation Finished!
2025-01-03 15:47:23	The CSV Imported Successfully to MetaData
2025-01-03 15:57:56	The CSV Imported Successfully to MetaData
2025-01-04 15:44:04	The CSV Imported Successfully to Timebars
2025-01-04 15:44:39	The CSV Imported Successfully to Timebars
2025-01-05 16:27:22	The CSV Imported Successfully to AdminPanel
2025-01-05 16:27:29	The CSV Imported Successfully to Timebars
2025-01-05 16:27:46	The CSV Imported Successfully to MetaData
2025-01-05 16:31:31	The CSV Imported Successfully to AdminPanel
2025-01-05 16:31:37	The CSV Imported Successfully to Timebars
2025-01-05 16:31:46	The CSV Imported Successfully to MetaData
2025-01-05 16:35:56	The CSV Imported Successfully to AdminPanel
2025-01-05 16:36:05	The CSV Imported Successfully to Timebars
2025-01-05 16:36:13	The CSV Imported Successfully to MetaData
2025-01-05 16:36:33	The CSV Imported Successfully to Resources
2025-01-05 16:38:59	The CSV Imported Successfully to AdminPanel
2025-01-05 16:39:04	The CSV Imported Successfully to Timebars
2025-01-05 16:39:13	The CSV Imported Successfully to MetaData
2025-01-05 16:39:33	The CSV Imported Successfully to Resources
2025-01-05 16:44:05	The CSV Imported Successfully to AdminPanel
2025-01-05 16:44:14	The CSV Imported Successfully to Timebars
2025-01-05 16:44:23	The CSV Imported Successfully to MetaData
2025-01-05 16:44:29	The CSV Imported Successfully to Resources
Clear Log!

## TEMP
tbResID	tbResResourceCalendar	tbResQuantity	tbResPayRate	tbResExtSystemResID	tbResName	tbResPrimaryRole	tbResPrimarySkill	tbResNameShort	tbResLabourType	tbResPercentGeneralAvailability	tbResEmail	tbResDepartment	tbResManager	tbResTeam	tbResLocation	tbResTeamLeader	tbResSupervisor	tbResPartTimeFullTime	tbResResourceType	tbResResourceClass	tbResCostCode	tbResCustomerID	tbResSortOrder	tbResLastModified	tbResPasswordHash	tbResPIN	tbResEmail2	tbResFirstName	tbResLastName	tbResMiddleName	tbResStreet	tbResCity	tbResStateProvince	tbResZipPostalCode	tbResPhoneNo	tbResPhoneNo2	tbResCellPhoneNo	tbResCountry	tbResCompany	tbResBirthday	tbResLanguage	tbResSocialLinks	tbResCourse	tbResCourseFinishDate	tbResPhoto	tbResPOBoxNo	tbResAptNo	tbResPostalStation	tbResOccupation	tbResSignature	tbResCertNo	tbResStatus	tbResState	tbResStage	tbResStep	tbResStepNotes	tbResOffice	tbResTransDate	tbResStartDate	tbResTermDate	tbResRemarks	id
700	8	1	50		Joe Invent	R&D	Testing	JI	Human	50	joe@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A404	44	1	05-Jun-2024	111111	111111	null	null	null	null	null	null	null	null	2302
701	8	1	50		Ally HR	HR SME	IT Architecture	AH	Human	50	ally@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A405	44	2	05-Jun-2024	111111	111111																																				2303
702	8	1	50		Julia Finance	Finance SME	Procurement	JF	Human	50	julia@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A406	44	3	05-Jun-2024	111111	111111																																				2304
717	8	1	75		Ryan Tower	Engineer	Testing	RT	Human	25	ryan@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A411	44	18	05-Jun-2024	111111	111111																																				2305
719	8	1	50		Chris Java	Developer	IT Architecture	CJ	Human	25	chris@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111																																				2306
720	8	1	50		John Test	Tester	Hardware/Software Testing	JT	Human	25	john@rlan.ca	Mechanical	George Bush	Ateam	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111																																				2307
800	8	40	100		General	Catch All Role	Catch All Skill	Catchall	Generic	50									Labour		A411	44	22	07/11/2018	111111	111111																																				2308
801	8	10	100		R&D	R&D		R&D	Generic	50									Labour		A411	44	22	07/11/2018	111111	111111																																				2309
802	8	11	50		HR SME	HR SME		HR SME	Generic	50									Labour		A411	44	23	07/11/2018	111111	111111																																				2310
803	8	12	75		Finance SME	Finance SME		Finance SME	Generic	50									Labour		A411	44	24	07/11/2018	111111	111111																																				2311
804	8	13	100		Engineer	Engineer		Engineer	Generic	50									Labour		A411	44	25	07/11/2018	111111	111111																																				2312
805	8	14	50		Developer	Developer		Developer	Generic	50									Labour		A411	44	26	07/11/2018	111111	111111																																				2313
806	8	15	75		Tester	Tester		Tester	Generic	50									Labour		A411	44	27	07/11/2018	111111	111111																																				2314