Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
Please select a value from the list.
## Portfolio
Custom Report			Add desired columns first, then cliick “Run Report” to merge Timebars sheet data MetaData sheet data into this sheet. When a column name in this sheet matches a column name in Timebars or MetaData sheets, data will import and overwrite existing data.					Audit
UID	Parent	Hierarchy Order	Name	Type	Description	Executive Summary	Work Hours	Cost	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Priority Strategic	PPM Yes No Selected	PPM Select Score	PPM Selection Notes	ROM Estimate	Estimation Class	Decision Notes					Updated From Which Sheet	When last updated
Run Report

## Setup
Import / Export Configuration Sheet
Importing					Validation and Formatting
Target Sheet	Location	File Name	Import	Setting		Target Sheet	Validate YN	ReFormat YN
Timebars	/home/jcox/Downloads	tbTimebars.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Timebars	Yes	No
MetaData	/home/jcox/Downloads	tbMetaData.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		MetaData	No	No
AdminPanel	/home/jcox/Downloads	tbAdminPanel.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Go!
Fields	/home/jcox/Downloads	tbFields.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
TBMDJoined	/home/jcox/Downloads	tbMdJoined.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Tags	/home/jcox/Downloads	tbTags.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Check Missing ID’s in tbMetaData
Resources	/home/jcox/Downloads	tbResources.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Documents	/home/jcox/Downloads	tbDocuments.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
ResCalcs	/home/jcox/Downloads	tbResCalcs.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		Check Duplicate ID’s tbTimebars and tbMetaData sheets
ResCalcs2	/home/jcox/Downloads	tbResCalcs2.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
ResCalcsUsage	/home/jcox/Downloads	tbResCalcsUsage.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Baseline	/home/jcox/Downloads	tbBaseline.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
Charts	/home/jcox/Downloads	tbCharts.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
CoreReport	/home/jcox/Downloads	tbCoreReport.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false		ID Checks Results
Exporting					ID	Is in this Sheet, not the other
Target Sheet	Location	File Name	ExportName	Setting		No missing IDs found.
Timebars	/home/jcox/Downloads/ssoutputs	tbTimebars.csv	No	59/44,34,76,1,,0,false,false,true,false,false
MetaData	/home/jcox/Downloads/ssoutputs	tbMetaData.csv	No	59/44,34,76,1,,0,false,false,true,false,false
Portfolio	/home/jcox/Downloads/ssoutputs	tbPortfolioExportDec21.csv	No	59/44,34,76,1,,0,false,false,true,false,false
CoreReport	/home/jcox/Downloads/ssoutputs	tbCoreReport.csv	Yes	59/44,34,76,1,,0,false,false,true,false,false
AdminPanel	/home/jcox/Downloads/ssoutputs	tbAdminPanel.csv	Yes	60/44,34,76,1,,0,false,false,true,false,false		Format All sheets
Fields	/home/jcox/Downloads/ssoutputs	tbFields.csv	No	61/44,34,76,1,,0,false,false,true,false,false
Dashboard	/home/jcox/Downloads/ssoutputs	tbMdJoined.csv	No	62/44,34,76,1,,0,false,false,true,false,false
Tags	/home/jcox/Downloads/ssoutputs	tbTags.csv	No	63/44,34,76,1,,0,false,false,true,false,false
Resources	/home/jcox/Downloads/ssoutputs	tbResources.csv	No	64/44,34,76,1,,0,false,false,true,false,false
Documents	/home/jcox/Downloads/ssoutputs	tbDocuments.csv	No	65/44,34,76,1,,0,false,false,true,false,false
ResCalcs	/home/jcox/Downloads/ssoutputs	tbResCalcs.csv	No	66/44,34,76,1,,0,false,false,true,false,false
ResCalcs2	/home/jcox/Downloads/ssoutputs	tbResCalcs2.csv	No	67/44,34,76,1,,0,false,false,true,false,false
ResCalcsUsage	/home/jcox/Downloads/ssoutputs	tbResCalcsUsage.csv	No	69/44,34,76,1,,0,false,false,true,false,false
Baseline	/home/jcox/Downloads/ssoutputs	tbBaseline.csv	No	68/44,34,76,1,,0,false,false,true,false,false
Charts	/home/jcox/Downloads/ssoutputs	tbCharts.csv	No	69/44,34,76,1,,0,false,false,true,false,false

	Export!
				Takes 50 seconds to export small dataset

	Mandatory Rules for Timebars and MetaData Sheets
	Must have Title in cell A2 – Enter any text to suit your needs to identify this data
	Must have the text: “UID” in cell A3 on Timebars tab
	Must have the text: “MDUID” in cell A3 on MetaData tab
	Colors for bars http://materialuicolors.co

## AdminPanel
apID	ap_name	ap_HolidayDate	ap_HolidayName	apTS_Start	apStatusDate	apCustomerID	source_product_version	source_file_name	source_file_version	publish_status	aggregation_level	division	cost_center	geographic_region	apFilteredFrom	apABuseStatusDate	apABFixedSizing	apTS_WeeklyOrMonthly	apTS_WeeklyPxFactor	apTS_Finish	apHelpCoordTop	apHelpCoordLeft	apTS_MonthlyPxFactor	apFilteredFromTbID	apSchMethod	apTbVisibleLevel	totalNumberOfPeople	numberOfPeoplePerLine	pxPerPerson	apHideCompletedBarsYN	showGhostBarsYN	showBaselineBarsYN	apFilteredFromKbID	apTbProduct	apT1	apT2	apT3	apT4	apT5	apT6	apT7	apT8	apT9	apT10	apT11	apT12	apT14	apT15	apHideRiskBars	apHideIssueBars	apHideCRBars	apDefaultSort	apBarType	apBarSpacing
Admin Panel Store																																		auto filled	Task lines on/off flag	User ID linked to license	License expires on	Count of timebars for license	Project count for license	Show Intro Flag	P3Menu hide, show remove flag	Product URI	Duplicate bar counter	Hierarchy lines yes no flag	Agilebars Kanban Bar/Box Toggle	Dark Mode Toggle	Lst scroll Y value	Use tbCordTop on P3 Menu
MDUID	Name	Holiday Date	Holiday Name	TS Start	StatusDate	Customer ID	Product Version	SS File Name	SS Version	Publish Status	Aggregation Level	Division/ Dept	Cost Center	Geo. Region	Filtered From	Use Status Date (Agilebars Only)	Fixed Sizing (Agilebars Only)	TS Weekly Or Monthly	TS Weekly Px Factor	TSFinish	Help Coord Top	Help Coord Left	TS Monthly Px Factor	Filtered From Tb ID	Sch Method	Tb Visible Level	Total Number Of People	Number Of People Per Line	Px Per Person	Hide Completed Bars YN	Show Ghost Bars YN	Show Baseline Bars YN	apFilteredFromKbID	apTbProduct	apT1	apT2	apT3	apT4	apT5	apT6	apT7	apT8	apT9	apT10	apT11	apT12	apT14	apT15	Hide Risk Bars	Hide Issue Bars	Hide CR Bars	apDefaultSort	apBarType	apBarSpacing
1	Standard Config Settings	na		02-Mar-2026	02-Mar-2026	44									Canvas			Monthly	10		50	400	2	A012	Standard	L5				0	No	No	A012	CBT03	1	jcox@costbars.com	47307	39	13	doNotShowIntro	FM-OFF	CB	99	0	0	0	0	0						Medium
3	Standard Holidays	25-Dec-2026	Christmas												Timebars
4	Standard Holidays	26-Dec-2026	Boxing Day												Timebars
5	Standard Holidays	01-Jan-2027	New Years Day												Timebars
6	Standard Holidays	02-Sep-2026	Labour Day												Timebars
7	Standard Holidays	17-Mar-2026	Good Friday												Timebars
8	Standard Holidays	20-Mar-2026	Easter Monday												Timebars
9	Standard Holidays	01-May-2026	Victoria Day												Timebars
10	Standard Holidays	01-Jul-2026	Canada Day												Timebars
11	Standard Holidays	07-Aug-2026	Summer Day Off												Timebars
Import Data

## Timebars
tbID	tbSelfKey2	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	tbCoordTopP3Menu	kbCoordLeft	tbPredecessor	tbResID	tbOwner	tbBudgetHours	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbBudgetCost	tbCost	tbACost	tbCostRemaining	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbCostID	tbCostType	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbStatus	tbState	tbPriority
Timebars Data Store			tbTypeInternal	SubType / Import Data	Format							Owner																																												These are for a future workflow feature
UID	Parent	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Custom Coord Top	Lane	Predecessor	ResID	Owner	Budget Hoours	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	Budget Cost	Cost	Actual Cost	Cost Remaining	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbCostID	Cost Type	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	Status	State	Priority

## MetaData
tbMDID	tbMDParent	tbMDName	tbMDTypes	tbMDSubtype	tbMDHierarchy	tbMDProduct	tbMDNotesProject	tbMDDescription	tbMDExecutiveSummary	tbMDHealth	tbMDPriority	tbMDStatus	tbMDState	tbMDStage	tbMDPhase	tbMDCategory	tbMDGate	tbMDIssueCategory	tbMDEscalationLevel	tbMDProjectNumber	tbMDPM	tbMDExSponsor	tbMDNotes	tbMDPrimaryContact	tbMDDepartment	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDProjectType	tbMDRiskVsSizeAndComplexity	tbMDROMEstimate	tbMDEstimationClass	tbMDSize	tbMDSeniorLevelCommitment	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDYesNoSelector	tbMDPriorityStrategic	tbMDCostbarsScore	tbMDFinancialScore	tbMDDecisionStrategic	tbMDDecisionNotes	tbMDPrimaryLineOfBusiness	tbMDSponsoringDepartment	tbMDContact	tbMDContactNumber	tbMDResponsibleTeam	tbMDBusinessAdvisor	tbMDDeliveryManager	tbMDOrgManager	tbMDBenefitCostRatio	tbMDEcnomicValueAdded	tbMDInternalRateOfReturn	tbMDSunkCosts	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDOther2	tbMDBusinessOwner	tbMDBackgroundInfo	tbMDStakeholderDescription	tbMDProblemOpportunity	tbMDOptionsAnalysis	tbMDConsequence	tbMDKeyDependencies	tbMDValueProposition	tbMDSuccessCriteria	tbMDDecisionsRequired	tbMDKeyRecommendations	tbMDMarketAnalysis	tbMDPortfolioImpactAnalysis	tbMDKeyProjectMetrics	tbMDObjectivesAndScope	tbMDExpectedBenefits	tbMDCapabilitiesNeeded	tbMDImplementationApproach	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDNextSteps	tbMDWrittenBy	tbMDVersion	tbMDBCaseDateApproved	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDResID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDResponsibility	tbMDExtSystemID1	tbMDSyncNotes	tbMDStageApprover	tbMDSprintName	tbMDExtLink1	tbMDOther3	canvasNo	tbMDRefID	tbMDSortOrder	tbMDtbLastModified	tbMDShowIn	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDNotesWorkflow	tbMDContractNumber	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSeverity	tbMDContingency	tbMDMitigationPlan	tbMDMitigationStatus	tbMDProbability	tbMDImpact	tbMDScore	tbMDRiskCategory	tbMDRiskResponseStrategy	tbMDContingencyPlan	tbMDTriggerEvent	tbMDEarlyWarningIndicators	tbMDOther4	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	tbMDPrerequisitesChecklist	tbMDScheduleCommentary	tbMDBudgetCommentary	tbMDScopeCommentary	tbMDResourceCommentary	tbMDFinancialCommentary	tbMDVersion	tbPASTeamSize	tbPASStakeholderCount	tbPASTechnologyNovelty	tbPASTeamTechExperience	tbPASProjectSimilarity	tbPASDomainExperience	tbPASExternalIntegrations	tbPASVendorDependencies	tbPASCrossTeamCollaboration	tbPASRegulatoryApprovals	tbPASMarketTiming	tbPASProjectType	tbPASOverallFeasibilityScore	tbPASComplexityScore	tbPASRiskScore	tbPASPoliticalRiskScore	tbPASScaleScore	tbPASTechnologyScore	tbPASFamiliarityScore	tbPASDependencyScore	tbPASRegulatoryScore	tbPASMarketScore	tbPASAssessmentVersion	tbPASStatus	tbPASApprovalRequired	tbPASAssessmentDate	tbPASAssessorName
MetaData Store		Set Picklists / Import Data / Format	tbType / Toggle Cols	SubType		Product				Schedule Status	Timebar Priority	Timebar Status	WF State	Stage	Phase	Category	Gate	Issue Category	Escalation Level						Department	Health Overall	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Type Of Initiative	Risk Vs Size	Budget Estimate	Estimation Class	Size	Executive Commitment	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Selected	Strategic Priority					Primary Line Of Business	Sponsoring Department			Responsible Team	Business Advisor	Delivery Manager	Organization Manager													x										x			x			x		x	x					Primary Skill	Primary Role	Responsibility																								Risk Probability	Risk Impact		Risk Category																					Team Size	Stakeholder Count	Technology Novelty	Team Tech Experience	Project Similarity	Domain Experience	External Integrations	Vendor Dependencies	Cross Team Collaboration	Regulatory Approvals	Market Timing	Project Assessment Type	Project Assessment Status
MDUID	Parent	Name	Type	SubType	Hierarchy Order	Product	Project Notes	Description	Executive Summary	Schedule Status	Priority	Status	WF State	PPM Stage	PMI Phase	Category	Gate	Issue Category	Escelation Level	Project Number	PM	Executive Sponsor	General Notes	Primary Contact	Department	Health Overall	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Initiative Type	Risk Vs Size And Complexity	ROM Estimate	Estimation Class	Size	Senior Level Committment	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Selected	Strategic Priority/Value	Costbars OA Risk Score	Financial Score	Strategic Decision	Decision Notes	Primary Line Of Business	Sponsoring Department	Contact	Contact Number	Responsible Team	Business Advisor	Delivery Manager	Organization Manager	Benefit Cost Ratio	Ecnomic Value Added	Internal Rate Of Return	Sunk Costs	Net Present Value	Opportunity Cost	Payback Period	Other Financial Score??	Business Owner	Background Info	Stakeholder Description	Problem Opportunity	Options Analysis	Consequence of Inaction	Key Dependencies	Value Proposition	Success Criteria	Decisions Required	Key Recommendations	Market Analysis	Portfolio Impact Analysis	Key Project Metrics	Objectives and Scope	Expected Benefits	Capabilities Needed	Implementation Approach	Constraints Assumptions	Cost Benefit Analysis	Next Steps	Written By	Version	B Case Date Approved	WBS	Weighting	Location	ResID	Primary Skill	Primary Role	Responsibility	Ext ID	Sync Notes	Stage Approver	Sprint Name	tbMDExtLink1	Other3	canvasNo	tbMDRefID	Sort Order	Last Modified	Show In	Customer ID	Azure ID	Name Short	Notes Workflow	Contract Number	Portfolio	Program	Program Activity Alignment	Severity	Contingency	Mitigation Plan	Mitigation Status	Probability	Impact	Score	Risk Category	Risk Response Strategy	Contingency Plan	Trigger Event	Early Warning Indicators	tbMDOther4	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	Prerequisites Checklist	Schedule Commentary	Budget Commentary	Scope Commentary	Resource Commentary	Financial Commentary	Version	Team Size	Stakeholder Count	Technology Novelty	Team Tech Experience	Project Similarity	Domain Experience	External Integrations	Vendor Dependencies	Cross Team Collaboration	Regulatory Approvals	Market Timing	Project Type	Overall Feasibility Score	Complexity Score	Tech Risk Score	Political Risk Score	Scale Score	Technology Score	Familiarity Score	Dependency Score	Regulatory Score	Market Score	Assessment Version	PAS Status	PAS Approval Required	Assessment Date	Assessor Name

## Baseline
tbID	tbSelfKey2	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	tbCoordTopP3Menu	kbCoordLeft	tbPredecessor	tbResID	tbOwner	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbBudget	tbBudgetRollupYN	tbCost	tbACost	tbCostRemaining	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbCostID	tbCostType	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbStatus	tbState	tbPriority
Baseline Data Store				Mandatory		Mandatory	Mandatory														Mandatory	Mandatory
UID	Parent	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Custom Coord Top	Lane	Predecessor	ResID	Owner	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	Budget	Budget Rollup YN	Cost	Actual Cost	Cost Remaining	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbCostID	Cost Type	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	Status	State	Priority
Import Data

## Resources
tbResID	tbResResourceCalendar	tbResQuantity	tbResPayRate	tbResExtSystemResID	tbResName	tbResPrimaryRole	tbResNameShort	tbResTeam	tbResPrimarySkill	tbResLabourType	tbResPercentGeneralAvailability	tbResEmail	tbResDepartment	tbResManager	tbResLocation	tbResTeamLeader	tbResSupervisor	tbResPartTimeFullTime	tbResResourceType	tbResResourceClass	tbResCostCode	tbResCustomerID	tbResSortOrder	tbResLastModified	tbResPasswordHash	tbResPIN	tbResEmail2	tbResFirstName	tbResLastName	tbResMiddleName	tbResStreet	tbResCity	tbResStateProvince	tbResZipPostalCode	tbResPhoneNo	tbResPhoneNo2	tbResCellPhoneNo	tbResCountry	tbResCompany	tbResBirthday	tbResLanguage	tbResSocialLinks	tbResCourse	tbResCourseFinishDate	tbResPhoto	tbResPOBoxNo	tbResAptNo	tbResPostalStation	tbResOccupation	tbResSignature	tbResCertNo	tbResStatus	tbResState	tbResStage	tbResStep	tbResStepNotes	tbResOffice	tbResTransDate	tbResStartDate	tbResTermDate	tbResRemarks
Resources (not used in Agilebars)					Import Data	Primary Role / Format			Primary Skill	Labour Type			Resource Department	Manager	Location	Team Leader	Supervisor	Parttime Fulltime	Resource Type	Resource Class
ResID	Calendar	Qty Resources	Pay Rate	ExtResID	Name	Primary Role *	Name Short	Team	Primary Skill *	Labour Type	Default Percent Available	Res Email	Res Department	Res Manager	Res Location	Team Leader	Res Supervisor	Part or Full Time	Res Type	Res Class	Cost Code	CustID	Sort Order	Last Modified	Password Hash	PIN	tbResEmail2	tbResFirstName	tbResLastName	tbResMiddleName	tbResStreet	tbResCity	tbResStateProvince	tbResZipPostalCode	tbResPhoneNo	tbResPhoneNo2	tbResCellPhoneNo	tbResCountry	tbResCompany	tbResBirthday	tbResLanguage	tbResSocialLinks	tbResCourse	tbResCourseFinishDate	tbResPhoto	tbResPOBoxNo	tbResAptNo	tbResPostalStation	tbResOccupation	tbResSignature	tbResCertNo	tbResStatus	tbResState	tbResStage	tbResStep	tbResStepNotes	tbResOffice	tbResTransDate	tbResStartDate	tbResTermDate	tbResRemarks
700	8	1	50		Joe Invent	R&D	JI	Ateam	Testing	Human	50	joe@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A404	44	1	05-Jun-2024	111111	111111	null	null	null	null	null	null	null	null
701	8	1	50		Ally HR	HR SME	AH	Ateam	IT Architecture	Human	50	ally@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A405	44	2	05-Jun-2024	111111	111111
702	8	1	50		Julia Finance	Finance SME	JF	Ateam	Procurement	Human	50	julia@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A406	44	3	05-Jun-2024	111111	111111
717	8	1	75		Ryan Tower	Engineer	RT	Ateam	Testing	Human	25	ryan@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	Permenant	A411	44	18	05-Jun-2024	111111	111111
719	8	1	50		Chris Java	Developer	CJ	Ateam	IT Architecture	Human	25	chris@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111
720	8	1	50		John Test	Tester	JT	Ateam	Project Manager	Human	25	john@rlan.ca	Mechanical	George Bush	Ottawa	App Team	Helen Hunt	Full Time	Labour	External	A411	44	20	05-Jun-2024	111111	111111
800	8	40	100		General Role (Do not use with other roles)	General Role	Gnrl Role		na	Generic	50								Labour		A411	44	22	07/11/2018	111111	111111

## Tags
tbTagID	tbTagGroup	tbTagName	tbTagSortOrder	tbTagOpFieldName	tbTagOpInternalName	tbTagTbInternalName	tbTagOpTagName	tbTagOpCustomOptionID	tbTagEntity	tbTagPopular	tbTagNameShort	tbTagPurpose	tbTagDescription	tbTagOwner	tbTagCustomerID	tbTagLastModified
Tags Data Store														Do not change
tbTagID	Picklist Name	Tag Name	Priority Order	OP Field Name	OP Internal Name	Tb Internal Name	OP Tag Name	OP Custom Option ID	tbTagEntity	tbTagPopular	tbTagNameShort	tbTagPurpose	tbTagDescription	tbTagOwner	tbTagCustomerID	tbTagLastModified
1	Benefit Cost Ratio	> 5:1				tbMDBenefitCostRatio					> 5:1	Tagging financial values on business case.
2	Benefit Cost Ratio	3:1 - 5:1				tbMDBenefitCostRatio					3:1 - 5:1	Tagging financial values on business case.
3	Benefit Cost Ratio	2:1 - 3:1				tbMDBenefitCostRatio					2:1 - 3:1	Tagging financial values on business case.
4	Benefit Cost Ratio	1.5:1 - 2:1				tbMDBenefitCostRatio					1.5:1 - 2:1	Tagging financial values on business case.
5	Benefit Cost Ratio	1:1 - 1.5:1				tbMDBenefitCostRatio					1:1 - 1.5:1	Tagging financial values on business case.
6	Benefit Cost Ratio	Not Assessed				tbMDBenefitCostRatio					Not Assessed	Tagging financial values on business case.
7	Budget Estimate	0 to 100K	1	ROM Estimate	customField25	tbMDROMEstimate	0 to 100K	91	ProjList		0 to 100K	Project Tagging	NA	PMO		1-Nov-22
8	Budget Estimate	101K to 300K	2	ROM Estimate	customField25	tbMDROMEstimate	101K to 300K	93	ProjList		101K to 300K	Project Tagging	NA	PMO		1-Nov-22
9	Budget Estimate	301K to 1000K	3	ROM Estimate	customField25	tbMDROMEstimate	301K to 1000K	94	ProjList		301K to 1000K	Project Tagging	NA	PMO		1-Nov-22
10	Budget Estimate	1001K to 5000K	4	ROM Estimate	customField25	tbMDROMEstimate	1001K to 5000K	92	ProjList		1001K to 5000K	Project Tagging	NA	PMO		1-Nov-22
11	Budget Estimate	5000K Plus	5	ROM Estimate	customField25	tbMDROMEstimate	1000K Plus	95	ProjList		1000K Plus	Project Tagging	NA	PMO		1-Nov-22
12	Business Advisor	Advisor 1	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 1	48	ProjList		Mike Ba	Project Tagging	NA	PMO		1-Nov-22
13	Business Advisor	Advisor 2	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 2	49	ProjList		Joe Ba	Project Tagging	NA	PMO		1-Nov-22
14	Business Advisor	Advisor 3	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 3	50	ProjList		Sally Ba	Project Tagging	NA	PMO		1-Nov-22
15	Business Advisor	Advisor 4	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 4	51	ProjList		Joe Ba	Project Tagging	NA	PMO		1-Nov-22
16	Business Advisor	Advisor 5	0	Business Advisor	customField17	tbMDBusinessAdvisor	Advisor 5	52	ProjList		Sally Ba	Project Tagging	NA	PMO		1-Nov-22
17	Calendar	4	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		4	For calculating wok on an Allocation	NA	PMO		1-Nov-22
18	Calendar	7.5	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		7.5	For calculating wok on an Allocation	NA	PMO		1-Nov-22
19	Calendar	8	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		8	For calculating wok on an Allocation	NA	PMO		1-Nov-22
20	Calendar	24	0	Calendar	customfield122	tbResResourceCalendar	na	na	ResList		24	For calculating wok on an Allocation	NA	PMO		1-Nov-22
21	Category	SW Upgrade	1						General	General	SW Upgrade	Technology aspect of project or initiative	NA
22	Category	HW Upgrade	2						General	General	HW Upgrade	Technology aspect of project or initiative	NA
23	Category	HW, SW System Upgrade	3						General	General	HW, SW System Upgrade	Technology aspect of project or initiative	NA
24	Category	New HW, SW System	4						General	General	New HW, SW System	Technology aspect of project or initiative	NA
25	Category	Business System Configuration	1						General	General	Business System Configuration	Technology aspect of project or initiative	NA
26	Category	Cloud Service New or Upgrade	2						General	General	Cloud Service New or Upgrade	Technology aspect of project or initiative	NA
27	Category	New Ground to Cloud Service	3						General	General	New Ground to Cloud Service	Technology aspect of project or initiative	NA
28	Category	Upgrade Ground to Cloud Service	4						General	General	Upgrade Ground to Cloud Service	Technology aspect of project or initiative	NA
29	Category	Not Assessed	3						General	General	Not Assessed	Technology aspect of project or initiative	NA
30	Category	Not Applicable	4						General	General	Not Applicable	Technology aspect of project or initiative	NA
31	Cost Code	A26	1			tbResCostCode			ResList		A26	Resource or person tagging	NA	PMO		1-Nov-22
32	Cost Code	B44	2						ResList		B44	Resource or person tagging	NA	PMO		1-Nov-22
33	Cost Code	C99	3						ResList		C99	Resource or person tagging	NA	PMO		1-Nov-22
34	Cost Code	D11	4						ResList		D11	Resource or person tagging	NA	PMO		1-Nov-22
35	Cost Code	E11	5						ResList		E11	Resource or person tagging	NA	PMO		1-Nov-22
36	Cost Code	E112	6						ResList		E112	Resource or person tagging	NA	PMO		1-Nov-22
37	Cost Type	Equipment							ProjList		Equipment	Tagging of Project, Sub-Project or Task	NA	PMO
38	Cost Type	Hardware							ProjList		Hardware	Tagging of Project, Sub-Project or Task	NA	PMO
39	Cost Type	Software							ProjList		Software	Tagging of Project, Sub-Project or Task	NA	PMO
40	CR Category	Strategic							General	General	Orgnizational		NA
41	CR Category	Financial							General	General	Orgnizational		NA
42	CR Category	Operational							General	General	Orgnizational		NA
43	CR Category	Technical							General	General	Orgnizational		NA
44	CR Category	Organizational							General	General	Orgnizational		NA
45	CR Requestor	Jim Soda	0			tbMDContact			ProjList	ProjList	CR	Identify a CR requester	NA	PMO		1-Nov-22
46	CR Requestor	Allyson Soda	0			tbMDContact			ProjList	ProjList	CR	Identify a CR requester	NA	PMO		1-Nov-22
47	Cross Team Collaboration	Single team				tbPASCrossTeamCollaboration			PAS	Scores 100	Single team	Tagging the Project Assessment Form
48	Cross Team Collaboration	2-3 teams				tbPASCrossTeamCollaboration			PAS		2-3 teams	Tagging the Project Assessment Form
49	Cross Team Collaboration	4-6 teams				tbPASCrossTeamCollaboration			PAS		4-6 teams	Tagging the Project Assessment Form
50	Cross Team Collaboration	7-10 teams				tbPASCrossTeamCollaboration			PAS		7-10 teams	Tagging the Project Assessment Form
51	Cross Team Collaboration	Many teams/departments				tbPASCrossTeamCollaboration			PAS		Many teams/departments	Tagging the Project Assessment Form
52	Delivery Manager	Manager of Engineering	1	Delivery Manager	customField6	tbMDDeliveryManager	Manager of Engineering	12	ProjList		MarioC	Project Tagging	NA	PMO		1-Nov-22
53	Delivery Manager	Manager of Integration	2	Delivery Manager	customField6	tbMDDeliveryManager	Manager of Integration	14	ProjList		SallyE	Project Tagging	NA	PMO		1-Nov-22
54	Delivery Manager	Manager of IT	2	Delivery Manager	customField6	tbMDDeliveryManager	Manager of IT	13	ProjList		SallyE	Project Tagging	NA	PMO		1-Nov-22
55	Department	Sales and Marketing	1	Department	customField5	tbMDDepartment	Sales and Marketing	5	ProjList		Marketing	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
56	Department	Operations	2	Department	customField5	tbMDDepartment	Engineering	6	ProjList		Engineering	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
57	Department	Finance	3	Department	customField5	tbMDDepartment	Manufacturing	7	ProjList		MFG	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
58	Department	Procurement	4	Department	customField5	tbMDDepartment	Procurement	8	ProjList		Purch	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
59	Department	Business Development	5	Department	customField5	tbMDDepartment	Business Development	9	ProjList		BD	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
60	Department	Research and Development	6	Department	customField5	tbMDDepartment	Research and Development	10	ProjList		R&D	Define what area of the business is responsible for Timebar	NA	PMO		1-Nov-22
61	Document Purpose	Approval Document	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
62	Document Purpose	Business Case	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
63	Document Purpose	Common Help	0						General		NA	Key for pages appearing on help accordions	NA	PMO		1-Nov-22
64	Document Purpose	Contact Us Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
65	Document Purpose	Gate Help	0						General		NA	Key for the Help pages on Gating forms	NA	System		1-Nov-22
66	Document Purpose	General Web Page	0						General		NA	To identify web pages	NA	PMO		1-Nov-22
67	Document Purpose	Kanban Help	0						General		NA	Key for pages appearing on help accordions	NA	PMO		1-Nov-22
68	Document Purpose	Main Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
69	Document Purpose	Marketing Page	0						General		NA	To identify web pages in marketing site	NA	System		1-Nov-22
70	Document Purpose	Project Charter	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
71	Document Purpose	Timebar Help	0						General		NA	Key for pages appearing on help accordions	NA	System		1-Nov-22
72	Document Status	Approved	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
73	Document Status	Canceled	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
74	Document Status	First Draft	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
75	Document Status	In Progress	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
76	Document Type	HTML	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
77	Document Type	MS Word	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
78	Document Type	PDF	0						General		NA	for tagging documents	NA	PMO		1-Nov-22
79	Domain Experience	Extensive experience				tbPASDomainExperience			PAS	Scores 100	Extensive experience	Tagging the Project Assessment Form
80	Domain Experience	Good experience				tbPASDomainExperience			PAS		Good experience	Tagging the Project Assessment Form
81	Domain Experience	Some experience				tbPASDomainExperience			PAS		Some experience	Tagging the Project Assessment Form
82	Domain Experience	Limited experience				tbPASDomainExperience			PAS		Limited experience	Tagging the Project Assessment Form
83	Domain Experience	New domain				tbPASDomainExperience			PAS		New domain	Tagging the Project Assessment Form
84	Escalation Level	Executives	2			tbMDEscalationLevel	Executives		General		Executives		NA	PMO		1-Nov-22
85	Escalation Level	Directors	3			tbMDEscalationLevel	Directors		General		Directors		NA	PMO		1-Nov-22
86	Escalation Level	Project Office	4			tbMDEscalationLevel	Project Office		General		Project Office		NA	PMO		1-Nov-22
87	Escalation Level	Not Assessed	5			tbMDEscalationLevel	Not Assessed		General		Not Assessed		NA	PMO		1-Nov-22
88	Estimation Class	SWAG	0	Estimation Class	customField18	tbMDEstimationClass	Class A	53	ProjList		Class A	Project Tagging	NA	PMO		1-Nov-22
89	Estimation Class	Based on History	0	Estimation Class	customField18	tbMDEstimationClass	Class B	54	ProjList		Class B	Project Tagging	NA	PMO		1-Nov-22
90	Estimation Class	Resource Driven	0	Estimation Class	customField18	tbMDEstimationClass	Class C	55	ProjList		Class C	Project Tagging	NA	PMO		1-Nov-22
91	Executive Commitment	Full				tbMDSeniorLevelCommitment					Full	Full sponsorship & active support
92	Executive Commitment	Strong				tbMDSeniorLevelCommitment					Strong	Strong executive backing
93	Executive Commitment	Moderate				tbMDSeniorLevelCommitment					Moderate	Moderate executive support
94	Executive Commitment	Limited				tbMDSeniorLevelCommitment					Limited	Limited executive involvement
95	Executive Commitment	Not Clear				tbMDSeniorLevelCommitment					Not Clear	No clear executive sponsor
96	Executive Commitment	Not Assessed				tbMDSeniorLevelCommitment					Not Assessed	Not Assessed
97	Executive Sponsor	Sally Exec	0						ProjList		Exec Sponsor	Project Tagging	NA	PMO		1-Nov-22
98	Expected Hours Per Week	5	0						ResList		5	Use for estimating work needs	NA	PMO		1-Nov-22
99	Expected Hours Per Week	10	0						ResList		10	Use for estimating work needs	NA	PMO		1-Nov-22
100	External Integrations	None				tbPASExternalIntegrations			PAS	Scores 100	None	Tagging the Project Assessment Form
101	External Integrations	1-2 simple integrations				tbPASExternalIntegrations			PAS		1-2 simple integrations	Tagging the Project Assessment Form
102	External Integrations	3-5 moderate integrations				tbPASExternalIntegrations			PAS		3-5 moderate integrations	Tagging the Project Assessment Form
103	External Integrations	5+ complex integrations				tbPASExternalIntegrations			PAS		5+ complex integrations	Tagging the Project Assessment Form
104	External Integrations	Many critical integrations				tbPASExternalIntegrations			PAS		Many critical integrations	Tagging the Project Assessment Form
105	ExtSystemResID	456M23	0						ResList		456M23	Use to tie into existing systems in the organization	NA	PMO		1-Nov-22
106	ExtSystemResID	456M24	0						ResList		456M24	Use to tie into existing systems in the organization	NA	PMO		1-Nov-22
107	Field Name	tbMDID	79						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
108	Field Name	tbMDName	80						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
109	Field Name	tbMDProjectType	81						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
110	Field Name	tbMDPortfolio	82						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
111	Field Name	tbMDProgram	83						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
112	Field Name	tbMDExecutiveSummary	84						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
113	Field Name	tbMDGate	85						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
114	Field Name	tbMDDeliveryManager	86						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
115	Field Name	tbMDBusinessAdvisor	87						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
116	Field Name	tbMDBusinessOwner	88						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
117	Field Name	tbMDEstimationClass	89						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
118	Field Name	tbMDROMEstimate	90						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
119	Field Name	tbMDInvestmentCategory	91						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
120	Field Name	tbMDInvestmentInitiative	92						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
121	Field Name	tbMDInvestmentObjective	93						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
122	Field Name	tbMDInvestmentStrategy	94						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
123	Field Name	tbMDPriorityStrategic	95						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
124	Field Name	tbMDCustomerID	96						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
125	Field Name	tbMDAzureID	97						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
126	Field Name	tbMDNameShort	98						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
127	Field Name	tbMDProjectNumber	99						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
128	Field Name	tbMDDescription	100						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
129	Field Name	tbMDNotes	101						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
130	Field Name	tbMDExtLink1	102						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
131	Field Name	tbMDExtSystemID1	103						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
132	Field Name	tbMDSortOrder	104						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
133	Field Name	tbMDtbLastModified	105						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
134	Field Name	tbMDPriority	106						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
135	Field Name	tbMDStatus	107						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
136	Field Name	tbMDState	108						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
137	Field Name	tbMDSeverity	109						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
138	Field Name	tbMDStage	110						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
139	Field Name	tbMDPhase	111						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
140	Field Name	tbMDCategory	112						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
141	Field Name	tbMDHealth	113						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
142	Field Name	tbMDResponsibility	114						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
143	Field Name	tbMDDepartment	115						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
144	Field Name	tbMDExSponsor	116						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
145	Field Name	tbMDPM	117						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
146	Field Name	tbMDShowIn	118						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
147	Field Name	tbMDYesNoSelector	119						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
148	Field Name	tbMDProduct	120						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
149	Field Name	tbMDContact	121						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
150	Field Name	tbMDWBS	122						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
151	Field Name	tbMDWeighting	123						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
152	Field Name	tbMDLocation	124						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
153	Field Name	tbMDPrimarySkill	125						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
154	Field Name	tbMDPrimaryRole	126						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
155	Field Name	tbMDOther2	127						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
156	Field Name	tbMDOther3	128						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
157	Field Name	tbMDOther4	129						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
158	Field Name	canvasNo	130						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
159	Field Name	tbMDProgActivityAlignment	131						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
160	Field Name	tbMDBackgroundInfo	132						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
161	Field Name	tbMDConsequence	133						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
162	Field Name	tbMDExpectedBenefits	134						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
163	Field Name	tbMDProblemOpportunity	135						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
164	Field Name	tbMDCapabilitiesNeeded	136						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
165	Field Name	tbMDSeniorLevelCommittment	137						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
166	Field Name	tbMDSprintName	138						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
167	Field Name	tbMDStakeholderDescription	139						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
168	Field Name	tbMDHealthCost	140						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
169	Field Name	tbMDHealthHours	141						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
170	Field Name	tbMDHealthIssues	142						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
171	Field Name	tbMDHealthOverall	143						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
172	Field Name	tbMDHealthRisk	144						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
173	Field Name	tbMDHealthSchedule	145						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
174	Field Name	tbMDHealthScope	146						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
175	Field Name	tbMDBenefitCostRatio	147						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
176	Field Name	tbMDConstraintsAssumptions	148						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
177	Field Name	tbMDContractNumber	149						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
178	Field Name	tbMDCostBenefitAnalysis	150						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
179	Field Name	tbMDEcnomicValueAdded	151						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
180	Field Name	tbMDInternalRateOfReturn	152						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
181	Field Name	tbMDNetPresentValue	153						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
182	Field Name	tbMDOpportunityCost	154						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
183	Field Name	tbMDOrgManager	155						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
184	Field Name	tbMDPaybackPeriod	156						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
185	Field Name	tbMDRiskVsSizeAndComplexity	157						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
186	Field Name	tbMDSize	158						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
187	Field Name	tbMDStageApprover	159						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
188	Field Name	tbMDSunkCosts	160						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
189	Field Name	tbMDWrittenBy	161						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
190	Field Name	tbMDPrimaryLineOfBusiness	162						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
191	Field Name	tbMDNotesWorkflow	163						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
192	Field Name	tbMDSyncNotes	164						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
193	Field Name	tbMDSponsoringDepartment	165						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
194	Field Name	tbMDPrimaryContact	166						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
195	Field Name	tbMDContactNumber	167						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
196	Field Name	tbMDResponsibleTeam	168						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
197	Field Name	tbMDNotesProject	169						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
198	Field Name	tbMDOther5	170						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
199	Field Name	tbMDOther6	171						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
200	Field Name	tbMDOther7	172						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
201	Field Name	tbMDOther8	173						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
202	Field Name	tbMDOther9	174						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
203	Field Name	tbMDOther10	175						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
204	Field Name	tbMDOther11	176						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
205	Field Name	tbMDOther12	177						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
206	Field Name	tbMDRefID	178						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
207	Field Name	tbID	179						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
208	Field Name	tbSelfKey2	180						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
209	Field Name	tbCoordTop	181						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
210	Field Name	tbCoordLeft	182						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
211	Field Name	tbHierarchyOrder	183						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
212	Field Name	tbName	184						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
213	Field Name	tbType	185						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
214	Field Name	tbL1	186						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
215	Field Name	tbL2	187						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
216	Field Name	tbL3	188						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
217	Field Name	tbL4	189						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
218	Field Name	tbL5	190						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
219	Field Name	tbOwner	191						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
220	Field Name	tbStart	192						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
221	Field Name	tbFinish	193						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
222	Field Name	tbDuration	194						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
223	Field Name	tbAStart	195						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
224	Field Name	tbAFinish	196						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
225	Field Name	tbRemainingDuration	197						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
226	Field Name	tbResID	198						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
227	Field Name	tbCalendar	199						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
228	Field Name	tbPercentTimeOn	200						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
229	Field Name	tbWork	201						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
230	Field Name	tbAWork	202						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
231	Field Name	tbWorkRemaining	203						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
232	Field Name	tbPercentComplete	204						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
233	Field Name	tbCost	205						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
234	Field Name	tbAcost	206						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
235	Field Name	tbCostRemaining	207						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
236	Field Name	tbPayRate	208						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
237	Field Name	tbCostType	209						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
238	Field Name	tbCostID	210						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
239	Field Name	tbConstraintType	211						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
240	Field Name	tbConstraintDate	212						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
241	Field Name	tbFloat	213						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
242	Field Name	tbFreeFloat	214						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
243	Field Name	tbExpHoursPerWeek	215						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
244	Field Name	canvasNo	216						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
245	Field Name	tbCustomerID	217						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
246	Field Name	tbMetaDataID	218						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
247	Field Name	tbBLID	219						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
248	Field Name	tbPredecessor	220						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
249	Field Name	tbAzureID	221						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
250	Field Name	tbCoordRight	222						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
251	Field Name	tbBarColor	223						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
252	Field Name	tbTextColor	224						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
253	Field Name	kbCoordLeft	225						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
254	Field Name	kbCoordTop	226						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
255	Field Name	focdItemCoordLeft	227						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
256	Field Name	focdItemCoordTop	228						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
257	Field Name	tbDocID	229						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
258	Field Name	tbDocName	230						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
259	Field Name	tbDocNameShort	231						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
260	Field Name	tbDocStatus	232						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
261	Field Name	tbDocPurpose	233						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
262	Field Name	tbDocWrittenBy	234						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
263	Field Name	tbDocBriefDescription	235						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
264	Field Name	tbDocCustomerID	236						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
265	Field Name	tbDocType	237						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
266	Field Name	tbDocHTMLContent	238						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
267	Field Name	tbDocGroup	239						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
268	Field Name	tbDocOwner	240						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
269	Field Name	tbDocPopular	241						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
270	Field Name	tbDocLastModified	243						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
271	Field Name	tbDocApprovedBy	244						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
272	Field Name	tbDocL1	245						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
273	Field Name	tbDocL2	246						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
274	Field Name	tbDocL3	247						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
275	Field Name	tbDocL4	248						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
276	Field Name	tbDocL5	249						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
277	Field Name	tbDocCardImage	250						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
278	Field Name	tbResID	251						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
279	Field Name	tbResName	252						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
280	Field Name	tbResNameShort	253						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
281	Field Name	tbResPrimarySkill	254						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
282	Field Name	tbResPrimaryRole	255						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
283	Field Name	tbResDepartment	256						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
284	Field Name	tbResManager	257						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
285	Field Name	tbResPayRate	258						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
286	Field Name	tbResTeam	259						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
287	Field Name	tbResLocation	260						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
288	Field Name	tbResTeamLeader	261						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
289	Field Name	tbResSupervisor	262						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
290	Field Name	tbResPartTimeFullTime	263						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
291	Field Name	tbResResourceType	264						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
292	Field Name	tbResResourceClass	265						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
293	Field Name	tbResResourceCalendar	266						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
294	Field Name	tbResPercentGeneralAvailability	267						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
295	Field Name	tbResCostCode	268						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
296	Field Name	tbResCustomerID	269						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
297	Field Name	tbResExtSystemResID	270						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
298	Field Name	tbResSortOrder	271						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
299	Field Name	tbResLastModified	272						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
300	Field Name	tbResExtSystemResID	273						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
301	Field Name	tbResCoordTop	274						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
302	Field Name	tbResCoordLeft	275						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
303	Field Name	tbResLabourType	276						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
304	Field Name	tbResEmail	277						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
305	Field Name	tbResPasswordHash	278						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
306	Field Name	tbResPIN	279						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
307	Field Name	tbResAzureID	280						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
308	Field State	Disabled	1						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
309	Field State	Editable	2						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
310	Field Type	Editor	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
311	Field Type	NoPicklist	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
312	Field Type	WithPicklist	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
313	Field Type	Band	7						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
314	Form Name	ALLOC1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
315	Form Name	ALLOC2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
316	Form Name	DOC1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
317	Form Name	DOC2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
318	Form Name	other1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
319	Form Name	other2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
320	Form Name	PF1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
321	Form Name	PF2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
322	Form Name	PJ1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
323	Form Name	PJ2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
324	Form Name	PJ3	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
325	Form Name	SPJ1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
326	Form Name	Task1	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
327	Form Name	Task2	6						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
328	Gate	1 Approved to Design	0	Gate	customField19	tbMDGate	1 Approved to Design	57	ProjList		1 Approved to Design	Project Tagging	NA	PMO		1-Nov-22
329	Gate	2 Approved to Develop	0	Gate	customField19	tbMDGate	2 Approved to Develop	58	ProjList		2 Approved to Develop	To confirm that the business case is sufficiently compelling to justify, sustain and guide the project; to identify any shortcomings in readiness for action before approval; and to confirm that key identified risks can be managed.	NA	System		1-Nov-22
330	Gate	3 Approved to Implement	0	Gate	customField19	tbMDGate	3 Approved to Implement	59	ProjList		3 Approved to Implement	To ensure that the resources, support and governance necessary for successful execution are in place prior to deployment	NA	System		1-Nov-22
331	Gate	Not Applicable	0	Gate	customField19	tbMDGate	Not Applicable	60	ProjList		Not Applicable	To confirm completion, assess the extent to which the project has achieved its goals, and provide an assessment of value for money.	NA	System		1-Nov-22
332	Health Cost	Green	1	Health Cost	customField53	tbMDHealthCost	Green	151	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
333	Health Cost	Yellow	2	Health Cost	customField53	tbMDHealthCost	Yellow	152	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
334	Health Cost	Not Assessed	3	Health Cost	customField53	tbMDHealthCost	Not Assessed	194	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
335	Health Cost	Red	3	Health Cost	customField53	tbMDHealthCost	Red	153	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
336	Health Hours	Green	1	Health Hours	customField54	tbMDHealthHours	Green	154	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
337	Health Hours	Yellow	2	Health Hours	customField54	tbMDHealthHours	Yellow	155	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
338	Health Hours	Not Assessed	3	Health Hours	customField54	tbMDHealthHours	Not Assessed	195	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
339	Health Hours	Red	3	Health Hours	customField54	tbMDHealthHours	Red	156	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
340	Health Issues	Green	1	Health Issues	customField55	tbMDHealthIssues	Green	157	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
341	Health Issues	Yellow	2	Health Issues	customField55	tbMDHealthIssues	Yellow	158	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
342	Health Issues	Not Assessed	3	Health Issues	customField55	tbMDHealthIssues	Not Assessed	196	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
343	Health Issues	Red	3	Health Issues	customField55	tbMDHealthIssues	Red	159	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
344	Health Overall	Green	1	Health Overall	customField56	tbMDHealthOverall	Green	160	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
345	Health Overall	Yellow	2	Health Overall	customField56	tbMDHealthOverall	Yellow	161	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
346	Health Overall	Not Assessed	3	Health Overall	customField56	tbMDHealthOverall	Not Assessed	199	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
347	Health Overall	Red	3	Health Overall	customField56	tbMDHealthOverall	Red	162	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
348	Health Risk	Green	1	Health Risk	customField57	tbMDHealthRisk	Green	163	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
349	Health Risk	Yellow	2	Health Risk	customField57	tbMDHealthRisk	Yellow	164	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
350	Health Risk	Not Assessed	3	Health Risk	customField57	tbMDHealthRisk	Not Assessed	215	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
351	Health Risk	Red	3	Health Risk	customField57	tbMDHealthRisk	Red	165	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
352	Health Schedule	Green	1	Health Schedule	customField58	tbMDHealthSchedule	Green	166	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
353	Health Schedule	Yellow	2	Health Schedule	customField58	tbMDHealthSchedule	Yellow	167	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
354	Health Schedule	Not Assessed	3	Health Schedule	customField58	tbMDHealthSchedule	Not Assessed	198	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
355	Health Schedule	Red	3	Health Schedule	customField58	tbMDHealthSchedule	Red	168	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
356	Health Scope	Green	1	Health Scope	customField59	tbMDHealthScope	Green	169	ProjList		Green	Project Tagging	NA	PMO		1-Nov-22
357	Health Scope	Yellow	2	Health Scope	customField59	tbMDHealthScope	Yellow	170	ProjList		Yellow	Project Tagging	NA	PMO		1-Nov-22
358	Health Scope	Not Assessed	3	Health Scope	customField59	tbMDHealthScope	Not Assessed	197	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
359	Health Scope	Red	3	Health Scope	customField59	tbMDHealthScope	Red	171	ProjList		Red	Project Tagging	NA	PMO		1-Nov-22
360	Hyper Links	Link 1	0						ProjList		Link 1	for manually storing hyperlink to external info.	NA	PMO		1-Nov-22
361	Hyper Links	Link 2	0						ProjList		Link 2	for manually storing hyperlink to external info.	NA	PMO		1-Nov-22
362	Internal Rate of Return	> 50%				tbMDInternalRateOfReturn					> 50%	Tagging financial values on business case.
363	Internal Rate of Return	25% - 50%				tbMDInternalRateOfReturn					25% - 50%	Tagging financial values on business case.
364	Internal Rate of Return	15% - 25%				tbMDInternalRateOfReturn					15% - 25%	Tagging financial values on business case.
365	Internal Rate of Return	5% - 15%				tbMDInternalRateOfReturn					5% - 15%	Tagging financial values on business case.
366	Internal Rate of Return	< 5%				tbMDInternalRateOfReturn					< 5%	Tagging financial values on business case.
367	Internal Rate of Return	Not Assessed				tbMDInternalRateOfReturn					Not Assessed	Tagging financial values on business case.
368	Investment Category	Not Assessed	0	Investment Category	customField20	tbMDInvestmentCategory	Not Assessed	67	ProjList		Not Assessed	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
369	Investment Category	Business Systems	10	Investment Category	customField20	tbMDInvestmentCategory	Business Support	63	ProjList		Business Systems	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
370	Investment Category	Our Core Products	20	Investment Category	customField20	tbMDInvestmentCategory	Core Products	65	ProjList		Our Core Products	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
371	Investment Category	Productivity Tools	30	Investment Category	customField20	tbMDInvestmentCategory	Engineering Tools	64	ProjList		Productivity Tools	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
372	Investment Category	Innovation	40	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Innovation	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
373	Investment Category	Digital Transformation	50	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Digital Transformation	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
374	Investment Category	Infrastructure and Security	60	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Infrastructure and Security	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
375	Investment Category	Data and Analytics	70	Investment Category	customField20	tbMDInvestmentCategory	Innovation	66	ProjList		Data and Analytics	Project Portfolio Balancing – Product/System Focus	NA	PMO		1-Nov-22
376	Investment Initiative	Not Assessed	0	Investment Initiative	customField21	tbMDInvestmentInitiative	Support moden digital workplace	73	ProjList		Support moden digital workplace	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
377	Investment Initiative	Strengthen Cybersecurity Infrastructure	10	Investment Initiative	customField21	tbMDInvestmentInitiative	Cross-sell our Network Device products	69	ProjList		Cross-sell our Network Device products	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
378	Investment Initiative	Build AI/ML Capabilities	20	Investment Initiative	customField21	tbMDInvestmentInitiative	Engineering Tool Innovation	70	ProjList		Engineering Tool Innovation	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
379	Investment Initiative	Faster response to new business opportunities	30	Investment Initiative	customField21	tbMDInvestmentInitiative	Faster response to new business opportunities	71	ProjList		Faster response to new business opportunities	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
380	Investment Initiative	Improve employee skills	40	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve Employee Skills	74	ProjList		Improve Employee Skills	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
381	Investment Initiative	Improve product reliability	50	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve product reliability	68	ProjList		Improve product reliability	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
382	Investment Initiative	Improve productivity with Agile Teams	60	Investment Initiative	customField21	tbMDInvestmentInitiative	Improve productivity with Agile Teams	75	ProjList		Improve productivity with Agile Teams	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
383	Investment Initiative	Source Cloud services for our Core products	70	Investment Initiative	customField21	tbMDInvestmentInitiative	Source Cloud services for our Core products	72	ProjList		Source Cloud services for our Core products	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
384	Investment Initiative	Support modern digital workplace	80	Investment Initiative	customField21	tbMDInvestmentInitiative	Support moden digital workplace	73	ProjList		Support moden digital workplace	Project Portfolio Balancing – Capability Building	NA	PMO		1-Nov-22
385	Investment Objective	Not Assessed	0	Investment Objective	customField22	tbMDInvestmentObjective	Transform the Business	78	ProjList		Transform the Business	Project Portfolio Balancing – Business Impact	NA	PMO		1-Nov-22
386	Investment Objective	Grow the Business	10	Investment Objective	customField22	tbMDInvestmentObjective	Grow the Business	77	ProjList		Grow the Business	Project Portfolio Balancing – Business Impact	NA	PMO		1-Nov-22
387	Investment Objective	Run the Business	20	Investment Objective	customField22	tbMDInvestmentObjective	Run the Business	76	ProjList		Run the Business	Project Portfolio Balancing – Business Impact	NA	PMO		1-Nov-22
388	Investment Objective	Modernize the Business	20	Investment Objective	customField22	tbMDInvestmentObjective	Run the Business	76	ProjList		Run the Business	Project Portfolio Balancing – Business Impact	NA	PMO		1-Nov-22
389	Investment Objective	Transform the Business	30	Investment Objective	customField22	tbMDInvestmentObjective	Transform the Business	78	ProjList		Transform the Business	Project Portfolio Balancing – Business Impact	NA	PMO		1-Nov-22
390	Investment Strategy	Not Assessed	0	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
391	Investment Strategy	Attract and retain the best people	10	Investment Strategy	customField23	tbMDInvestmentStrategy	Attract and retain the best people	84	ProjList		Attract and retain the best people	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
392	Investment Strategy	Improve our core products	20	Investment Strategy	customField23	tbMDInvestmentStrategy	Best in market core products	80	ProjList		Best in market core products	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
393	Investment Strategy	Ensure compliance	30	Investment Strategy	customField23	tbMDInvestmentStrategy	Ensure compliance	83	ProjList		Ensure compliance	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
394	Investment Strategy	Accelerate Time-to-Market	40	Investment Strategy	customField23	tbMDInvestmentStrategy	Improve and maintain workplace safety	85	ProjList		Improve and maintain workplace safety	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
395	Investment Strategy	Improve customer service	50	Investment Strategy	customField23	tbMDInvestmentStrategy	Improve customer service	87	ProjList		Improve customer service	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
396	Investment Strategy	Build Recurring Revenue Streams	60	Investment Strategy	customField23	tbMDInvestmentStrategy	Increase revenue	81	ProjList		Increase revenue	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
397	Investment Strategy	Increase share of market	70	Investment Strategy	customField23	tbMDInvestmentStrategy	Increase share of market	82	ProjList		Increase share of market	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
398	Investment Strategy	Reduce waste	80	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
399	Investment Strategy	Drive Contract Renewals	90	Investment Strategy	customField23	tbMDInvestmentStrategy	Reduce waste	86	ProjList		Reduce waste	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
400	Investment Strategy	Server more customers	100	Investment Strategy	customField23	tbMDInvestmentStrategy	Server more customers	79	ProjList		Serve more customers	Project Portfolio Balancing – Specific Business Goals	NA	PMO		1-Nov-22
401	Issue Category	Product	1						General	General	Product		NA
402	Issue Category	Financial	2						General	General	Financial		NA
403	Issue Category	Operational	3						General	General	Operational		NA
404	Issue Category	Technical	4						General	General	Techincal		NA
405	Issue Category	Schedule	4						General	General	Schedule		NA
406	L1	Top Level	0						ProjList		TopLevel	Can use to make custom hierarchy	NA	System		1-Nov-22
407	L2	Next Level Down	0						ProjList		Next Level Down	Can use to make custom hierarchy	NA	System		1-Nov-22
408	L3	Third Level Down	0						ProjList		Third Level Down	Can use to make custom hierarchy	NA	System		1-Nov-22
409	Labour Type	Generic	0	Labour Type	customfield145	tbResLabourType	Generic	201	ResList		Generic	Resource or person tagging	NA	PMO		1-Nov-22
410	Labour Type	Human	0	Labour Type	customfield145	tbResLabourType	Human	200	ResList		Human	Resource or person tagging	NA	PMO		1-Nov-22
411	Labour Type	Other	0	Labour Type	customfield145	tbResLabourType	Other	202	ResList		Other	Resource or person tagging	NA	PMO		1-Nov-22
412	Location	Edmonton	0	Location	customField15	tbResLocation	Edmonton	44	ResList		Gatineau	Where is resource located	NA	PMO		1-Nov-22
413	Location	Halifax	0	Location	customField15	tbResLocation	Halifax	45	ResList		Gatineau	Where is resource located	NA	PMO		1-Nov-22
414	Location	Ottawa	0	Location	customField15	tbResLocation	Ottawa	43	ResList		Ottawa	Where is resource located	NA	PMO		1-Nov-22
415	Manager	George Bush	0	Manager	customField11	tbResManager	George Bush	30	ResList		Kent Om	Project Tagging	NA	PMO		1-Nov-22
416	Manager	John Cougar	0	Manager	customField11	tbResManager	John Cougar	31	ResList		Perry Om	Project Tagging	NA	PMO		1-Nov-22
417	Manager	Sally Res	0	Manager	customField11	tbResManager	Sally Res	32	ResList		Perry Om	Project Tagging	NA	PMO		1-Nov-22
418	Market Timing	Perfect timing				tbPASMarketTiming			PAS	Scores 100	Perfect timing	Tagging the Project Assessment Form
419	Market Timing	Good timing				tbPASMarketTiming			PAS		Good timing	Tagging the Project Assessment Form
420	Market Timing	Acceptable timing				tbPASMarketTiming			PAS		Acceptable timing	Tagging the Project Assessment Form
421	Market Timing	Challenging timing				tbPASMarketTiming			PAS		Challenging timing	Tagging the Project Assessment Form
422	Market Timing	Poor timing				tbPASMarketTiming			PAS		Poor timing	Tagging the Project Assessment Form
423	Mitigation Status	Identified	1			tbMDMitigationStatus	Identified		General		Identified	The risk has been recognized	NA	PMO		1-Nov-22
424	Mitigation Status	Assessed	2			tbMDMitigationStatus	Assessed		General		Assessed	The risk has been analyzed for its impact and probability	NA	PMO		1-Nov-22
425	Mitigation Status	Mitigation Planned	3			tbMDMitigationStatus	Mitigation Planned		General		Mitigation Planned	A mitigation strategy has been developed and documented but not yet implemented.	NA	PMO		1-Nov-22
426	Mitigation Status	In Progress				tbMDMitigationStatus	In Progress		General		In Progress	The mitigation actions are actively being implemented to address the risk.
427	Mitigation Status	Mitigated				tbMDMitigationStatus	Mitigated		General		Mitigated	The planned mitigation actions have been completed
428	Mitigation Status	Under Review				tbMDMitigationStatus	Under Review		General		Under Review	The risk and its mitigation are being evaluated to determine if further action is needed.
429	Mitigation Status	Accepted				tbMDMitigationStatus	Accepted		General		Accepted	The risk is acknowledged but will not be mitigated
430	Mitigation Status	Transferred				tbMDMitigationStatus	Transferred		General		Transferred	The responsibility of the risk has been assigned to a third party
431	Mitigation Status	Escalated				tbMDMitigationStatus	Escalated		General		Escalated	The risk has been moved to higher management or another department for resolution due to its complexity or impact level.
432	Mitigation Status	Closed				tbMDMitigationStatus	Closed		General		Closed	The risk is no longer relevant or has been fully resolved; no further action is required.
433	Mitigation Status	Deferred				tbMDMitigationStatus	Deferred		General		Deferred	The risk has been identified but will be monitored over time before deciding on mitigation.
434	Net Present Value	> $5M				tbMDNetPresentValue					> $5M	Tagging financial values on business case.
435	Net Present Value	$1M - $5M				tbMDNetPresentValue					$1M - $5M	Tagging financial values on business case.
436	Net Present Value	$250K - $1M				tbMDNetPresentValue					$250K - $1M	Tagging financial values on business case.
437	Net Present Value	$50K - $250K				tbMDNetPresentValue					$50K - $250K	Tagging financial values on business case.
438	Net Present Value	< $50K				tbMDNetPresentValue					< $50K	Tagging financial values on business case.
439	Net Present Value	Not Assessed				tbMDNetPresentValue					Not Assessed	Tagging financial values on business case.
440	Non Project Tag	No	0						ProjList		No	Project Tagging	NA	PMO		1-Nov-22
441	Non Project Tag	Yes	0						ProjList		Yes	Project Tagging	NA	PMO		1-Nov-22
442	Owner	Jim				tbOwner			General	General	NA
443	Owner	Julia				tbOwner			General	General	NA
444	Owner	Allyson				tbOwner			General	General	NA
445	Owner	Kyle				tbOwner			General	General	NA
446	Part-time Full-time	Full Time	1	Part or Full Time	customField16	tbResPartTimeFullTime	Full Time	46	ResList		Full Time	Resource or person tagging	NA	PMO		1-Nov-22
447	Part-time Full-time	Part Time	2	Part or Full Time	customField16	tbResPartTimeFullTime	Part Time	47	ResList		Part Time	Resource or person tagging	NA	PMO		1-Nov-22
448	Payback Period	< 1 year				tbMDPaybackPeriod					< 1 year	Tagging financial values on business case.
449	Payback Period	1 - 2 years				tbMDPaybackPeriod					1 - 2 years	Tagging financial values on business case.
450	Payback Period	2 - 3 years				tbMDPaybackPeriod					2 - 3 years	Tagging financial values on business case.
451	Payback Period	3 - 5 years				tbMDPaybackPeriod					3 - 5 years	Tagging financial values on business case.
452	Payback Period	> 5 years				tbMDPaybackPeriod					> 5 years	Tagging financial values on business case.
453	Payback Period	Not Assessed				tbMDPaybackPeriod					Not Assessed	Tagging financial values on business case.
454	Percent Available	10	0						ResList		10	For tagging an allocation for resource management	NA	PMO		1-Nov-22
455	Percent Available	25	0						ResList		25	For tagging an allocation for resource management	NA	PMO		1-Nov-22
456	Percent Available	50	0						ResList		50	For tagging an allocation for resource management	NA	PMO		1-Nov-22
457	Percent Available	75	0						ResList		75	For tagging an allocation for resource management	NA	PMO		1-Nov-22
458	Percent Available	100	0						ResList		100	For tagging an allocation for resource management	NA	PMO		1-Nov-22
459	PercentTimeAllocated	10	0						ResList		10	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
460	PercentTimeAllocated	25	0						ResList		25	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
461	PercentTimeAllocated	50	0						ResList		50	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
462	PercentTimeAllocated	75	0						ResList		75	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
463	PercentTimeAllocated	100	0						ResList		100	Main tool to use to estimate timebar work	NA	PMO		1-Nov-22
464	Phase	Closing	0	Phase	customField26	tbMDPhase	Closing	98	General		Closing	High-level Phase of Project or Program	NA	PMO		1-Nov-22
465	Phase	Executing	0	Phase	customField26	tbMDPhase	Executing	97	General		Executing	High-level Phase of Project or Program	NA	PMO		1-Nov-22
466	Phase	Initiating	0	Phase	customField26	tbMDPhase	Initiating	96	General		Initiating	High-level Phase of Project or Program	NA	PMO		1-Nov-22
467	Phase	Planning	0	Phase	customField26	tbMDPhase	Planning	99	General		Planning	High-level Phase of Project or Program	NA	PMO		1-Nov-22
468	Portfolios	Building Services	0	Portfolio	customField27	tbMDPortfolio	Building Services	104	ProjList		Building Services	Project Tagging	NA	PMO		1-Nov-22
469	Portfolios	Business Support Systems	0	Portfolio	customField27	tbMDPortfolio	Business Support Systems	102	ProjList		Business Support Systems	Project Tagging	NA	PMO		1-Nov-22
470	Portfolios	Core Product Delivery	0	Portfolio	customField27	tbMDPortfolio	Core Product Delivery	101	ProjList		Core Product Delivery	Project Tagging	NA	PMO		1-Nov-22
471	Portfolios	IT Platform	0	Portfolio	customField27	tbMDPortfolio	IT Platform	103	ProjList		IT Platform	Project Tagging	NA	PMO		1-Nov-22
472	Portfolios	R&D New Technology	0	Portfolio	customField27	tbMDPortfolio	R&D New Technology	100	ProjList		R&D New Technology	Project Tagging	NA	PMO		1-Nov-22
473	Primary LOB	Business Development	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Business Development	106	ProjList		Research and Development	Project Tagging	NA	PMO		1-Nov-22
474	Primary LOB	Business Technology Solutions	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Business Technology Solutions	108	ProjList		Corporate Affairs	Project Tagging	NA	PMO		1-Nov-22
475	Primary LOB	Corporate Affairs	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Corporate Affairs	107	ProjList		Business Development	Project Tagging	NA	PMO		1-Nov-22
476	Primary LOB	Engineering and Product Delivery	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Engineering and Product Delivery	109	ProjList		Business Technology Solutions	Project Tagging	NA	PMO		1-Nov-22
477	Primary LOB	Human Resources	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Human Resources	110	ProjList		Engineering and Product Delivery	Project Tagging	NA	PMO		1-Nov-22
478	Primary LOB	Research and Development	0	Primary Line of Business	customField29	tbMDPrimaryLineOfBusiness	Research and Development	105	ProjList		Finance	Project Tagging	NA	PMO		1-Nov-22
479	Primary Role	Catch All Role	1	Primary Role	customField12	tbResPrimaryRole	Catch All Role	36	ResList		NA	Tag resources for resource demand calculations	NA	system		1-Nov-22
480	Primary Role	Executive Sponsor	2	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
481	Primary Role	Director	3	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
482	Primary Role	Manager	4	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
483	Primary Role	Team Lead	5	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
484	Primary Role	Department Head	6	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
485	Primary Role	Policy & Planning	7	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
486	Primary Role	Strategic Planning	8	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
487	Primary Role	Business Strategy	9	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
488	Primary Role	Transformation Office	10	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
489	Primary Role	Transformation Delivery	11	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
490	Primary Role	Portfolio Manager	12	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
491	Primary Role	Program Manager	13	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
492	Primary Role	Project Manager	14	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
493	Primary Role	Project Coordinator	15	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
494	Primary Role	Client Relationship Manager	16	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
495	Primary Role	Customer Success Manager	17	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
496	Primary Role	Business Lead	18	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
497	Primary Role	Business SME	19	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
498	Primary Role	Business Analyst	20	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
499	Primary Role	Process Analyst	21	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
500	Primary Role	Business Intake	22	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
501	Primary Role	Partnership Manager	23	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
502	Primary Role	Vendor Manager	24	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
503	Primary Role	Contract Manager	25	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
504	Primary Role	Product Manager	26	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
505	Primary Role	Product Owner	27	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
506	Primary Role	R&D Lab	28	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
507	Primary Role	Innovation Manager	29	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
508	Primary Role	Artificial Intelligence and Robotics	30	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
509	Primary Role	Solution Design	31	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
510	Primary Role	Engineer	32	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
511	Primary Role	Solution Architecture	33	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
512	Primary Role	Infrastructure Architecture	34	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
513	Primary Role	Technical Architecture	35	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
514	Primary Role	Developer	36	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
515	Primary Role	Software Engineer	37	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
516	Primary Role	DevOps Engineer	38	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
517	Primary Role	Cloud Technologies	39	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
518	Primary Role	Platform Performance Team	40	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
519	Primary Role	Database Administrator	41	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
520	Primary Role	Data Platform	42	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
521	Primary Role	Enterprise Data Warehouse	43	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
522	Primary Role	Data Analyst	44	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
523	Primary Role	Data Scientist	45	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
524	Primary Role	Data Engineer	46	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
525	Primary Role	Business Intelligence	47	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
526	Primary Role	Analytics	48	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
527	Primary Role	Data Governance	49	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
528	Primary Role	Functional Design Team	50	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
529	Primary Role	UX/UI Designer	51	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
530	Primary Role	Graphic Designer	52	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
531	Primary Role	Technical Writer	53	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
532	Primary Role	Document Technologies	54	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
533	Primary Role	Quality Manager	55	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
534	Primary Role	Quality Assurance	56	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
535	Primary Role	Test Automation	57	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
536	Primary Role	Performance Testing	58	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
537	Primary Role	Tester	59	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
538	Primary Role	Security	60	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
539	Primary Role	Cybersecurity Specialist	61	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
540	Primary Role	Information Security	62	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
541	Primary Role	Privacy Officer	63	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
542	Primary Role	Compliance Officer	64	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
543	Primary Role	Risk Manager	65	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
544	Primary Role	Auditor	66	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
545	Primary Role	Application Operations	67	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
546	Primary Role	Service Integration	68	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
547	Primary Role	Application Lifecycle Manager	69	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
548	Primary Role	Env Support	70	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
549	Primary Role	Service Desk	71	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
550	Primary Role	Operations Support	72	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
551	Primary Role	Incident Manager	73	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
552	Primary Role	Major Release and Planning	74	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
553	Primary Role	Change and Release	75	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
554	Primary Role	Disaster Recovery	76	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
555	Primary Role	Change Lead	77	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
556	Primary Role	Change Manager	78	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
557	Primary Role	Training & Development	79	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
558	Primary Role	Communications	80	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
559	Primary Role	Stakeholder	81	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
560	Primary Role	Information Manager	82	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
561	Primary Role	Knowledge Manager	83	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
562	Primary Role	Document Manager	84	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
563	Primary Role	Records Manager	85	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
564	Primary Role	Network Administrator	86	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
565	Primary Role	System Administrator	87	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
566	Primary Role	Cloud Infrastructure	88	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
567	Primary Role	Telecommunications	89	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
568	Primary Role	Facilities Manager	90	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
569	Primary Role	Financial Analyst	91	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
570	Primary Role	Budget Analyst	92	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
571	Primary Role	Procurement	93	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
572	Primary Role	Cost Manager	94	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
573	Primary Role	Financial Planning	95	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
574	Primary Role	HR SME	96	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
575	Primary Role	Talent Acquisition	97	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
576	Primary Role	Legal Counsel	98	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
577	Primary Role	Employment Law	99	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
578	Primary Role	Organizational Development	100	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
579	Primary Role	Marketing Manager	101	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
580	Primary Role	Communications Manager	102	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
581	Primary Role	Public Relations	103	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
582	Primary Role	Brand Manager	104	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
583	Primary Role	Digital Marketing	105	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
584	Primary Role	Sales Manager	106	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
585	Primary Role	Account Manager	107	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
586	Primary Role	Business Development	108	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
587	Primary Role	Revenue Operations	109	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
588	Primary Role	Technical Debt Reduction	110	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
589	Primary Role	Performance Optimization	111	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
590	Primary Role	Integration Specialist	112	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
591	Primary Role	Migration Specialist	113	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
592	Primary Role	Technical Training	114	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
593	Primary Role	Configuration Manager	115	Primary Role	customField12	tbResPrimaryRole			ResList		NA	Tag resources for resource demand calculations
594	Primary Skill	IT Architecture	1	Primary Skill	customField9	tbResPrimarySkill	IT Architecture	22	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
595	Primary Skill	Testing	2	Primary Skill	customField9	tbResPrimarySkill	Testing	23	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
596	Primary Skill	Design	3	Primary Skill	customField9	tbResPrimarySkill	Design	24	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
597	Primary Skill	Project Management	4	Primary Skill	customField9	tbResPrimarySkill	Project Management	25	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
598	Primary Skill	Procurement	5	Primary Skill	customField9	tbResPrimarySkill	Procurement	26	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
599	Primary Skill	Catch All Skill	5	Primary Skill	customField9	tbResPrimarySkill	Catch All Skill	26	ResList		NA	Tag resources for resource demand calculations	NA	PMO		1-Nov-22
600	Primary Skill	na	6	Primary Skill	customField9	tbResPrimarySkill			ResList		NA	Tag resources for resource demand calculations
601	Product	Access Point	1	Product	customField146	tbMDProduct	Access Point	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
602	Product	Analyzers	2	Product	customField146	tbMDProduct	Analyzers	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
603	Product	Antenna	3	Product	customField146	tbMDProduct	Antenna	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
604	Product	Billing System	4	Product	customField146	tbMDProduct	Billing System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
605	Product	CEP	5	Product	customField146	tbMDProduct	CEP	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
606	Product	DM System	6	Product	customField146	tbMDProduct	DM System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
607	Product	Hot spot	7	Product	customField146	tbMDProduct	Hot spot	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
608	Product	HR System	8	Product	customField146	tbMDProduct	HR System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
609	Product	NA	9	Product	customField146	tbMDProduct	NA	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
610	Product	Network	10	Product	customField146	tbMDProduct	Network	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
611	Product	SAP System	11	Product	customField146	tbMDProduct	SAP System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
612	Product	Secure Cloud System	12	Product	customField146	tbMDProduct	Secure Cloud System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
613	Product	Security System	13	Product	customField146	tbMDProduct	Security System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
614	Product	Ticketing system	14	Product	customField146	tbMDProduct	Ticketing system	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
615	Product	Tools	15	Product	customField146	tbMDProduct	Tools	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
616	Product	VNS System	16	Product	customField146	tbMDProduct	VNS System	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
617	Product	WIFI	17	Product	customField146	tbMDProduct	WIFI	205	ProjList		SAP ERP System	If this timebar is for creating a product, use this tag	NA	PMO		1-Nov-22
618	Program Activity Alignment (PAA)	1 1 1 1 Sub-Sub-Program: Banks support of One-Benefit distribution	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
619	Program Activity Alignment (PAA)	1 1 1 2 Sub-Sub-Program: Tax System changes to suit new One-Benefit.	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
620	Program Activity Alignment (PAA)	1 1 1 Sub-Program: One Canada wide monthly payment to each Canadian	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
621	Program Activity Alignment (PAA)	1 1 Program: Common One-Benefit service for all Canadians	0						ProjList			Project Tagging	NA	PMO		1-Nov-22
622	Programs	Building and Office Modernization	0						ProjList		Building and Office Modernization	Project Tagging	NA	PMO		1-Nov-22
623	Programs	Business Continuity Management Program	0						ProjList		Business Continuity Management Program	Project Tagging	NA	PMO		1-Nov-22
624	Programs	Centralized Billing and Receivables	0						ProjList		Centralized Billing and Receivables	Project Tagging	NA	PMO		1-Nov-22
625	Programs	Continuous Improvement Transformation	0						ProjList		Continuous Improvement Transformation	Project Tagging	NA	PMO		1-Nov-22
626	Programs	Continuous Internal Delivery Enablement	0						ProjList		Continuous Internal Delivery Enablement	Project Tagging	NA	PMO		1-Nov-22
627	Programs	Core Operations Program	0						ProjList		Core Operations Program	Project Tagging	NA	PMO		1-Nov-22
628	Programs	Digital Workplace - Transformation	0						ProjList		Digital Workplace - Transformation	Project Tagging	NA	PMO		1-Nov-22
629	Programs	ERP Transformation	0						ProjList		ERP Transformation	Project Tagging	NA	PMO		1-Nov-22
630	Programs	HR Service Delivery	0						ProjList		HR Service Delivery	Project Tagging	NA	PMO		1-Nov-22
631	Programs	IM Policy and Guidelines	0						ProjList		IM Policy and Guidelines	Project Tagging	NA	PMO		1-Nov-22
632	Programs	Information Solutions Resiliency	0						ProjList		Information Solutions Resiliency	Project Tagging	NA	PMO		1-Nov-22
633	Programs	Infrastructure as a Service (IaaS) Program	0						ProjList		Infrastructure as a Service (IaaS) Program	Project Tagging	NA	PMO		1-Nov-22
634	Programs	Integration API Development Program	0						ProjList		Integration API Development Program	Project Tagging	NA	PMO		1-Nov-22
635	Programs	Market Information Management	0						ProjList		Market Information Management	Project Tagging	NA	PMO		1-Nov-22
636	Programs	NA	0						ProjList		NA	Project Tagging	NA	PMO		1-Nov-22
637	Programs	SAP System Upgrade	0						ProjList		SAP System Upgrade	Project Tagging	NA	PMO		1-Nov-22
638	Programs	SharePoint 2016 Upgrade	0						ProjList		SharePoint 2016 Upgrade	Project Tagging	NA	PMO		1-Nov-22
639	Programs	Standalone Project with No Program	0						ProjList		Standalone Project with No Program	Project Tagging	NA	PMO		1-Nov-22
640	Programs	TBS Compliance	0						ProjList		TBS Compliance	Project Tagging	NA	PMO		1-Nov-22
641	Programs	Ticketing System and Requirements Management	0						ProjList		Ticketing System and Requirements Management	Project Tagging	NA	PMO		1-Nov-22
642	Project Assessment Status	Draft				tbPASStatus			PAS		Draft	Tagging the Project Assessment Form
643	Project Assessment Status	Completed				tbPASStatus			PAS		Completed	Tagging the Project Assessment Form
644	Project Assessment Status	Approved				tbPASStatus			PAS		Approved	Tagging the Project Assessment Form
645	Project Assessment Status	Rejected				tbPASStatus			PAS		Rejected	Tagging the Project Assessment Form
646	Project Assessment Status	On Hold				tbPASStatus			PAS		On Hold	Tagging the Project Assessment Form
647	Project Assessment Type	Incremental Improvement				tbPASProjectType			PAS		Incremental Improvement	Tagging the Project Assessment Form
648	Project Assessment Type	Enhancement				tbPASProjectType			PAS	Scores 100	Enhancement	Tagging the Project Assessment Form
649	Project Assessment Type	New Feature				tbPASProjectType			PAS		New Feature	Tagging the Project Assessment Form
650	Project Assessment Type	New Product				tbPASProjectType			PAS		New Product	Tagging the Project Assessment Form
651	Project Assessment Type	Breakthrough Innovation				tbPASProjectType			PAS		Breakthrough Innovation	Tagging the Project Assessment Form
652	Project Manager	Jim Soda	0			tbMDPM			ProjList	ProjList	CR	Identify a CR requester	NA	PMO		1-Nov-22
653	Project Manager	Allyson Soda	0			tbMDPM			ProjList	ProjList	CR	Identify a CR requester	NA	PMO		1-Nov-22
654	Project Similarity	Very Similar				tbPASProjectSimilarity			PAS		Very Similar	Tagging the Project Assessment Form
655	Project Similarity	Somewhat Similar				tbPASProjectSimilarity			PAS		Somewhat Similar	Tagging the Project Assessment Form
656	Project Similarity	Moderately Different				tbPASProjectSimilarity			PAS		Moderately Different	Tagging the Project Assessment Form
657	Project Similarity	Quite Different				tbPASProjectSimilarity			PAS		Quite Different	Tagging the Project Assessment Form
658	Project Similarity	Completely New				tbPASProjectSimilarity			PAS		Completely New	Tagging the Project Assessment Form
659	Project Status	at_risk	0	status	status	tbStatus	at_risk	at_risk	ProjList		On-Hold	Matches OpenProject not used for now	NA	PMO		1-Nov-22
660	Project Status	off_track	0	status	status	tbStatus	off_track	off_track	ProjList		Canceled	Matches OpenProject not used for now	NA	PMO		1-Nov-22
661	Project Status	on_track	0	status	status	tbStatus	on_track	on_track	ProjList		Active	Matches OpenProject not used for now	NA	PMO		1-Nov-22
662	Project Status	discontinued		status	status	tbStatus	discontinued	discontinued	ProjList			Matches OpenProject not used for now
663	Project Status	finished		status	status	tbStatus	finished	finished	ProjList			Matches OpenProject not used for now
664	Project Status	not_started		status	status	tbStatus	not_started	not_started	ProjList			Matches OpenProject not used for now
665	RandIStage	1 Proposed	1						ProjList		Proposed	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
666	RandIStage	2 Triaged	2						ProjList		Triaged	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
667	RandIStage	3 Prioritized	3						ProjList		Prioritized	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
668	RandIStage	4 Assigned	4						ProjList		Assigned	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
669	RandIStage	5 Solving	5						ProjList		Solving	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
670	RandIStage	6 Mitigating	6						ProjList		Mitigation	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
671	RandIStage	7 Closed	7						ProjList		Closed	Controlling Risk and Issue life-cycle workflow	NA	PMO		1-Nov-22
672	RandIState	Active	1						ProjList		Active	Workflow Life-cycle tag	NA	PMO		1-Nov-22
673	RandIState	On Hold	2						ProjList		On Hold	Workflow Life-cycle tag	NA	PMO		1-Nov-22
674	RandIState	Completed	3						ProjList		Completed	Workflow Life-cycle tag	NA	PMO		1-Nov-22
675	RandIState	Canceled	3						ProjList		Canceled	Workflow Life-cycle tag	NA	PMO		1-Nov-22
676	RandIStatus	Managing	1						General		Managing	Timebar Task, Issue, Risk or CR Status.	NA	PMO		1-Nov-22
677	RandIStatus	Concerned	2						General		Concerned	Timebar Task, Issue, Risk or CR Status.	NA	PMO		1-Nov-22
678	RandIStatus	Critical	3						General		Critical	Timebar Task, Issue, Risk or CR Status.	NA	PMO		1-Nov-22
679	RandIStatus	Completed	3						General		Completed	Timebar Task, Issue, Risk or CR Status.	NA	PMO		1-Nov-22
680	Regulatory Approvals	None required				tbPASRegulatoryApprovals			PAS	Scores 100	None required	Tagging the Project Assessment Form
681	Regulatory Approvals	Internal approvals				tbPASRegulatoryApprovals			PAS		Internal approvals	Tagging the Project Assessment Form
682	Regulatory Approvals	Industry standards				tbPASRegulatoryApprovals			PAS		Industry standards	Tagging the Project Assessment Form
683	Regulatory Approvals	Government approvals				tbPASRegulatoryApprovals			PAS		Government approvals	Tagging the Project Assessment Form
684	Regulatory Approvals	Multiple regulatory bodies				tbPASRegulatoryApprovals			PAS		Multiple regulatory bodies	Tagging the Project Assessment Form
685	Resource Class	External	0	Class	customField10	tbResResourceClass	External	27	ResList		Contractor	Resource or person tagging	NA	PMO		1-Nov-22
686	Resource Class	Permanent	0	Class	customField10	tbResResourceClass	Permenant	28	ResList		Perm	Resource or person tagging	NA	PMO		1-Nov-22
687	Resource Class	Seasonal	0	Class	customField10	tbResResourceClass	Seasonal	29	ResList		Seasonal	Resource or person tagging	NA	PMO		1-Nov-22
688	Resource Department	Finance	1	Department	customField148	tbResDepartment	Mechanical	206	ResList	ResList	Mechanical		NA	PMO		1-Nov-22
689	Resource Department	Information Technology	2	Department	customField148	tbResDepartment	Electrical	207	ResList	ResList	Electrical		NA	PMO		1-Nov-22
690	Resource Department	Legal Compliance	3	Department	customField148	tbResDepartment	Delivery	208	ResList	ResList	Delivery		NA	PMO		1-Nov-22
691	Resource Type	Equipment	0	Resource Type	customfield150	tbResResourceType	Equipment	213	ResList		Other	Resource or person tagging	NA	PMO		1-Nov-22
692	Resource Type	Labour	0	Resource Type	customfield150	tbResResourceType	Labour	212	ResList		Generic	Resource or person tagging	NA	PMO		1-Nov-22
693	Resource Type	Material	0	Resource Type	customfield150	tbResResourceType	Material	214	ResList		Material	Resource or person tagging	NA	PMO		1-Nov-22
694	Responsible Person	from tbResources table	0	Op Iinternal user field	responsible	tbMDResponsibility			General		Jim	Define who is responsible for Timebar when in trouble	NA	PMO		1-Nov-22
695	Responsible Team	Product Engineering	1	Responsible Team	customField33	tbMDResponsibleTeam	Product Engineering	117	ProjList		Ateam	Project Tagging	NA	PMO		1-Nov-22
696	Responsible Team	Information Technology	2	Responsible Team	customField33	tbMDResponsibleTeam	Information Technology	118	ProjList		Bteam	Project Tagging	NA	PMO		1-Nov-22
697	Responsible Team	Accounting	3	Responsible Team	customField33	tbMDResponsibleTeam	Accounting	119	ProjList		Cteam	Project Tagging	NA	PMO		1-Nov-22
698	Responsible Team	Finance	4	Responsible Team	customField33	tbMDResponsibleTeam	Finance	120	ProjList		Dteam	Project Tagging	NA	PMO		1-Nov-22
699	Responsible Team	Procurement	5	Responsible Team	customField33	tbMDResponsibleTeam	Procurement	121	ProjList		Fteam	Project Tagging	NA	PMO		1-Nov-22
700	Risk Category	Strategic	1						General	General	Strategic		NA
701	Risk Category	Financial	2						General	General	Financial		NA
702	Risk Category	Operational	3						General	General	Operational		NA
703	Risk Category	Technical	4						General	General	Techincal		NA
704	Risk Category	Organizational	4						General	General	Orgnizational		NA
705	Risk Impact	Very Low	1			tbMDImpact	High		General		Very Low	Tagging risks for the risk score result	NA	PMO		1-Nov-22
706	Risk Impact	Low	2			tbMDImpact	Medium		General		Low	Tagging risks for the risk score result	NA	PMO		1-Nov-22
707	Risk Impact	Medium	3			tbMDImpact	Low		General		Medium	Tagging risks for the risk score result	NA	PMO		1-Nov-22
708	Risk Impact	High	4			tbMDImpact	Normal		General		High	Tagging risks for the risk score result	NA	PMO		1-Nov-22
709	Risk Impact	Very High	5			tbMDImpact	Not Assessed		General		Very High	Tagging risks for the risk score result	NA	PMO		1-Nov-22
710	Risk Impact	Not Assessed	5			tbMDImpact	Not Assessed		General		Not Assessed	Tagging risks for the risk score result	NA	PMO		1-Nov-22
711	Risk Probability	Very Unlikely	1			tbMDProbability	High		General		Very Unlikely	Tagging risks for the risk score result	NA	PMO		1-Nov-22
712	Risk Probability	Unlikely	2			tbMDProbability	Intermediate		General		Unlikely	Tagging risks for the risk score result	NA	PMO		1-Nov-22
713	Risk Probability	Likely	3			tbMDProbability	Low		General		Likely	Tagging risks for the risk score result	NA	PMO		1-Nov-22
714	Risk Probability	Very Likely	4			tbMDProbability	Normal		General		Very Likely	Tagging risks for the risk score result	NA	PMO		1-Nov-22
715	Risk Probability	Certain	5			tbMDProbability	Not Assessed		General		Certain	Tagging risks for the risk score result	NA	PMO		1-Nov-22
716	Risk Probability	Not Assessed	5			tbMDProbability	Not Assessed		General		Not Assessed	Tagging risks for the risk score result	NA	PMO		1-Nov-22
717	Risk Vs Size	Not Assessed	1			tbMDRiskVsSizeAndComplexity			ProjList		Not Assessed	Supports bubble charts	NA	PMO		1-Nov-22
718	Risk Vs Size	0-10 Very Small and Simple	2			tbMDRiskVsSizeAndComplexity			ProjList		0-10 Very Small and Simple	Supports bubble charts	NA	PMO		1-Nov-22
719	Risk Vs Size	11-20 Small and Straightforward	3			tbMDRiskVsSizeAndComplexity			ProjList		11-20 Small and Straightforward	Supports bubble charts	NA	PMO		1-Nov-22
720	Risk Vs Size	21-30 Medium with Some Complexity	4			tbMDRiskVsSizeAndComplexity			ProjList		21-30 Medium with Some Complexity	Supports bubble charts	NA	PMO		1-Nov-22
721	Risk Vs Size	31-40 Large with Moderate Complexity	5			tbMDRiskVsSizeAndComplexity			ProjList		31-40 Large with Moderate Complexity	Supports bubble charts	NA	PMO		1-Nov-22
722	Risk Vs Size	41-50 Complex but Manageable	1			tbMDRiskVsSizeAndComplexity			ProjList		41-50 Complex but Manageable	Supports bubble charts	NA	PMO		1-Nov-22
723	Risk Vs Size	51-60 Significant Complexity	2			tbMDRiskVsSizeAndComplexity			ProjList		51-60 Significant Complexity	Supports bubble charts	NA	PMO		1-Nov-22
724	Risk Vs Size	61-70 Large and Complex	3			tbMDRiskVsSizeAndComplexity			ProjList		61-70 Large and Complex	Supports bubble charts	NA	PMO		1-Nov-22
725	Risk Vs Size	71-80 Very Large and Complex	4			tbMDRiskVsSizeAndComplexity			ProjList		71-80 Very Large and Complex	Supports bubble charts	NA	PMO		1-Nov-22
726	Risk Vs Size	81-90 Highly Complex and Risky	5			tbMDRiskVsSizeAndComplexity			ProjList		81-90 Highly Complex and Risky	Supports bubble charts	NA	PMO		1-Nov-22
727	Risk Vs Size	91-100 Extremely Complex and Risky	5			tbMDRiskVsSizeAndComplexity			ProjList		91-100 Extremely Complex and Risky	Supports bubble charts	NA	PMO		1-Nov-22
728	Schedule Status	Completed	0	Health	customField152	tbMDHealth	Completed	221	ProjList		Completed	For Reporting Color indicators	NA	PMO		1-Nov-22
729	Schedule Status	Early	0	Health	customField152	tbMDHealth	Early	217	ProjList		Early	For Reporting Color indicators	NA	PMO		1-Nov-22
730	Schedule Status	Late	0	Health	customField152	tbMDHealth	Late	219	ProjList		Late	For Reporting Color indicators	NA	PMO		1-Nov-22
731	Schedule Status	On schedule	0	Health	customField152	tbMDHealth	On Schedule	216	ProjList		On schedule	For Reporting Color indicators	NA	PMO		1-Nov-22
732	Schedule Status	Slipping	0	Health	customField152	tbMDHealth	Slipping	218	ProjList		Slipping	For Reporting Color indicators	NA	PMO		1-Nov-22
733	Schedule Status	Not Assessed	0	Health	customField152	tbMDHealth	Not Assessed	218	ProjList		Not Assessed	For Reporting Color indicators	NA	PMO		1-Nov-22
734	Selected	Yes	0	Yes		tbMDSelectedYesNo	Yes	17	ProjList	General	Yes	For PPM Selected yns no indicators	NA	PMO		1-Nov-22
735	Selected	No	0	No		tbMDSelectedYesNo	No	17	ProjList	General	No	For PPM Selected yn indicators	NA	PMO		1-Nov-22
736	Selected	Not Assessed	0	Not Assessed		tbMDSelectedYesNo	Not Assessed	17	ProjList	General	Not Assessed	For PPM Selected yn indicators	NA	PMO		1-Nov-22
737	Severity	Critical	0						General		1	Indicates how severe a priority item is, in terms of impact	NA	PMO		1-Nov-22
738	Severity	Important	0						General		2	Indicates how severe a priority item is, in terms of impact	NA	PMO		1-Nov-22
739	Severity	Normal	0						General		3	Indicates how severe a priority item is, in terms of impact	NA	PMO		1-Nov-22
741	Show In Reports	Milestone Horizon	0	Show In	customField34	tbMDShowIn	PM Dashboard	123	ProjList		PM Dashboard	Project Tagging	NA	PMO		1-Nov-22
742	Show In Reports	Business Case	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
743	Show In Reports	Shop Schedule	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
748	Show In Reports	Key Deliverables	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
749	Show In Reports	Key Dates	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
750	Show In Reports	Key Milestones	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
751	Show In Reports	Key Risks	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
752	Show In Reports	Key Issues	0	Show In	customField34	tbMDShowIn	Project Sites	124	ProjList			Project Tagging	NA	PMO		1-Nov-22
753	Size	Small	1						ProjList		Small	Project or Task Tagging	NA	PMO		1-Nov-22
754	Size	Medium	2						ProjList		Medium	Project or Task Tagging	NA	PMO		1-Nov-22
755	Size	Large	3						ProjList		Large	Project or Task Tagging	NA	PMO		1-Nov-22
756	Size	Huge	4						ProjList		Release	Project Tagging	NA	PMO		1-Nov-22
757	Sponsoring Department	Finance	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Customer Support Department	125	ProjList		Finance	Project Tagging	NA	PMO		1-Nov-22
758	Sponsoring Department	IT Department	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	IT Department	127	ProjList		IT Department	Project Tagging	NA	PMO		1-Nov-22
759	Sponsoring Department	Presidents Office	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Presidents Office	126	ProjList		Presidents Office	Project Tagging	NA	PMO		1-Nov-22
760	Sponsoring Department	Communications Public Relations	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Customer Support Department	125	ProjList		Communications Public Relations	Project Tagging	NA	PMO		1-Nov-22
761	Sponsoring Department	Legal Compliance	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	IT Department	127	ProjList		Legal Compliance	Project Tagging	NA	PMO		1-Nov-22
762	Sponsoring Department	Operations	0	Sponsoring Department	customField35	tbMDSponsoringDepartment	Presidents Office	126	ProjList		Operations	Project Tagging	NA	PMO		1-Nov-22
763	Stage	1 Proposed	0	Stage	customField37	tbMDStage	1 Proposed	132	ProjList	ProjList	Proposed	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
764	Stage	2 Triaged	0	Stage	customField37	tbMDStage	2 Triaged	133	ProjList	ProjList	Triaged	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
765	Stage	3 Prioritized	0	Stage	customField37	tbMDStage	3 Prioritized	134	ProjList	ProjList	Prioritized	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
766	Stage	4 Selected	0	Stage	customField37	tbMDStage	4 Selected	135	ProjList	ProjList	Selected	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
767	Stage	5 Assigned	0	Stage	customField37	tbMDStage	5 Assigned	136	ProjList	ProjList	Assigned	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
768	Stage	6 Delivering	0	Stage	customField37	tbMDStage	6 Delivering	137	ProjList	ProjList	Delivering	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
769	Stage	7 Delivered	0	Stage	customField37	tbMDStage	7 Delivered	138	ProjList	ProjList	Delivered	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
770	Stage	8 Closed	0	Stage	customField37	tbMDStage	8 Closed	139	ProjList	ProjList	Closed	Controlling project life-cycle workflow	NA	PMO		1-Nov-22
771	Stakeholder Count	1-5 stakeholders				tbPASStakeholderCount			PAS	Scores 100	1-5 stakeholders	Tagging the Project Assessment Form
772	Stakeholder Count	6-10 stakeholders				tbPASStakeholderCount			PAS		6-10 stakeholders	Tagging the Project Assessment Form
773	Stakeholder Count	11-20 stakeholders				tbPASStakeholderCount			PAS		11-20 stakeholders	Tagging the Project Assessment Form
774	Stakeholder Count	21-50 stakeholders				tbPASStakeholderCount			PAS		21-50 stakeholders	Tagging the Project Assessment Form
775	Stakeholder Count	Over 50 stakeholders				tbPASStakeholderCount			PAS		Over 50 stakeholders	Tagging the Project Assessment Form
776	stdTasks	Design	0						StdTasks	StdTasks	Design	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
777	stdTasks	Develop	0						StdTasks	StdTasks	Dev	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
778	stdTasks	Project Finish	0						StdTasks	StdTasks	Finish	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
779	stdTasks	Project Start	0						StdTasks	StdTasks	Start	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
780	stdTasks	Test	0						StdTasks	StdTasks	Test	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
781	stdTasks	UAT	0						StdTasks	StdTasks	UAT	Drag and Drop on Project or Release to create a Standard Task	NA	PMO		1-Nov-22
782	Strategic Priority	High	0	Priority Strategic	customField30	tbMDPriorityStrategic	High	111	ProjList		Improve intiitative visibility	Project Tagging	NA	PMO		1-Nov-22
783	Strategic Priority	Low	0	Priority Strategic	customField30	tbMDPriorityStrategic	Low	113	ProjList		Fewer meetings	Project Tagging	NA	PMO		1-Nov-22
784	Strategic Priority	Medium	0	Priority Strategic	customField30	tbMDPriorityStrategic	Medium	112	ProjList		Reduce complexity of process	Project Tagging	NA	PMO		1-Nov-22
785	SubType	Issue	0						ProjList	ProjList	Issue	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
786	SubType	Other	0						ProjList	ProjList	Other	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
787	SubType	Risk	0						ProjList	ProjList	Risk	Risk or Issue or Other tagging at the task level	NA	PMO		1-Nov-22
788	SubType	Task	0						ProjList	ProjList	Task	Task, Risk, Issue or Other. Determines Blue bar sub type	NA	PMO		1-Nov-22
789	SubType	CR	0						ProjList	ProjList	CR	Identify an L4 bar as a Change Request	NA	PMO		1-Nov-22
790	Supervisor	John Hammond	1	Supervisor	customField13	tbResSupervisor	John Hammond	37	ResList		WileyC	Resource or person tagging	NA	PMO		1-Nov-22
791	Supervisor	Jim Key	2	Supervisor	customField13	tbResSupervisor	Jim Key	38	ResList		BugsB	Resource or person tagging	NA	PMO		1-Nov-22
792	Supervisor	Helen Hunt	3	Supervisor	customField13	tbResSupervisor	Helen Hunt	39	ResList		WileyC	Resource or person tagging	NA	PMO		1-Nov-22
793	Tag Group	Business Advisors	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
794	Tag Group	Business Owners	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
795	Tag Group	Calendar	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
796	Tag Group	Category	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
797	Tag Group	Contact	6						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
798	Tag Group	Cost Code	7						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
799	Tag Group	Delivery Managers	8						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
800	Tag Group	Department	9						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
801	Tag Group	Document Purpose	10						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
802	Tag Group	Document Status	11						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
803	Tag Group	Document Type	12						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
804	Tag Group	Estimation Class	13						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
805	Tag Group	ExpectedHoursPerWeek	14						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
806	Tag Group	Ex Sponsor	15						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
807	Tag Group	ExtSystemResID	16						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
808	Tag Group	Gates Large	17						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
809	Tag Group	Gates Medium	18						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
810	Tag Group	Gates Release	19						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
811	Tag Group	Gates Small	20						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
812	Tag Group	Health	21						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
813	Tag Group	Health Indicators	22						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
814	Tag Group	Hyper Links	23						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
815	Tag Group	Investment Category	24						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
816	Tag Group	Investment Initiative	25						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
817	Tag Group	Investment Objective	26						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
818	Tag Group	Investment Strategy	27						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
819	Tag Group	L1	28						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
820	Tag Group	L2	29						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
821	Tag Group	L3	30						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
822	Tag Group	Labour Type	31						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
823	Tag Group	Life-cycle Phase	32						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
824	Tag Group	Location	33						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
825	Tag Group	Non Project Tag	34						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
826	Tag Group	OOM Estimates	35						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
827	Tag Group	Organizational Manager	36						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
828	Tag Group	Part-time Full-time	37						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
829	Tag Group	PartTimeFullTime	38						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
830	Tag Group	PercentTimeAllocated	39						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
831	Tag Group	PerecentAvailable	40						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
832	Tag Group	Phase	41						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
833	Tag Group	Portfolios	42						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
834	Tag Group	Primary Contact	43						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
835	Tag Group	Primary Line of Business	44						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
836	Tag Group	Primary Skill	45						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
837	Tag Group	Primary Strategic Priority	46						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
838	Tag Group	Priority	47						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
839	Tag Group	Product	48						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
840	Tag Group	Program Activity Alignment (PAA)	49						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
841	Tag Group	Programs	50						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
842	Tag Group	Project Managers	51						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
843	Tag Group	Project Status	52						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
844	Tag Group	Project Manager	53						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
845	Tag Group	Project Number	54						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
846	Tag Group	Resource Class	55						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
847	Tag Group	Resource Manager	56						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
848	Tag Group	Resource Role	57						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
849	Tag Group	Resource Supervisor	58						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
850	Tag Group	Resource Calendar	59						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
851	Tag Group	Responsibility	60						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
852	Tag Group	Responsible Teams	61						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
853	Tag Group	Severity	62						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
854	Tag Group	Show In Reports	63						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
855	Tag Group	ShowIn	64						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
856	Tag Group	Size	65						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
857	Tag Group	Sponsoring Department	66						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
858	Tag Group	Sponsors	67						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
859	Tag Group	Stage	68						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
860	Tag Group	Stage (Manual)	69						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
861	Tag Group	State	70						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
862	Tag Group	Status	71						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
863	Tag Group	stdTasks	72						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
864	Tag Group	tbType	73						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
865	Tag Group	Team Leader	74						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
866	Tag Group	Type Of Initiative	75						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
867	Tag Group	YesNo	76						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
868	Tag Group	Field Type	77						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
869	Tag Group	Form Name	78						General	General	NA	Setting up dynamic forms	NA	system		1-Nov-22
870	tbMDPM	tbDocSortOrder	242						General		NA	Setting up dynamic forms	NA	system		1-Nov-22
871	tbType	Action Item	0						NewBars	General	Actn	Future - drop anywhere to create an Action Item	NA	system		1-Nov-22
872	tbType	Allocation	0						NewBars	General	Alloc	Not used, see Resource Allocator to assign a new Resource	NA	system		1-Nov-22
873	tbType	Issue	0						NewBars	General	Issue	Future - drop anywhere to create a Issue	NA	system		1-Nov-22
874	tbType	Program	0						NewBars	General	Prog	Drag and Drop on Portfolio to create new Program	NA	system		1-Nov-22
875	tbType	Risk	0						NewBars	General	Risk	Future - drop anywhere to create a Risk	NA	system		1-Nov-22
876	tbType	Gate	1							NewBarsNo	Gate	Drag and Drop on Canvas to create new Portfolio	NA	System		1-Nov-22
877	tbType	Portfolio	2	Timebar Type	customfield39	tbMDTypes	L1 Portfolio	146		NewBars	L1 Portfolio	Drag and Drop on on Portfolio or Program to create new Project	NA	System		1-Nov-22
878	tbType	Project	3	Timebar Type	customfield39	tbMDTypes	L2 Project	147		NewBars	L2 Project	Drag and Drop on project to create sub project	NA	System		1-Nov-22
879	tbType	Sub-Project	4	Timebar Type	customfield39	tbMDTypes	L3 Sub-Project	148		NewBars	L3 Sub-Project	Drag and Drop on, another Task to clone it, a Project or Release to create new Task	NA	System		1-Nov-22
880	tbType	Milestone	5	Timebar Type	customfield39	tbMDTypes	L4 Milestone			NewBars	Milestone	Drag and Drop on Canvas to create new Portfolio	NA	System		1-Nov-22
881	tbType	Task	5	Timebar Type	customfield39	tbMDTypes	L4 Task	149		NewBars	Task	Drag and Drop on, another Milestone to clone it, a Project or Release to create new Milestone	NA	System		1-Nov-22
882	tbType	Allocation	6	Timebar Type	customfield39	tbMDTypes	Allocation	150		NewBars	Allocation	Drop to create a gate object on canvas	NA	System		1-Nov-22
883	tbType	Tile	7							NewBarsNo	Tile	Drag and Drop on Canvas to create new Release	NA	System		1-Nov-22
884	tbTypeInternal	Portfolio	1								L1 Portfolio		NA	System		1-Nov-22
885	tbTypeInternal	Project	2								L2 Project		NA	System		1-Nov-22
886	tbTypeInternal	Sub-Project	3								L3 Sub-Project		NA	System		1-Nov-22
887	tbTypeInternal	Task	4								L4 Task		NA	System		1-Nov-22
888	tbTypeInternal	Milestone	5								L4 Milestone		NA	System		1-Nov-22
889	tbTypeInternal	Allocation	6								Allocation		NA	System		1-Nov-22
890	Team Leader	App Team	0	Team Leader	customField14	tbResTeamLeader	App Team	41	ResList	ResList	Erica tl	Resource or person tagging	NA	system		1-Nov-22
891	Team Leader	CRM Team	0	Team Leader	customField14	tbResTeamLeader	CRM Team	40	ResList	ResList	Ben tl	Resource or person tagging	NA	system		1-Nov-22
892	Team Leader	Desktop Team	0	Team Leader	customField14	tbResTeamLeader	Desktop Team	42	ResList	ResList	Julia tl	Resource or person tagging	NA	system		1-Nov-22
893	Team Size	1-3 people				tbPASTeamSize			PAS	Scores 100	1-3 people	Tagging the Project Assessment Form
894	Team Size	4-8 people				tbPASTeamSize			PAS		4-8 people	Tagging the Project Assessment Form
895	Team Size	9-15 people				tbPASTeamSize			PAS		9-15 people	Tagging the Project Assessment Form
896	Team Size	16-30 people				tbPASTeamSize			PAS		16-30 people	Tagging the Project Assessment Form
897	Team Size	Over 30 people				tbPASTeamSize			PAS		Over 30 people	Tagging the Project Assessment Form
898	Team Tech Experience	Expert level				tbPASTeamTechExperience			PAS	Scores 100	Expert level	Tagging the Project Assessment Form
899	Team Tech Experience	Advanced				tbPASTeamTechExperience			PAS		Advanced	Tagging the Project Assessment Form
900	Team Tech Experience	Intermediate				tbPASTeamTechExperience			PAS		Intermediate	Tagging the Project Assessment Form
901	Team Tech Experience	Basic				tbPASTeamTechExperience			PAS		Basic	Tagging the Project Assessment Form
902	Team Tech Experience	No experience				tbPASTeamTechExperience			PAS		No experience	Tagging the Project Assessment Form
903	Technology Novelty	Proven/Mature				tbPASTechnologyNovelty			PAS	Scores 100	Proven/Mature	Tagging the Project Assessment Form
904	Technology Novelty	Established				tbPASTechnologyNovelty			PAS		Established	Tagging the Project Assessment Form
905	Technology Novelty	Emerging				tbPASTechnologyNovelty			PAS		Emerging	Tagging the Project Assessment Form
906	Technology Novelty	Cutting-edge				tbPASTechnologyNovelty			PAS		Cutting-edge	Tagging the Project Assessment Form
907	Technology Novelty	Experimental				tbPASTechnologyNovelty			PAS		Experimental	Tagging the Project Assessment Form
908	Timebar Priority	High	0	priority	priority	tbMDPriority	High	9	General		High	Set timebar priority	NA	PMO		1-Nov-22
909	Timebar Priority	Immediate	0	priority	priority	tbMDPriority	Immediate	10	General		Med	Set timebar priority	NA	PMO		1-Nov-22
910	Timebar Priority	Low	0	priority	priority	tbMDPriority	Low	7	General		Low	Set timebar priority	NA	PMO		1-Nov-22
911	Timebar Priority	Normal	0	priority	priority	tbMDPriority	Normal	8	General		Med	Set timebar priority	NA	PMO		1-Nov-22
912	Timebar Priority	Not Assessed	0	priority	priority	tbMDPriority	Not Assessed	14	General		Low	Set timebar priority	NA	PMO		1-Nov-22
913	Timebar Status	Rejected		status	status	tbMDStatus	Rejected	14			Rejected	Mandatory values for enabling reporting.
914	Timebar Status	In progress	0	status	status	tbMDStatus	In progress	7	ProjList		In progress	Mandatory values for enabling reporting.	NA	PMO		1-Nov-22
915	Timebar Status	New	0	status	status	tbMDStatus	New	1	ProjList		New	Mandatory values for enabling reporting.	NA	PMO		1-Nov-22
916	Timebar Status	Closed		status	status	tbMDStatus	Closed	12			Closed	Mandatory values for enabling reporting.
917	Timebar Status	On Hold		status	status	tbMDStatus	On Hold	13			On Hold	Mandatory values for enabling reporting.
918	Timebar Status	Blocked		status	status	tbMDStatus	On Hold	13			Blocked	Mandatory values for enabling reporting.
919	Type Of Initiative	Innovation Transformation	4	Type Of Initiative	customField36	tbMDProjectType	Other	131	ProjList	ProjList	Innovation/Transformation	Project Type Tagging for Portfolio Balancing	NA	system		1-Nov-22
920	Type Of Initiative	Mandatory Compliance	1	Type Of Initiative	customField36	tbMDProjectType	Program	129	ProjList	ProjList	Mandatory/Compliance	Project Type Tagging for Portfolio Balancing	NA	system		1-Nov-22
921	Type Of Initiative	Maintenance Operational	2	Type Of Initiative	customField36	tbMDProjectType	Project	128	ProjList	ProjList	Maintenance/Operational	Project Type Tagging for Portfolio Balancing	NA	system		1-Nov-22
922	Type Of Initiative	Growth Enhancement	3	Type Of Initiative	customField36	tbMDProjectType	Sprint	130	ProjList	ProjList	Growth/Enhancement	Project Type Tagging for Portfolio Balancing	NA	system		1-Nov-22
923	Vendor Dependencies	No vendors				tbPASVendorDependencies			PAS	Scores 100	No vendors	Tagging the Project Assessment Form
924	Vendor Dependencies	1 reliable vendor				tbPASVendorDependencies			PAS		1 reliable vendor	Tagging the Project Assessment Form
925	Vendor Dependencies	2-3 known vendors				tbPASVendorDependencies			PAS		2-3 known vendors	Tagging the Project Assessment Form
926	Vendor Dependencies	Multiple/new vendors				tbPASVendorDependencies			PAS		Multiple/new vendors	Tagging the Project Assessment Form
927	Vendor Dependencies	Critical unknown vendors				tbPASVendorDependencies			PAS		Critical unknown vendors	Tagging the Project Assessment Form
928	WF State	Spawned	0	State	customField38	tbMDState	Spawned	144	ProjList	ProjList	Spawned	Workflow Life-cycle tag	NA	PMO		1-Nov-22
929	WF State	Awaiting Input	1	State	customField38	tbMDState	Awaiting Input	141	ProjList	ProjList	Awaiting Input	Workflow Life-cycle tag	NA	PMO		1-Nov-22
930	WF State	Requested Approval	2	State	customField38	tbMDState	Requested Approval	142	ProjList	ProjList	Requested Approval	Workflow Life-cycle tag	NA	PMO		1-Nov-22
931	WF State	Awaiting Approval	3	State	customField38	tbMDState	Awaiting Approval	140	ProjList	ProjList	Awaiting Approval	Workflow Life-cycle tag	NA	PMO		1-Nov-22
932	WF State	Approved	4	State	customField38	tbMDState	Approved	143	ProjList	ProjList	Approved	Workflow Life-cycle tag	NA	PMO		1-Nov-22
933	WF State	Awaiting Review	5	State	customField38	tbMDState	Awaiting Review	145	ProjList	ProjList	Awaiting Review	Workflow Life-cycle tag	NA	PMO		1-Nov-22
934	WP Health	Not Assessed	0	WP Health	customField8	tbMDHealth	Blocked	19	ProjList		Not Assessed	For Dashboard indicators	NA	PMO		1-Nov-22
935	WP Health	Completed	0	WP Health	customField8	tbMDHealth	Completed	20	ProjList		Completed	For Dashboard indicators	NA	PMO		1-Nov-22
936	WP Health	Early	0	WP Health	customField8	tbMDHealth	Early	16	ProjList		Early	For Dashboard indicators	NA	PMO		1-Nov-22
937	WP Health	Late	0	WP Health	customField8	tbMDHealth	Late	18	ProjList		Late	For Dashboard indicators	NA	PMO		1-Nov-22
938	WP Health	On schedule	0	WP Health	customField8	tbMDHealth	On Schedule	15	ProjList		On schedule	For Dashboard indicators	NA	PMO		1-Nov-22
939	WP Health	Slipping	0	WP Health	customField8	tbMDHealth	Slipping	17	ProjList		Slipping	For Dashboard indicators	NA	PMO		1-Nov-22
940	YesNo	No	0						General	General	No	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
941	YesNo	Yes	0						General	General	Yes	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
942	YesNo	NA	6						General	General	NA	for tagging a time bar for true or false on unknown	NA	system		1-Nov-22
Import Data

## Fields
dfID	dfCoordTop	dfCoordLeft	dfWidth	dfName	dfType	dfFormName	dfLabel	dfTitle	dfPicklist	dfOther1	dfOther2	dfShowYN	dfOther3	dfOther4	dfOther5
Dynamic Fields Data Store								Hover title
ID	Coord Top	Coord Left	Width	Name	Type	Form Name	Label	Title	Picklist Name	Store	Status	Show YN	dfOther3	dfOther4	dfOther5
1	46	8	567	pfBand	Band	ALLOC1	Allocation Key Metadata			tbMetaData		Yes			466
2	100	8	225	tbName	NoPicklist	ALLOC1	Allocation Name			tbTimebars		Yes
3	100	290	450	tbResID	NoPicklist	ALLOC1	Resource ID			tbTimebars	disabled	Yes
4	400.5	3	172	tbBudgetHours	NoPicklist	ALLOC1	Budget Hours			tbTimebars		Yes			221
5	400	150.94	152	tbBudgetCost	NoPicklist	ALLOC1	Budget Cost			tbTimebars		Yes			221
6	192.43	289.95	75	tbID	NoPicklist	ALLOC1	UID			tbTimebars	disabled	Yes			41.36364
7	192.43	383.9	75	tbSelfKey2	NoPicklist	ALLOC1	Parent ID			tbTimebars	disabled	Yes			41.36364
8	206.45	8	125	tbStart	NoPicklist	ALLOC1	Start			tbTimebars	disabled	Yes			91.36364
9	206.45	136.45	125	tbFinish	NoPicklist	ALLOC1	Finish			tbTimebars	disabled	Yes			91.36364
10	319.91	7.35	122.72764	tbCalendar	NoPicklist	ALLOC1	Availability/Calendar			tbTimebars		Yes			89.09064
11	319.92	136.33	92.72724	tbPercentTimeOn	NoPicklist	ALLOC1	% Allocated			tbTimebars		Yes			59.07674
12	319.92	289	200	tbOwner	NoPicklist	ALLOC1	Owner			tbTimebars	disabled	Yes			59.07674
13	18.77	673.41	75	tbSelfKey2	NoPicklist	dfIssue	ParentID	ParentID		tbTimebars	disabled	Yes			71
14	19.27	753.16	75	tbID	NoPicklist	dfIssue	UID	ItemID		tbTimebars	disabled	Yes			71
15	51.88	47.91	477	tbName	NoPicklist	dfIssue	Name	Issue Name		tbTimebars		Yes	3		473
16	146.38	225.44	100	tbMDPriority	WithPicklist	dfIssue	Priority		Timebar Priority	tbMetaData		Yes			96
17	146.38	51.44	159	tbMDHealth	WithPicklist	dfIssue	Timebar Health		Schedule Status	tbMetaData		Yes			155
18	148.38	339.91	144	tbMDEscalationLevel	WithPicklist	dfIssue	Escalation Level	Escalation Level	Escalation Level	tbMetaData		Yes			140
19	148.38	495.08	125	tbStart	NoPicklist	dfIssue	Created On	Date issue resolution began.		tbTimebars	disabled	Yes			121
20	148.88	629.41	125	tbFinish	NoPicklist	dfIssue	Finish	Anticipated resolution date		tbTimebars	disabled	Yes			121
21	220.77	448.02	100	tbMDStage	WithPicklist	dfIssue	Stage	Issue Stage	RandIStage	tbMetaData		Yes			96
22	210	448.02	100	tbMDIssueCategory	WithPicklist	dfIssue	Issue Category	Issue Category	Issue Category	tbMetaData		Yes			96
23	223.91	43.3	117	tbSubType	WithPicklist	dfIssue	SubType	Sub Type is used to to change Task into Risk or Issue.	SubType	tbTimebars		Yes			113
24	223.91	177.25	137	tbMDStatus	WithPicklist	dfIssue	Timebar Status	Timebar Status	Timebar Status	tbMetData		Yes			133
25	223.91	333.58	100	tbMDState	WithPicklist	dfIssue	State	Issue State	RandIState	tbMetData		Yes			96
26	305.17	43.75	700	tbMDNotes	TextArea	dfIssue	Issue Actions and Tracking Notes	Issue Tracking Notes		tbMetaData		Yes	5		696
27	416.5	43.75	700	tbMDDescription	TextArea	dfIssue	Description	Issue Description		tbMetaData		Yes	5		696
28	540.55	50.33	728	tbMDExecutiveSummary	Editor	dfIssue	Edit Executive Summary	Issue Executive Summary		tbMetaData		Yes	5		724
29	7.83	642.33	92	tbSelfKey2	NoPicklist	dfRisk	ParentID	ParentID		tbTimebars	disabled	Yes			88
30	8.33	555.16	75	tbID	NoPicklist	dfRisk	UID	Unique ID		tbTimebars	disabled	Yes			71
31	8.33	741.61	92	tbSubType	WithPicklist	dfRisk	SubType	SubType	SubType	tbTimebars		Yes			113
32	57.88	43.91	477	tbName	NoPicklist	dfRisk	Risk Name	Risk Name		tbTimebars		Yes	3		473
33	146.33	533.47	163	tbMDState	WithPicklist	dfRisk	State	State	RandIState	tbMetaData		Yes			96
34	156.33	500.47	163	tbMDRiskCategory	WithPicklist	dfRisk	Risk Category	Risk Category	Risk Category	tbMetaData		Yes			96
35	146.33	45.91	137	tbMDStatus	WithPicklist	dfRisk	Timebar Status	Timebar Status	Timebar Status	tbMetData		Yes			133
36	146.33	357.44	167	tbMDPriority	WithPicklist	dfRisk	Priority		Timebar Priority	tbMetaData		Yes			163
37	146.33	193.44	151	tbMDHealth	WithPicklist	dfRisk	Timebar Health		Schedule Status	tbMetaData		Yes			147
38	148.08	752.25	621	tbMDMitigationPlan	Editor	dfRisk	Edit Mitigation Plan	Risk Mitigation Plan		tbMetaData		Yes	5		617
39	255.55	50.44	117	tbMDProbability	WithPicklist	dfRisk	Probability	Likelyhood of Risk happening	Risk Probability	tbMetaData		Yes			113
40	256.05	172.91	132	tbMDImpact	WithPicklist	dfRisk	Impact	Impact to the project	Risk Impact	tbMetaData		Yes			128
41	256.55	433.91	154	tbMDEscalationLevel	WithPicklist	dfRisk	Escalation Level	Escalation Level	Escalation Level	tbMetaData		Yes			150
42	256.55	312.16	108	tbMDScore	NoPicklist	dfRisk	Score	Score: Internally Calculated by the probability and impact in a percentage value		tbMetaData	disabled	Yes			104
43	350.33	511.91	125	tbFinish	NoPicklist	dfRisk	Finish	When would Risk monitoring end		tbTimebars	disabled	Yes			121
44	350.83	373.08	125	tbStart	NoPicklist	dfRisk	Start	Anticipated date of Risk materializing		tbTimebars	disabled	Yes			121
45	350.83	59.91	194	tbMDMitigationStatus	WithPicklist	dfRisk	Mitigation Status	Risk Mitigation Status	Mitigation Satus	tbMetaData		Yes			190
46	351.33	259.77	100	tbMDStage	WithPicklist	dfRisk	Stage	Stage	RandIStage	tbMetaData		Yes			96
47	431.77	57.91	315	tbMDTriggerEvent	TextArea	dfRisk	Trigger Event	Trigger Event		tbMetaData		Yes	5		311
48	431.77	382.97	339	tbMDEarlyWarningIndicators	TextArea	dfRisk	Early Warning Indicators	Early Warning Indicators		tbMetaData		Yes	5		335
49	451.08	749.91	496	tbMDContingencyPlan	Editor	dfRisk	Contingency Plan	Contingency Plan		tbMetaData		Yes	5		492
50	524.17	45.91	597	tbMDDescription	TextArea	dfRisk	Risk Description	Risk Description		tbMetaData		Yes	5		593
51	612.58	45.91	631	tbMDNotes	TextArea	dfRisk	Risk Actions and Tracking Notes	Risk Tracking Notes		tbMetaData		Yes	5		627
52	735.94	51.91	669	tbMDExecutiveSummary	Editor	dfRisk	Edit Executive Summary	Risk Executive Summary short description please		tbMetaData		Yes	5		665
53	753.08	749.91	447	tbMDRiskResponseStrategy	Editor	dfRisk	Risk Response Strategy	Risk Response Strategy		tbMetaData		Yes	5		443
54	60	10.44	557	pfBand	Band	PF1	Portfolio Information					Yes			553
55	122	6.13	417	tbName	NoPicklist	PF1	Portfolio Name			tbTimebars		Yes			382
56	211.5	263.28	200	tbMDPM	NoPicklist	PF1	PM			tbMetaData		Yes			196
57	211.5	3	137	tbBudgetHours	NoPicklist	PF1	Budget Hours			tbTimebars		Yes			196
58	211.5	130.94	147	tbBudgetCost	NoPicklist	PF1	Budget Cost			tbTimebars		Yes			196
59	122	402.86	100	tbMDID	NoPicklist	PF1	UID			tbMetaData	disabled	Yes			96
60	287	4.94	400	tbMDDescription	TextArea	PF1	Description			tbMetaData		Yes			396
61	400	4.94	400	tbMDExecutiveSummary	TextArea	PF1	Executive Summary			tbMetaData		Yes			396
62	37	455.41	107	tbID	NoPicklist	PJ1	UID			tbTimebars	disabled	Yes			46
63	55	1	451	pfBand	Band	PJ1	Project Key Metadata			tbMetaData		Yes			496
64	107	6.95	380	tbName	NoPicklist	PJ1	ProjectName			tbTimebars		Yes			376
65	253	6.27	144	tbBudgetHours	NoPicklist	PJ1	Budget Hours			tbTimebars		Yes			140
66	253.5	198.94	137	tbBudgetCost	NoPicklist	PJ1	Budget Cost			tbTimebars		Yes			133
67	175.5	-2.7	132	tbMDProjectNumber	NoPicklist	PJ1	Project Number			tbMetaData		Yes			128
68	175.5	131.27	125	tbMDStatus	WithPicklist	PJ1	Project Status	Project Status	Project Status	tbMetaData		Yes			121
69	175.5	270	237	tbMDProduct	WithPicklist	PJ1	Product		Product	tbMetaData		Yes			233
70	542.5	2.3	221	tbPredecessor	NoPicklist	PJ1	Predecessor Project ID			tbTimebars		Yes			217
71	347.25	4.94	400	tbMDDescription	TextArea	PJ1	Brief Description			tbMetaData		Yes			396
72	457.5	-4.17	600	tbMDNotesProject	TextArea	PJ1	Project Notes			tbMetaData		Yes			596
73	35	1	417	pfBand	Band	SPJ1	Sub Project Key Metadata			tbMetaData		Yes
74	20.5	415	75	tbID	NoPicklist	SPJ1	UID			tbTimebars	disabled	Yes			71
75	95.5	0	380	tbName	NoPicklist	SPJ1	Sub Project Name			tbTimebars		Yes			376
76	252	13	177	tbBudgetHours	NoPicklist	SPJ1	Budget Hours			tbTimebars		Yes			173
77	251.5	198.94	177	tbBudgetCost	NoPicklist	SPJ1	Budget Cost			tbTimebars		Yes			173
78	177.5	4.34	159	tbMDProjectNumber	NoPicklist	SPJ1	Project Number			tbMetaData		Yes			155
79	175.5	164.33	100	tbMDPriority	WithPicklist	SPJ1	Priority		Timebar Priority	tbMetaData		Yes			96
80	175.5	273.94	157	tbMDStatus	WithPicklist	SPJ1	Project Status	Project Status	Project Status	tbMetaData		Yes			153
81	339.94	4.94	400	tbMDDescription	TextArea	SPJ1	Brief Description			tbMetaData		Yes			396
82	45	10	495.44064	pfBand	Band	TASK1	Task Key Metadata			tbMetaData		Yes			491.44
83	95.5	430.94	90.44034	tbSelfKey2	NoPicklist	TASK1	ParentID			tbTimebars	disabled	Yes			86.44
84	95.5	337.23	92.72724	tbID	NoPicklist	TASK1	UID			tbTimebars	disabled	Yes			88.72
85	95.5	11.95	321.719	tbName	NoPicklist	TASK1	Task Name			tbTimebars		Yes			340.72
86	162	309.95	100	tbMDPriority	WithPicklist	TASK1	Priority		Timebar Priority	tbMetaData		Yes			96
87	162	11.95	100	tbSubType	WithPicklist	TASK1	SubType		SubType	tbTimebars		Yes			96
88	162	136.44	157	tbMDStatus	WithPicklist	TASK1	Timebar Status	Timebar Status	Timebar Status	tbMetaData		Yes			153
89	162	421.44	100	tbMDState	WithPicklist	TASK1	State		RandIState	tbMetaData		Yes			96
90	248.55	10.28	125	tbStart	NoPicklist	TASK1	Start			tbTimebars	disabled	Yes			121
91	251.05	150	125	tbFinish	NoPicklist	TASK1	Finish			tbTimebars	disabled	Yes			121
92	250.55	275.94	75	tbDuration	NoPicklist	TASK1	Duration			tbTimebars		Yes			71
93	250.05	345.94	75	tbRemainingDuration	NoPicklist	TASK1	Rem Dur			tbTimebars		Yes			71
94	398	16.92	125	tbWork	NoPicklist	TASK1	Work			tbTimebars		Yes			121
95	398	146.45	142	tbAWork	NoPicklist	TASK1	Actual Work			tbTimebars		Yes			121
96	400	281.44	178	tbWorkRemaining	NoPicklist	TASK1	Work Remaining			tbTimebars		Yes			174
97	316	16.91	125	tbBudgetHours	NoPicklist	TASK1	Budget Hours			tbTimebars		Yes			121
98	316	170	125	tbBudgetCost	NoPicklist	TASK1	Budget Cost			tbTimebars		Yes			121
99	472	15	182	tbOwner	NoPicklist	TASK1	Owner			tbTimebars		Yes			121
100	472	170	182	tbMDEscalationLevel	WithPicklist	TASK1	Escalation Level		Escalation Level	tbMetaData		Yes			178
101	550.67	10.12	472	tbMDDescription	TextArea	TASK1	Description			tbMetaData		Yes			468
102	630.67	10.09	482	tbMDNotes	TextArea	TASK1	Risk Actions and Tracking Notes			tbMetaData		Yes			455.5
Import Data

## Documents
tbDocID	tbDocL1	tbDocL2	tbDocL3	tbDocL4	tbDocL5	tbDocCardImage	tbDocName	tbDocNameShort	tbDocHTMLContent	tbDocStatus	tbDocPurpose	tbDocWrittenBy	tbDocBriefDescription	tbDocCustomerID	tbDocType	tbDocGroup	tbDocOwner	tbDocPopular	tbDocSortOrder	tbDocLastModified	tbDocApprovedBy	id
Documents	Must be the tbID of the parent timebar.	Used to generate Chips in Document Cards Page					Mandatory and brief		Main content for the doc, populated by editor or by hand here	Uses picklist Document Status
tbDocID	tbDocL1	tbDocL2	tbDocL3	tbDocL4	tbDocL5	tbDocCardImage	tbDocName	tbDocNameShort	tbDocHTMLContent	tbDocStatus	tbDocPurpose	tbDocWrittenBy	tbDocBriefDescription	tbDocCustomerID	tbDocType	tbDocGroup	tbDocOwner	tbDocPopular	tbDocSortOrder	tbDocLastModified	tbDocApprovedBy	id
2	A012	Business Case					Business Case for ID 20		This is my content	Approved		Jim Cox	my brief2	44	HTML		Jim Cox	Yes		21-Oct-22	JC	10
3	B013	Business Case					Business Case for ID 40		This is my content	First Draft		Jim Cox	my brief3	44	HTML		Jim Cox	Yes		21-Oct-22	JC	11
4	A012	Project Charter					Business Case for ID 20		This is my content	Approved		Jim Cox	my brief4	44	HTML		Jim Cox	Yes		21-Oct-22	JC	12
5	B013	Project Charter					Business Case for ID 40		This is my content	Approved		Jim Cox	my brief5	44	HTML		Jim Cox	Yes		21-Oct-22	JC	13
Import Data

## TBMDJoined
tbID	tbSelfKey2	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	tbCoordTopP3Menu	kbCoordLeft	tbPredecessor	tbResID	tbOwner	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbBudget	tbBudgetRollupYN	tbCost	tbACost	tbCostRemaining	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbCostID	tbCostType	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	tbStatus	tbState	tbPriority	tbMDID	tbMDParent	tbMDName	tbMDTypes	tbMDSubtype	tbMDHierarchy	tbMDProduct	tbMDNotesProject	tbMDDescription	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDHealth	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDIssueCategory	tbMDEscalationLevel	tbMDProjectNumber	tbMDPM	tbMDExSponsor	tbMDNotes	tbMDPrimaryContact	tbMDDepartment	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDProjectType	tbMDRiskVsSizeAndComplexity	tbMDROMEstimate	tbMDEstimationClass	tbMDSize	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDYesNoSelector	tbMDPriorityStrategic	tbMDCostbarsScore	tbMDFinancialScore	tbMDDecisionStrategic	tbMDDecisionNotes	tbMDPrimaryLineOfBusiness	tbMDSponsoringDepartment	tbMDContact	tbMDContactNumber	tbMDResponsibleTeam	tbMDBusinessAdvisor	tbMDDeliveryManager	tbMDOrgManager	tbMDBenefitCostRatio	tbMDEcnomicValueAdded	tbMDInternalRateOfReturn	tbMDSunkCosts	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDOther2	tbMDBusinessOwner	tbMDBackgroundInfo	tbMDStakeholderDescription	tbMDProblemOpportunity	tbMDOptionsAnalysis	tbMDConsequence	tbMDKeyDependencies	tbMDValueProposition	tbMDSuccessCriteria	tbMDDecisionsRequired	tbMDKeyRecommendations	tbMDMarketAnalysis	tbMDPortfolioImpactAnalysis	tbMDKeyProjectMetrics	tbMDObjectivesAndScope	tbMDExpectedBenefits	tbMDCapabilitiesNeeded	tbMDImplementationApproach	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommitment	tbMDNextSteps	tbMDWrittenBy	tbMDVersion	tbMDBCaseDateApproved	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDResID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDResponsibility	tbMDExtSystemID1	tbMDSyncNotes	tbMDStageApprover	tbMDSprintName	tbMDExtLink1	tbMDOther3	canvasNo	tbMDRefID	tbMDSortOrder	tbMDtbLastModified	tbMDShowIn	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDNotesWorkflow	tbMDContractNumber	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSeverity	tbMDContingency	tbMDMitigationPlan	tbMDMitigationStatus	tbMDProbability	tbMDImpact	tbMDScore	tbMDRiskCategory	tbMDRiskResponseStrategy	tbMDContingencyPlan	tbMDTriggerEvent	tbMDEarlyWarningIndicators	tbMDOther4	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	tbMDPrerequisitesChecklist	tbMDScheduleCommentary	tbMDBudgetCommentary	tbMDScopeCommentary	tbMDResourceCommentary	tbMDFinancialCommentary	blID	blName	blSelfKey2	blType	blStart	blFinish	blAStart	blAFinish	blDuration	blRemainingDuration	blWork	blAWork	blWorkRemaining	blPercentComplete	blCost	blACost	blCostRemaining	blResCostCode	blResID	blCalendar	blPercentTimeOn	blCostType	blPayRate	blSchEngOverride	blOwner	blL1	blL2	blL3	blL4	blL5	blHierarchyOrder	blStartVariance	blFinishVariance	blCostVariance	blWorkVariance	blDurationVariance
TbMDJoined -Derived Data Store missing PAS fields								Total of 186 columns, a join of Timebars, MetaData and Baseline Stores.
UID	Parent	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Custom Coord Top	Lane	Predecessor	ResID	Owner	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	Budget	Budget Rollup YN	Cost	Actual Cost	Cost Remaining	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbCostID	Cost Type	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage	Status	State	Priority	MDUID	Parent	Name	Type	SubType	Hierarchy Order	Product	Project Notes	Description	Executive Summary	Priority	Status	Schedule Status	WF State	Stage	Phase	Gate	Category	Issue Category	Escelation Level	Project Number	PM	Executive Sponsor	General Notes	Primary Contact	Department	Health Overall	Health Scope	Health Cost	Health Issues	Health Risk	Health Schedule	Health Hours	Initiative Type	Risk Vs Size And Complexity	ROM Estimate	Estimation Class	Size	Investment Category	Investment Initiative	Investment Objective	Investment Strategy	Selected	Strategic Priority	Costbars Score	Financial Score	Strategic Decision	Decision Notes	Primary Line Of Business	Sponsoring Department	Contact	Contact Number	Responsible Team	Business Advisor	Delivery Manager	Organization Manager	Benefit Cost Ratio	Ecnomic Value Added	Internal Rate Of Return	Sunk Costs	Net Present Value	Opportunity Cost	Payback Period	Financial Score	Business Owner	Background Info	Stakeholder Description	Problem Opportunity	Options Analysis	Consequence of Inaction	Key Dependencies	Value Proposition	Success Criteria	Decisions Required	Key Recommendations	Market Analysis	Portfolio Impact Analysis	Key Project Metrics	Objectives and Scope	Expected Benefits	Capabilities Needed	Implementation Approach	Constraints Assumptions	Cost Benefit Analysis	Senior Level Committment	Next Steps	Written By	B Case Version	B Case Date Approved	WBS	Weighting	Location	ResID	Primary Skill	Primary Role	Responsibility	Ext ID	Sync Notes	Stage Approver	Sprint Name	tbMDExtLink1	Other3	canvasNo	tbMDRefID	Sort Order	Last Modified	Show In	Customer ID	Azure ID	Name Short	Notes Workflow	Contract Number	Portfolio	Program	Program Activity Alignment	Severity	Contingency	Mitigation Plan	Mitigation Status	Probability	Impact	Score	Risk Category	Risk Response Strategy	Contingency Plan	Trigger Event	Early Warning Indicators	tbMDOther4	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	Prerequisites Checklist	Schedule Commentary	Budget Commentary	Scope Commentary	Resource Commentary	Financial Commentary	blID	blName	blSelfKey2	blType	blStart	blFinish	blAStart	blAFinish	blDuration	blRemainingDuration	blWork	blAWork	blWorkRemaining	blPercentComplete	blCost	blACost	blCostRemaining	blResCostCode	blResID	blCalendar	blPercentTimeOn	blCostType	blPayRate	blSchEngOverride	blOwner	blL1	blL2	blL3	blL4	blL5	blHierarchyOrder	blStartVariance	blFinishVariance	blCostVariance	blWorkVariance	blDurationVariance
Import Data

## ResCalcs
tbResCalcID	tbResCalcTbResID	tbResCalcName	tbResCalcCustomerID	tbResCalcWeek	tbResCalcWdays	tbResCalcStartWeekNo	tbResCalcTbWeekNo	tbResCalcWeekSumHours	tbResCalcWeekSumCost	tbResCalcLastModified	tbResCalcTbID	id
Rescalcs Data Store		(Burndown Chart Data)
tbResCalcID	tbResCalcTbResID	tbResCalcName	tbResCalcCustomerID	tbResCalcWeek	tbResCalcWdays	tbResCalcStartWeekNo	tbResCalcTbWeekNo	tbResCalcWeekSumHours	tbResCalcWeekSumCost	tbResCalcLastModified	tbResCalcTbID	id
Import Data

## ResCalcs2
tbResCalcID	tbResCalcTbID	tbResCalcResID	tbResCalcWeekNo	tbResCalcName	tbName	tbType	tbResCalcMonday	tbResCalcWeek	tbResCalcFriday	tbResCalcHours	tbResCalcCost	tbResCalcWdays	apStatusDate	tbResCalcCustomerID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDNameShort	tbMDLocation	tbMDDepartment	tbL1	tbL2	tbL3	tbL4	tbL5	tbOwner
Rescalcs2 Data Store		(Resource Stacked Chart Data)
tbResCalcID	tbResCalcTbID	tbResCalcResID	tbResCalcWeekNo	tbResCalcName	tbName	tbType	tbResCalcMonday	tbResCalcWeek	tbResCalcFriday	tbResCalcHours	tbResCalcCost	tbResCalcWdays	apStatusDate	tbResCalcCustomerID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDNameShort	tbMDLocation	tbMDDepartment	tbL1	tbL2	tbL3	tbL4	tbL5	tbOwner
Import Data

## Charts
tbChartID	tbChartTbId	tbChartName	tbChartType	tbChartLabels	tbChartDataset1	tbChartDataset2	tbChartDataset3	tbChartDataset4	tbChartConfig1	tbChartConfig2	tbChartCustomerID	id
Charts Data Store
tbChartID	tbChartTbId	tbChartName	tbChartType	tbChartLabels	tbChartDataset1	tbChartDataset2	tbChartDataset3	tbChartDataset4	tbChartConfig1	tbChartConfig2	tbChartCustomerID	id
1	2	Burndown Chart	Bar	["Wk1","Wk2","Wk3","Wk4","Wk5","Wk6","Wk7"]	[65,59,80,81,56,55,40]	[65,50,70,88,66,55,20]					44	3
Import Data

## ResCalcsUsage
id	tbResCalcProject	tbResCalcResID	tbResCalcWeek1	tbResCalcWeek2	tbResCalcWeek3	tbResCalcWeek4	tbResCalcWeek5	tbResCalcWeek6	tbResCalcWeek7	tbResCalcWeek8	tbResCalcWeek9	tbResCalcWeek10	tbResCalcWeek11	tbResCalcWeek12	tbResCalcWeek13	tbResCalcWeek14	tbResCalcWeek15	tbResCalcWeek16	tbResCalcWeek17	tbResCalcWeek18	tbResCalcWeek19	tbResCalcWeek20	tbResCalcWeek21	tbResCalcWeek22	tbResCalcWeek23	tbResCalcWeek24	tbResCalcWeek25	tbResCalcWeek26	tbResCalcWeek27	tbResCalcWeek28	tbResCalcWeek29	tbResCalcWeek30	tbResCalcWeek31	tbResCalcWeek32	apStatusDate	tbResCalcLastModified	tbResCalcResName
ResCalcUsage Data Store (Weekly Usage)
id	tbResCalcProject	tbResCalcResID	tbResCalcWeek1	tbResCalcWeek2	tbResCalcWeek3	tbResCalcWeek4	tbResCalcWeek5	tbResCalcWeek6	tbResCalcWeek7	tbResCalcWeek8	tbResCalcWeek9	tbResCalcWeek10	tbResCalcWeek11	tbResCalcWeek12	tbResCalcWeek13	tbResCalcWeek14	tbResCalcWeek15	tbResCalcWeek16	tbResCalcWeek17	tbResCalcWeek18	tbResCalcWeek19	tbResCalcWeek20	tbResCalcWeek21	tbResCalcWeek22	tbResCalcWeek23	tbResCalcWeek24	tbResCalcWeek25	tbResCalcWeek26	tbResCalcWeek27	tbResCalcWeek28	tbResCalcWeek29	tbResCalcWeek30	tbResCalcWeek31	tbResCalcWeek32	apStatusDate	tbResCalcLastModified	tbResCalcResName
Import Data

## CoreReport
tbCRID	tbCRSection	tbCRFieldName	tbCRPortfolio	tbCRProject	tbCRSubProject	tbCRTask	tbCRAllocation	tbCRNoOfColumns
	Core Report Settings		Note: Do not show PAS Fields
CRID	MD Form Section	Field ID	L1 Brown Bar	L2 Green Bar	L3 Orange Bar	L4 Blue Bar	L5 Gold Bar	NoOfColumns
1	coreFormSection1-Notes	tbID	show	show	show	show	show	3
2	coreFormSection1-Notes	tbSubType	show	show	show	show	show	3
3	coreFormSection1-Notes	tbMDNameShort	show	show	show	show	show	3
4	coreFormSection1-Notes	tbHierarchyOrder	show	show	show	show	show	3
5	coreFormSection1-Notes	tbOwner	show	show	show	show	show	3
6	coreFormSection1-Notes	tbMDPM		show	show			3
7	coreFormSection1-Notes	tbName	show	show	show	show	show	2
8	coreFormSection1-Notes	tbMDDescription	show	show	show	show		2
9	coreFormSection1-Notes	tbMDNotes	show	show	show	show		2
10	coreFormSection1-Notes	tbMDExecutiveSummary	show	show	show	show		2
11	coreFormSection2-Progress	tbMDStatus	show	show	show	show	show	3
12	coreFormSection2-Progress	tbMDEscalationLevel	show	show	show	show	show	3
13	coreFormSection2-Progress	tbMDHealth		show	show	show	show	3
14	coreFormSection2-Progress	tbMDState	show	show	show	show	show	3
15	coreFormSection2-Progress	tbMDPriority	show	show	show	show	show	3
16	coreFormSection2-Progress	tbMDCategory		show	show	show	show	3
17	coreFormSection2-Progress	tbMDStage		show	show	show	show	3
18	coreFormSection2-Progress	tbMDPhase		show	show	show	show	3
19	coreFormSection2-Progress	tbMDExtSystemID1		show	show	show	show	3
20	coreFormSection3-Common	tbMDExSponsor		show	show			3
21	coreFormSection3-Common	tbMDResponsibleTeam		show	show			3
22	coreFormSection3-Common	tbMDProjectNumber		show	show			3
23	coreFormSection3-Common	tbOwner	show	show	show	show	show	3
24	coreFormSection3-Common	tbMDProduct		show	show			3
25	coreFormSection3-Common	tbMDContact		show	show			3
26	coreFormSection3-Common	tbMDResponsibility				show		3
27	coreFormSection3-Common	tbMDSeverity				show		3
28	coreFormSection3-Common	tbMDDepartment		show	show	show	show	3
29	coreFormSection3-Common	tbMDShowIn				show	show	3
30	coreFormSection3-Common	tbMDDeliveryManager						3
31	coreFormSection3-Common	tbMDtbLastModified				show	show	3
32	coreFormSection4-Health	tbMDHealthOverall	show	show	show			3
33	coreFormSection4-Health	tbMDHealthCost	show	show	show			3
34	coreFormSection4-Health	tbMDHealthRisk	show	show	show			3
35	coreFormSection4-Health	tbMDHealthSchedule	show	show	show			3
36	coreFormSection4-Health	tbMDHealthScope	show	show	show			3
37	coreFormSection4-Health	tbMDHealthIssues	show	show	show			3
38	coreFormSection5-Estimates	tbMDSize		show	show			3
39	coreFormSection5-Estimates	tbMDEstimationClass		show	show			3
40	coreFormSection5-Estimates	tbMDROMEstimate		show	show			3
41	coreFormSection5-Estimates	tbMDRiskVsSizeAndComplexity		show	show			3
42	coreFormSection5-Estimates	tbMDWeighting				show		3
43	coreFormSection5-Estimates	tbMDGate		show	show			3
44	coreFormSection6-Hierarchy	tbL1		show	show	show	show	3
45	coreFormSection6-Hierarchy	tbL2			show	show	show	3
46	coreFormSection6-Hierarchy	tbL3				show	show	3
47	coreFormSection6-Hierarchy	tbL4					show	3
48	coreFormSection6-Hierarchy	tbL5						3
49	coreFormSection6-Hierarchy	tbMDWBS				show		3
50	coreFormSection6-Hierarchy	tbWbsDescription				show		3
51	coreFormSection7-Strategy	tbMDInvestmentObjective		show				3
52	coreFormSection7-Strategy	tbMDInvestmentStrategy		show				3
53	coreFormSection7-Strategy	tbMDInvestmentInitiative		show				3
54	coreFormSection7-Strategy	tbMDPriorityStrategic		show				3
55	coreFormSection7-Strategy	tbMDInvestmentCategory		show				3
56	coreFormSection8-InvestmentPlan	tbMDBusinessAdvisor		show				3
57	coreFormSection8-InvestmentPlan	tbMDPrimaryLineOfBusiness		show				3
58	coreFormSection8-InvestmentPlan	tbMDBusinessOwner		show				3
59	coreFormSection8-InvestmentPlan	tbMDSponsoringDepartment		show				3
60	coreFormSection8-InvestmentPlan	tbMDPortfolio		show				3
61	coreFormSection8-InvestmentPlan	tbMDProjectType		show				3
62	coreFormSection8-InvestmentPlan	tbMDNotesProject		show				3
63	coreFormSection8-InvestmentPlan	tbMDContractNumber		show				3
64	coreFormSection8-InvestmentPlan	tbMDPrimaryContact		show				3
65	coreFormSection8-InvestmentPlan	tbMDContactNumber		show				3
66	coreFormSection8-InvestmentPlan	tbMDNetPresentValue						3
67	coreFormSection8-InvestmentPlan	tbMDOpportunityCost						3
68	coreFormSection8-InvestmentPlan	tbMDSunkCosts						3
69	coreFormSection8-InvestmentPlan	tbMDPaybackPeriod						3
70	coreFormSection8-InvestmentPlan	tbMDInternalRateOfReturn						3
71	coreFormSection8-InvestmentPlan	tbMDEcnomicValueAdded						3
72	coreFormSection8-InvestmentPlan	tbMDBenefitCostRatio						3
73	coreFormSection8-InvestmentPlan	tbMDProgram						3
74	coreFormSection9-BusinessCase	tbMDBackgroundInfo						2
75	coreFormSection9-BusinessCase	tbMDStakeholderDescription						2
76	coreFormSection9-BusinessCase	tbMDConsequence						2
77	coreFormSection9-BusinessCase	tbMDExpectedBenefits						2
78	coreFormSection9-BusinessCase	tbMDProblemOpportunity						2
79	coreFormSection9-BusinessCase	tbMDCapabilitiesNeeded						2
80	coreFormSection9-BusinessCase	tbMDSeniorLevelCommitment		show				2
81	coreFormSection9-BusinessCase	tbMDConstraintsAssumptions						2
82	coreFormSection9-BusinessCase	tbMDCostBenefitAnalysis						2
83	coreFormSection9-BusinessCase	tbMDWrittenBy						2
84	coreFormSection9-BusinessCase	tbMDObjectivesAndScope						2
85	coreFormSection9-BusinessCase	tbMDOptionsAnalysis						2
86	coreFormSection9-BusinessCase	tbMDImplementationApproach						2
87	coreFormSection9-BusinessCase	tbMDNextSteps						2
88	coreFormSection9-BusinessCase	tbMDVersion						2
89	coreFormSection9-BusinessCase	tbMDBCaseDateApproved						2
90	coreFormSection9-BusinessCase	tbMDKeyDependencies
91	coreFormSection9-BusinessCase	tbMDValueProposition
92	coreFormSection9-BusinessCase	tbMDSuccessCriteria
93	coreFormSection9-BusinessCase	tbMDDecisionsRequired	show	show	show	show	show	2
94	coreFormSection9-BusinessCase	tbMDKeyRecommendations
95	coreFormSection9-BusinessCase	tbMDMarketAnalysis
96	coreFormSection9-BusinessCase	tbMDPortfolioImpactAnalysis
97	coreFormSection9-BusinessCase	tbMDKeyProjectMetrics
98	coreFormSection9b-Commentary	tbMDPrerequisitesChecklist
99	coreFormSection9b-Commentary	tbMDScheduleCommentary
100	coreFormSection9b-Commentary	tbMDBudgetCommentary
101	coreFormSection9b-Commentary	tbMDScopeCommentary
102	coreFormSection9b-Commentary	tbMDResourceCommentary
103	coreFormSection9b-Commentary	tbMDFinancialCommentary
104	coreFormSection10-Other	tbMDSprintName						3
105	coreFormSection10-Other	tbMDSortOrder	show	show	show	show	show	3
106	coreFormSection10-Other	tbMDYesNoSelector	show	show	show	show	show	3
107	coreFormSection10-Other	tbMDCustomerID	show	show	show	show	show	3
108	coreFormSection10-Other	tbMDAzureID						3
109	coreFormSection10-Other	tbMDRefID						3
110	coreFormSection10-Other	tbMDNotesWorkflow						3
111	coreFormSection10-Other	tbMDStageApprover						3
112	coreFormSection10-Other	tbMDSyncNotes						3
113	coreFormSection10-Other	tbMDOther2	show	show	show	show	show	3
114	coreFormSection10-Other	tbMDOther3	show	show	show	show	show	3
115	coreFormSection10-Other	tbMDOther4	show	show	show	show	show
116	coreFormSection10-Other	tbMDOther5	show	show	show	show	show
117	coreFormSection10-Other	tbMDOther6
118	coreFormSection10-Other	tbMDOther7
119	coreFormSection10-Other	tbMDOther8
120	coreFormSection10-Other	tbMDOther9
121	coreFormSection10-Other	tbMDOther10
122	coreFormSection10-Other	tbMDOther11
123	coreFormSection10-Other	tbMDOther12
Import Data

## FormatSheets
ID	SheetName	FieldName	DataType	Alignment	Width
1	Timebars	tbID	Text	Left	15
2	Timebars	tbSelfKey2	Text	Left	15
3	Timebars	tbPredecessor	Text	Left	15
4	Timebars	tbName	Text	Left	100
5	Timebars	tbType	Text	Left	20
6	Timebars	tbSubType	Text	Left	15
7	Timebars	tbHierarchyOrder	Text	Left	26
8	Timebars	tbCoordTop	Number	Center	10
9	Timebars	kbCoordTop	Number	Center	1
10	Timebars	kbCoordLeft	Number	Center	1
11	Timebars	tbCoordTopP3Menu	Text	Left	1
12	Timebars	tbResID	Text	Left	15
13	Timebars	tbOwner	Text	Left	25
14	Timebars	tbWork	Number	Left	18
15	Timebars	tbAWork	Number	Left	18
16	Timebars	tbWorkRemaining	Number	Left	18
17	Timebars	tbPercentComplete	Number	Left	18
18	Timebars	tbStart	Date	Left	25
19	Timebars	tbFinish	Date	Left	25
20	Timebars	tbAStart	Date	Left	25
21	Timebars	tbAFinish	Date	Left	25
22	Timebars	tbDuration	Number	Left	15
23	Timebars	tbRemainingDuration	Number	Left	15
24	Timebars	tbCost	Currency	Left	18
25	Timebars	tbACost	Currency	Left	18
26	Timebars	tbCostRemaining	Currency	Left	18
27	Timebars	tbCalendar	Text	Left	12
28	Timebars	tbExpHoursPerWeek	Text	Left	12
29	Timebars	tbPercentTimeOn	Text	Left	12
30	Timebars	tbPayRate	Text	Left	12
31	Timebars	tbCostID	Text	Left	12
32	Timebars	tbCostType	Text	Left	12
33	Timebars	tbPhase	Text	Left	12
34	Timebars	tbL1	Text	Left	50
35	Timebars	tbL2	Text	Left	50
36	Timebars	tbL3	Text	Left	50
37	Timebars	tbL4	Text	Left	50
38	Timebars	tbL5	Text	Left	50
39	Timebars	tbWbsDescription	Text	Left	10
40	Timebars	tbConstraintType	Text	Left	10
41	Timebars	tbConstraintDate	Text	Left	10
42	Timebars	tbFloat	Text	Left	10
43	Timebars	tbFreeFloat	Text	Left	10
44	Timebars	canvasNo	Text	Left	10
45	Timebars	focdItemCoordLeft	Text	Left	10
46	Timebars	focdItemCoordTop	Text	Left	10
47	Timebars	tbBarColor	Text	Left	10
48	Timebars	tbTextColor	Text	Left	10
49	Timebars	tbBarHeight	Text	Left	10
50	Timebars	tbBLID	Text	Left	10
51	Timebars	tbCustomerID	Text	Left	10
52	Timebars	tbSchEngOverride	Text	Left	10
53	Timebars	tbT1	Text	Left	10
54	Timebars	tbT2	Text	Left	10
55	Timebars	tbStep	Text	Left	10
56	Timebars	tbStepStatus	Text	Left	10
57	Timebars	tbWfReasonNote	Text	Left	2
58	Timebars	tbStage	Text	Left	10
59	Timebars	tbStatus	Text	Left	10
60	Timebars	tbState	Text	Left	10
61	Timebars	tbPriority	Text	Left	18
62	Timebars	tbTaskParent	Text	Left	10
63	MetaData	tbMDID	Text	Left	15
64	MetaData	tbMDParent	Text	Left	15
65	MetaData	tbMDName	Text	Left	60
66	MetaData	tbMDTypes	Text	Left	20
67	MetaData	tbMDSubtype	Text	Left	20
68	MetaData	tbMDHierarchy	Text	Left	26
69	MetaData	tbMDProduct	Text	Left	24
70	MetaData	tbMDNotesProject	Text	Left	15
71	MetaData	tbMDDescription	Text	Left	30
72	MetaData	tbMDExecutiveSummary	Text	Left	30
73	MetaData	tbMDPriority	Text	Left	18
74	MetaData	tbMDStatus	Text	Left	20
75	MetaData	tbMDHealth	Text	Left	18
76	MetaData	tbMDState	Text	Left	20
77	MetaData	tbMDStage	Text	Left	20
78	MetaData	tbMDPhase	Text	Left	20
79	MetaData	tbMDGate	Text	Left	20
80	MetaData	tbMDCategory	Text	Left	20
81	MetaData	tbMDEscalationLevel	Text	Left	20
82	MetaData	tbMDProjectNumber	Text	Left	20
83	MetaData	tbMDPM	Text	Left	30
84	MetaData	tbMDExSponsor	Text	Left	30
85	MetaData	tbMDNotes	Text	Left	50
86	MetaData	tbMDPrimaryContact	Text	Left	30
87	MetaData	tbMDDepartment	Text	Left	25
88	MetaData	tbMDHealthOverall	Text	Left	18
89	MetaData	tbMDHealthScope	Text	Left	18
90	MetaData	tbMDHealthCost	Text	Left	18
91	MetaData	tbMDHealthIssues	Text	Left	18
92	MetaData	tbMDHealthRisk	Text	Left	18
93	MetaData	tbMDHealthSchedule	Text	Left	18
94	MetaData	tbMDHealthHours	Text	Left	18
95	MetaData	tbMDProjectType	Text	Left	20
96	MetaData	tbMDRiskVsSizeAndComplexity	Text	Left	20
97	MetaData	tbMDROMEstimate	Text	Left	26
98	MetaData	tbMDEstimationClass	Text	Left	20
99	MetaData	tbMDSize	Text	Left	20
100	MetaData	tbMDInvestmentCategory	Text	Left	30
101	MetaData	tbMDInvestmentInitiative	Text	Left	30
102	MetaData	tbMDInvestmentObjective	Text	Left	30
103	MetaData	tbMDInvestmentStrategy	Text	Left	30
104	MetaData	tbMDYesNoSelector	Text	Left	30
105	MetaData	tbMDPriorityStrategic	Text	Left	18
106	MetaData	tbMDCostbarsScore	Text	Left	18
107	MetaData	tbMDFinancialScore	Text	Left	18
108	MetaData	tbMDDecisionStrategic	Text	Left	30
109	MetaData	tbMDDecisionNotes	Text	Left	50
110	MetaData	tbMDPrimaryLineOfBusiness	Text	Left	30
111	MetaData	tbMDSponsoringDepartment	Text	Left	25
112	MetaData	tbMDContact	Text	Left	30
113	MetaData	tbMDContactNumber	Text	Left	30
114	MetaData	tbMDResponsibleTeam	Text	Left	30
115	MetaData	tbMDBusinessAdvisor	Text	Left	30
116	MetaData	tbMDDeliveryManager	Text	Left	30
117	MetaData	tbMDOrgManager	Text	Left	30
118	MetaData	tbMDBenefitCostRatio	Text	Left	20
119	MetaData	tbMDEcnomicValueAdded	Text	Left	20
120	MetaData	tbMDInternalRateOfReturn	Text	Left	20
121	MetaData	tbMDSunkCosts	Text	Left	20
122	MetaData	tbMDNetPresentValue	Text	Left	20
123	MetaData	tbMDOpportunityCost	Text	Left	20
124	MetaData	tbMDPaybackPeriod	Text	Left	20
125	MetaData	tbMDOther2	Text	Left	20
126	MetaData	tbMDBusinessOwner	Text	Left	30
127	MetaData	tbMDBackgroundInfo	Text	Left	30
128	MetaData	tbMDCapabilitiesNeeded	Text	Left	30
129	MetaData	tbMDConsequence	Text	Left	30
130	MetaData	tbMDExpectedBenefits	Text	Left	30
131	MetaData	tbMDProblemOpportunity	Text	Left	30
132	MetaData	tbMDConstraintsAssumptions	Text	Left	30
133	MetaData	tbMDCostBenefitAnalysis	Text	Left	30
134	MetaData	tbMDSeniorLevelCommittment	Text	Left	30
135	MetaData	tbMDObjectivesAndScope	Text	Left	30
136	MetaData	tbMDOptionsAnalysis	Text	Left	30
137	MetaData	tbMDImplementationApproach	Text	Left	30
138	MetaData	tbMDNextSteps	Text	Left	30
139	MetaData	tbMDVersion	Text	Left	30
140	MetaData	tbMDBCaseDateApproved	Text	Left	30
141	MetaData	tbMDStakeholderDescription	Text	Left	30
142	MetaData	tbMDWrittenBy	Text	Left	20
143	MetaData	tbMDPrerequisitesChecklist	Text	Left	30
144	MetaData	tbMDScheduleCommentary	Text	Left	30
145	MetaData	tbMDBudgetCommentary	Text	Left	30
146	MetaData	tbMDScopeCommentary	Text	Left	30
147	MetaData	tbMDResourceCommentary	Text	Left	30
148	MetaData	tbMDFinancialCommentary	Text	Left	30
149	MetaData	tbMDKeyDependencies	Text	Left	30
150	MetaData	tbMDValueProposition	Text	Left	30
151	MetaData	tbMDSuccessCriteria	Text	Left	30
152	MetaData	tbMDDecisionsRequired	Text	Left	30
153	MetaData	tbMDKeyRecommendations	Text	Left	30
154	MetaData	tbMDMarketAnalysis	Text	Left	30
155	MetaData	tbMDPortfolioImpactAnalysis	Text	Left	30
156	MetaData	tbMDKeyProjectMetrics	Text	Left	30
157	MetaData	tbMDWBS	Text	Left	20
158	MetaData	tbMDWeighting	Text	Left	20
159	MetaData	tbMDLocation	Text	Left	20
160	MetaData	tbMDResID	Text	Left	15
161	MetaData	tbMDPrimarySkill	Text	Left	20
162	MetaData	tbMDPrimaryRole	Text	Left	20
163	MetaData	tbMDResponsibility	Text	Left	20
164	MetaData	tbMDExtSystemID1	Text	Left	10
165	MetaData	tbMDSyncNotes	Text	Left	2
166	MetaData	tbMDStageApprover	Text	Left	2
167	MetaData	tbMDSprintName	Text	Left	2
168	MetaData	tbMDExtLink1	Text	Left	2
169	MetaData	tbMDOther3	Text	Left	2
170	MetaData	canvasNo	Text	Left	2
171	MetaData	tbMDRefID	Text	Left	10
172	MetaData	tbMDSortOrder	Text	Left	20
173	MetaData	tbMDtbLastModified	Text	Left	20
174	MetaData	tbMDShowIn	Text	Left	20
175	MetaData	tbMDCustomerID	Text	Left	10
176	MetaData	tbMDAzureID	Text	Left	10
177	MetaData	tbMDNameShort	Text	Left	20
178	MetaData	tbMDNotesWorkflow	Text	Left	2
179	MetaData	tbMDContractNumber	Text	Left	20
180	MetaData	tbMDPortfolio	Text	Left	20
181	MetaData	tbMDProgram	Text	Left	20
182	MetaData	tbMDProgActivityAlignment	Text	Left	20
183	MetaData	tbMDSeverity	Text	Left	20
184	MetaData	tbMDContingency	Text	Left	30
185	MetaData	tbMDMitigationPlan	Text	Left	30
186	MetaData	tbMDMitigationStatus	Text	Left	30
187	MetaData	tbMDProbability	Text	Left	30
188	MetaData	tbMDImpact	Text	Left	30
189	MetaData	tbMDRiskResponseStrategy	Text	Left	30
190	MetaData	tbMDContingencyPlan	Text	Left	30
191	MetaData	tbMDTriggerEvent	Text	Left	30
192	MetaData	tbMDEarlyWarningIndicators	Text	Left	30
193	MetaData	tbMDRiskCategory	Text	Left	31
194	MetaData	tbMDIssueCategory	Text	Left	32
195	MetaData	tbMDScore	Text	Left	18
196	Resources	tbResID	Text	Center	15
197	Resources	tbResResourceCalendar	Text	Center	10
198	Resources	tbResQuantity	Text	Center	10
199	Resources	tbResPayRate	Text	Center	10
200	Resources	tbResExtSystemResID	Text	Center	10
201	Resources	tbResName	Text	Left	40
202	Resources	tbResPrimaryRole	Text	Left	25
203	Resources	tbResPrimarySkill	Text	Left	25
204	Resources	tbResNameShort	Text	Left	20
205	Resources	tbResLabourType	Text	Left	18
206	Resources	tbResPercentGeneralAvailability	Text	Center	18
207	Resources	tbResEmail	Text	Left	30
208	Resources	tbResDepartment	Text	Left	25
209	Resources	tbResManager	Text	Left	25
210	Resources	tbResTeam	Text	Left	20
211	Resources	tbResLocation	Text	Left	20
212	Resources	tbResTeamLeader	Text	Left	20
213	Resources	tbResSupervisor	Text	Left	20
214	Resources	tbResPartTimeFullTime	Text	Left	20
215	Resources	tbResResourceType	Text	Left	20
216	Resources	tbResResourceClass	Text	Left	20
217	Resources	tbResCostCode	Text	Left	20
218	Resources	tbResCustomerID	Text	Left	10
219	Resources	tbResSortOrder	Text	Left	20
220	Resources	tbResLastModified	Text	Left	20
221	Resources	tbResPasswordHash	Text	Left	20
222	Resources	tbResPIN	Text	Left	20
223	Resources	tbResEmail2	Text	Left	20
224	Resources	tbResFirstName	Text	Left	20
225	Resources	tbResLastName	Text	Left	20
226	Resources	tbResMiddleName	Text	Left	10
227	Resources	tbResStreet	Text	Left	20
228	Resources	tbResCity	Text	Left	20
229	Resources	tbResStateProvince	Text	Left	20
230	Resources	tbResZipPostalCode	Text	Left	20
231	Resources	tbResPhoneNo	Text	Left	20
232	Resources	tbResPhoneNo2	Text	Left	20
233	Resources	tbResCellPhoneNo	Text	Left	20
234	Resources	tbResCountry	Text	Left	20
235	Resources	tbResCompany	Text	Left	20
236	Resources	tbResBirthday	Text	Left	20
237	Resources	tbResLanguage	Text	Left	20
238	Resources	tbResSocialLinks	Text	Left	20
239	Resources	tbResCourse	Text	Left	20
240	Resources	tbResCourseFinishDate	Text	Left	20
241	Resources	tbResPhoto	Text	Left	20
242	Resources	tbResPOBoxNo	Text	Left	20
243	Resources	tbResAptNo	Text	Left	20
244	Resources	tbResPostalStation	Text	Left	20
245	Resources	tbResOccupation	Text	Left	20
246	Resources	tbResSignature	Text	Left	20
247	Resources	tbResCertNo	Text	Left	20
248	Resources	tbResStatus	Text	Left	20
249	Resources	tbResState	Text	Left	20
250	Resources	tbResStage	Text	Left	20
251	Resources	tbResStep	Text	Left	20
252	Resources	tbResStepNotes	Text	Left	2
253	Resources	tbResOffice	Text	Left	20
254	Resources	tbResTransDate	Text	Left	20
255	Resources	tbResStartDate	Text	Left	20
256	Resources	tbResTermDate	Text	Left	20
257	Resources	tbResRemarks	Text	Left	20
258	MetaData	tbPASTeamSize	Text	Left	10
259	MetaData	tbPASStakeholderCount	Text	Left	10
260	MetaData	tbPASTechnologyNovelty	Text	Left	10
261	MetaData	tbPASProjectSimilarity	Text	Left	10
262	MetaData	tbPASDomainExperience	Text	Left	10
263	MetaData	tbPASExternalIntegrations	Text	Left	10
264	MetaData	tbPASVendorDependencies	Text	Left	10
265	MetaData	tbPASCrossTeamCollaboration	Text	Left	10
266	MetaData	tbPASRegulatoryApprovals	Text	Left	10
267	MetaData	tbPASMarketTiming	Text	Left	10
268	MetaData	tbPASProjectType	Text	Left	10
269	MetaData	tbPASOverallFeasibilityScore	Text	Left	10
270	MetaData	tbPASComplexityScore	Text	Left	10
271	MetaData	tbPASRiskScore	Text	Left	10
272	MetaData	tbPASScaleScore	Text	Left	10
273	MetaData	tbPASTechnologyScore	Text	Left	10
274	MetaData	tbPASFamiliarityScore	Text	Left	10
275	MetaData	tbPASDependencyScore	Text	Left	10
276	MetaData	tbPASRegulatoryScore	Text	Left	10
277	MetaData	tbPASMarketScore	Text	Left	10
278	MetaData	tbPASAssessmentVersion	Text	Left	10
279	MetaData	tbPASStatus	Text	Left	10
280	MetaData	tbPASApprovalRequired	Text	Left	10
281	MetaData	tbPASAssessmentDate	Text	Left	10
282	MetaData	tbPASAssessorName	Text	Left	10
283	MetaData	tbPASTeamTechExperience	Text	Left	10

## Bar Creator Sheet
tbID	tbSelfKey2	tbName	tbType	tbSubType	tbHierarchyOrder	tbCoordTop	kbCoordTop	kbCoordLeft	tbStart	tbFinish	tbAStart	tbAFinish	tbDuration	tbRemainingDuration	tbPredecessor	tbTaskParent	tbOwner	tbCost	tbACost	tbCostRemaining	tbWork	tbAWork	tbWorkRemaining	tbPercentComplete	tbCalendar	tbExpHoursPerWeek	tbPercentTimeOn	tbPayRate	tbResID	tbCostID	tbCostType	tbStatus	tbState	tbPriority	tbPhase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	tbFloat	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	tbBarHeight	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage
Timebars Data Store					Renumber Ids				Calc Finish
UID	Parent	Name	Type	SubType	Hierarchy Order	Coord Top	kbCoordTop	Lane	Start	Finish	Actual Start	Actual Finish	Duration	Rem Dur	tbPredecessor	tbTaskParent	Owner	Cost	Actual Cost	Cost Remaining	Work Hours	Actual Work Hours	Remaining Work Hours	Percent Complete	Calendar	Expected Hours Per Week	Percent Time Allocated	PayRate	tbResID	tbCostID	Cost Type	Status	State	Priority	Phase	tbL1	tbL2	tbL3	tbL4	tbL5	tbWbsDescription	tbConstraintType	tbConstraintDate	Float	tbFreeFloat	canvasNo	focdItemCoordLeft	focdItemCoordTop	tbBarColor	tbTextColor	Bar Height	tbBLID	tbCustomerID	tbSchEngOverride	tbT1	tbT2	tbStep	tbStepStatus	tbWfReasonNote	tbStage
2500	2100	LOV Service	Project		01.02.00.00.00	366			02-Oct-2023	16-Apr-2024			137	137			Stefan	0	0	0	0	0	0	0								Active	Spawned		Phase 1	OAG Replacement Project	LOV Service														30		44
2501	2101	Design:Docs Upload Service	Sub-Project		01.01.01.00.00	134	187	0	02-Oct-2023	04-Nov-2023			24	24				3843.7	0	3843.7	45.1	0	45.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: Death Notification Service						0	0	1					30		44
2502	2501	Interface Design – Docs Upload Service	Task		01.01.01.01.00	178	100	0	02-Oct-2023	14-Oct-2023			9	9				1265.6	0	1265.6	16.9	0	16.9	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	Interface Design -Docs Upload Service					0	0	1					30		44
2503	2502	SME Cloud	Allocation		01.01.01.01.01	208			02-Oct-2023	14-Oct-2023			9	9			SME Cloud Technologies	1265.6	0	1265.6	16.9	0	16.9	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2504	2501	MAR Design – Docs Upload Service	Task		01.01.01.02.00	178	100	0	16-Oct-2023	28-Oct-2023			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	MAR Design -Docs Upload Service					0	0	1					30		44
2505	2504	Dev SQL	Allocation		01.01.01.02.01	210			16-Oct-2023	28-Oct-2023			10	10			Developer SQL	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2506	2501	Testing Design – Docs Upload Service	Task		01.01.01.03.00	184	100	0	30-Oct-2023	04-Nov-2023			5	5				703.1	0	703.1	9.4	0	9.4	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design:Docs Upload Service	Testing Design -Docs Upload Service					0	0	1					30		44
2507	2506	Dev Web	Allocation		01.01.01.03.01	220			30-Oct-2023	04-Nov-2023			5	5			Developer Web	703.1	0	703.1	9.4	0	9.4	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2508	2101	Migration:Docs Upload Service	Sub-Project		01.01.02.00.00	140	194	0	06-Nov-2023	25-Nov-2023			15	15				3609.4	0	3609.4	43.1	0	43.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service						0	0	1					30		44
2509	2508	Interface Migration - Docs Upload Service	Task		01.01.02.01.00	184	100	0	06-Nov-2023	11-Nov-2023			5	5				984.4	0	984.4	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	Interface Migration -Docs Upload Service					0	0	1					30		44
2510	2509	SME Cloud	Allocation		01.01.02.01.01	214			06-Nov-2023	11-Nov-2023			4	4			SME Cloud Technologies	984.4	0	984.4	13.1	0	13.1	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2511	2508	Testing Migration -Docs Upload Service	Task		01.01.02.02.00	184	100	0	20-Nov-2023	25-Nov-2023			5	5				1125	0	1125	15	0	15	0					0			Active				OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	Testing Migration -Docs Upload Service					0	0	1					30		44
2512	2511	Dev Web	Allocation		01.01.02.02.01	214			20-Nov-2023	25-Nov-2023			4	4			Developer Web	1125	0	1125	15	0	15	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2513	2508	MAR Migration – Docs Upload Service	Task		01.01.02.03.00	186	100	0	13-Nov-2023	18-Nov-2023			5	5				1500	0	1500	15	0	15	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration:Docs Upload Service	MAR Migration -Docs Upload Service					0	0	1					30		44
2514	2513	Dev SQL	Allocation		01.01.02.03.01	216			13-Nov-2023	18-Nov-2023			4	4			Developer SQL	1500	0	1500	15	0	15	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2515	2101	Deployment:Docs Upload Service	Sub-Project		01.01.03.00.00	148	176	0	27-Nov-2023	09-Dec-2023			10	10				2343.9	0	2343.9	37.6	0	37.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Deployment:Docs Upload Service						0	0	1					30		44
2516	2515	LOB Interface Deployment - Docs Upload Service	Task		01.01.03.01.00	192	100	0	27-Nov-2023	02-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0				0	0			Active			Phase 1									0	0	1							44
2517	2516	Chris Java	Allocation		01.01.03.01.01	222			27-Nov-2023	02-Dec-2023			5	5			Chris Java	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	719		External	Active												0	0	1							44
2518	2515	Mar Deployment – Docs Upload Service	Task		01.01.03.02.00	192	100	0	04-Dec-2023	09-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0					0			Active												0	0	1					30		44
2519	2518	Dev ERP	Allocation		01.01.03.02.01	222			04-Dec-2023	09-Dec-2023			5	5			Developer ERP System	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	811		External	Active												0	0	1					30		44
2520	2515	Testing Deployment – Docs Upload Service	Task		01.01.03.03.00	258	100	0	27-Nov-2023	09-Dec-2023			10	10				1406.3	0	1406.3	18.8	0	18.8	0					0			Active												0	0	1					30		44
2521	2520	Dev Web	Allocation		01.01.03.03.01	288			27-Nov-2023	09-Dec-2023			10	10			Developer Web	1406.3	0	1406.3	18.8	0	18.8	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2522	2101	Implementation:Docs Upload Service	Sub-Project		01.01.04.00.00	164	176	0	11-Dec-2023	26-Dec-2023			10	10				1406.3	0	1406.3	20.6	0	20.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service						0	0	1					30		44
2523	2522	Interface Implementation - Docs Upload Service	Task		01.01.04.01.00	208	100	0	11-Dec-2023	19-Dec-2023			7	7				656.3	0	656.3	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	Interface Implementation - Docs Upload Service					0	0	1					30		44
2524	2523	Dev General	Allocation		01.01.04.01.01	238			11-Dec-2023	19-Dec-2023			7	7			Developer General	656.3	0	656.3	13.1	0	13.1	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2525	2522	MAR Implementation – Death Notification Service	Task		01.01.04.02.00	208	100	0	19-Dec-2023	25-Dec-2023			4	4				750	0	750	7.5	0	7.5	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	MAR Implementation -Death Notification Service					0	0	1							44
2526	2525	Dev SQL	Allocation		01.01.04.02.01	238			19-Dec-2023	25-Dec-2023			4	4			Developer SQL	750	0	750	7.5	0	7.5	0	7.5	1.875	25	100	810		External	Active												0	0	1							44
2527	2522	Testing Implementation - Docs Upload Service	Task		01.01.04.03.00	208	100	0	25-Dec-2023	26-Dec-2023			0	0				0	0	0	0	0	0	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation:Docs Upload Service	Testing Implementation - Docs Upload Service					0	0	1					30		44
2528	2527	Dev Web	Allocation		01.01.04.03.01	238			25-Dec-2023	26-Dec-2023			0	0			Developer Web	0	0	0	0	0	0	0	7.5	1.875	25	75	809		External	Active												0	0	1							44
2529	2101	Post-Deployment:Docs Upload Service	Sub-Project		01.01.05.00.00	174	184	0	27-Dec-2023	03-Feb-2024			27	27				4031.3	0	4031.3	50.7	0	50.7	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Post-Deployment:Docs Upload Service						0	0	1					30		44
2530	2529	Interface Post-Deployment - Docs Upload Service	Task		01.01.05.01.00	218	100	0	27-Dec-2023	10-Jan-2024			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1									0	0	1					30		44
2531	2530	SME SA	Allocation		01.01.05.01.01	248			27-Dec-2023	10-Jan-2024			10	10			SME Solution Architecture	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	807		External	Active												0	0	1					30		44
2532	2529	API Post Deployment Fixes - Docs Upload Service	Task		01.01.05.02.00	218	100	0	11-Jan-2024	25-Jan-2024			11	11				1031.3	0	1031.3	20.6	0	20.6	0					0			Active												0	0	1					30		44
2533	2532	Dev General	Allocation		01.01.05.02.01	248			11-Jan-2024	25-Jan-2024			11	11			Developer General	1031.3	0	1031.3	20.6	0	20.6	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2534	2529	Testing Post Deployment - Docs Upload Service	Task		01.01.05.03.00	218	100	0	26-Jan-2024	03-Feb-2024			6	6				1125	0	1125	11.3	0	11.3	0					0			Active												0	0	1					30		44
2535	2534	Tester EDC	Allocation		01.01.05.03.01	254			26-Jan-2024	03-Feb-2024			6	6			Tester Platforms and Datacenter	1125	0	1125	11.3	0	11.3	0	7.5	1.875	25	100	813		External	Active												0	0	1					30		44
2536	2100	Docs Upload Service	Project		01.03.00.00.00	454			02-Oct-2023	07-Apr-2024			130	130			Stefan	0	0	0	0	0	0	0								Active	Spawned		Phase 1	OAG Replacement Project	Docs Upload Service Docs														29.9826		44
2537	2101	Design: LOV Service	Sub-Project		01.01.01.00.00	134	187	0	02-Oct-2023	04-Nov-2023			24	24				3843.7	0	3843.7	45.1	0	45.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service						0	0	1					30		44
2538	2501	Interface Design - LOV Service	Task		01.01.01.01.00	178	100	0	02-Oct-2023	14-Oct-2023			9	9				1265.6	0	1265.6	16.9	0	16.9	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	Interface Design - LOV Service					0	0	1					30		44
2539	2502	SME Cloud	Allocation		01.01.01.01.01	208			02-Oct-2023	14-Oct-2023			9	9			SME Cloud Technologies	1265.6	0	1265.6	16.9	0	16.9	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2540	2501	MAR Design - LOV Service	Task		01.01.01.02.00	178	100	0	16-Oct-2023	28-Oct-2023			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	MAR Design - LOV Service					0	0	1					30		44
2541	2504	Dev SQL	Allocation		01.01.01.02.01	210			16-Oct-2023	28-Oct-2023			10	10			Developer SQL	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2542	2501	Testing Design - LOV Service	Task		01.01.01.03.00	184	100	0	30-Oct-2023	04-Nov-2023			5	5				703.1	0	703.1	9.4	0	9.4	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Design: LOV Service	Testing Design - LOV Service					0	0	1					30		44
2543	2506	Dev Web	Allocation		01.01.01.03.01	220			30-Oct-2023	04-Nov-2023			5	5			Developer Web	703.1	0	703.1	9.4	0	9.4	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2544	2101	Migration: LOV Service	Sub-Project		01.01.02.00.00	140	194	0	06-Nov-2023	25-Nov-2023			15	15				3609.4	0	3609.4	43.1	0	43.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service						0	0	1					30		44
2545	2508	Interface Migration - LOV Service	Task		01.01.02.01.00	184	100	0	06-Nov-2023	11-Nov-2023			5	5				984.4	0	984.4	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service	Interface Migration - LOV Service					0	0	1					30		44
2546	2509	SME Cloud	Allocation		01.01.02.01.01	214			06-Nov-2023	11-Nov-2023			4	4			SME Cloud Technologies	984.4	0	984.4	13.1	0	13.1	0	7.5	1.875	25	75	806		External	Active												0	0	1					30		44
2547	2508	Testing Migration - LOV Service	Task		01.01.02.02.00	184	100	0	20-Nov-2023	25-Nov-2023			5	5				1125	0	1125	15	0	15	0					0			Active				OAG Replacement Project	Death Notification Service	Migration: LOV Service	Testing Migration - LOV Service					0	0	1					30		44
2548	2511	Dev Web	Allocation		01.01.02.02.01	214			20-Nov-2023	25-Nov-2023			4	4			Developer Web	1125	0	1125	15	0	15	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2549	2508	MAR Migration - LOV Service	Task		01.01.02.03.00	186	100	0	13-Nov-2023	18-Nov-2023			5	5				1500	0	1500	15	0	15	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Migration: LOV Service	MAR Migration - LOV Service					0	0	1					30		44
2550	2513	Dev SQL	Allocation		01.01.02.03.01	216			13-Nov-2023	18-Nov-2023			4	4			Developer SQL	1500	0	1500	15	0	15	0	7.5	1.875	25	100	810		External	Active												0	0	1					30		44
2551	2101	Deployment: LOV Service	Sub-Project		01.01.03.00.00	148	176	0	27-Nov-2023	09-Dec-2023			10	10				2343.9	0	2343.9	37.6	0	37.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Deployment: LOV Service						0	0	1					30		44
2552	2515	LOB Interface Deployment - LOV Service	Task		01.01.03.01.00	192	100	0	27-Nov-2023	02-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0				0	0			Active			Phase 1									0	0	1							44
2553	2516	Chris Java	Allocation		01.01.03.01.01	222			27-Nov-2023	02-Dec-2023			5	5			Chris Java	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	719		External	Active												0	0	1							44
2554	2515	Mar Deployment - LOV Service	Task		01.01.03.02.00	192	100	0	04-Dec-2023	09-Dec-2023			5	5				468.8	0	468.8	9.4	0	9.4	0					0			Active												0	0	1					30		44
2555	2518	Dev ERP	Allocation		01.01.03.02.01	222			04-Dec-2023	09-Dec-2023			5	5			Developer ERP System	468.8	0	468.8	9.4	0	9.4	0	7.5	1.875	25	50	811		External	Active												0	0	1					30		44
2556	2515	Testing Deployment - LOV Service	Task		01.01.03.03.00	258	100	0	27-Nov-2023	09-Dec-2023			10	10				1406.3	0	1406.3	18.8	0	18.8	0					0			Active												0	0	1					30		44
2557	2520	Dev Web	Allocation		01.01.03.03.01	288			27-Nov-2023	09-Dec-2023			10	10			Developer Web	1406.3	0	1406.3	18.8	0	18.8	0	7.5	1.875	25	75	809		External	Active												0	0	1					30		44
2558	2101	Implementation: LOV Service	Sub-Project		01.01.04.00.00	164	176	0	11-Dec-2023	26-Dec-2023			10	10				1406.3	0	1406.3	20.6	0	20.6	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service						0	0	1					30		44
2559	2522	Interface Implementation - LOV Service	Task		01.01.04.01.00	208	100	0	11-Dec-2023	19-Dec-2023			7	7				656.3	0	656.3	13.1	0	13.1	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	Interface Implementation - LOV Service					0	0	1					30		44
2560	2523	Dev General	Allocation		01.01.04.01.01	238			11-Dec-2023	19-Dec-2023			7	7			Developer General	656.3	0	656.3	13.1	0	13.1	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2561	2522	MAR Implementation - LOV Service	Task		01.01.04.02.00	208	100	0	19-Dec-2023	25-Dec-2023			4	4				750	0	750	7.5	0	7.5	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	MAR Implementation -Death Notification Service					0	0	1							44
2562	2525	Dev SQL	Allocation		01.01.04.02.01	238			19-Dec-2023	25-Dec-2023			4	4			Developer SQL	750	0	750	7.5	0	7.5	0	7.5	1.875	25	100	810		External	Active												0	0	1							44
2563	2522	Testing Implementation - LOV Service	Task		01.01.04.03.00	208	100	0	25-Dec-2023	26-Dec-2023			0	0				0	0	0	0	0	0	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Implementation: LOV Service	Testing Implementation - LOV Service					0	0	1					30		44
2564	2527	Dev Web	Allocation		01.01.04.03.01	238			25-Dec-2023	26-Dec-2023			0	0			Developer Web	0	0	0	0	0	0	0	7.5	1.875	25	75	809		External	Active												0	0	1							44
2565	2101	Post-Deployment: LOV Service	Sub-Project		01.01.05.00.00	174	184	0	27-Dec-2023	03-Feb-2024			27	27				4031.3	0	4031.3	50.7	0	50.7	0				0	0			Active			Phase 1	OAG Replacement Project	Death Notification Service	Post-Deployment: LOV Service						0	0	1					30		44
2566	2529	Interface Post-Deployment - LOV Service	Task		01.01.05.01.00	218	100	0	27-Dec-2023	10-Jan-2024			10	10				1875	0	1875	18.8	0	18.8	0				0	0			Active			Phase 1									0	0	1					30		44
2567	2530	SME SA	Allocation		01.01.05.01.01	248			27-Dec-2023	10-Jan-2024			10	10			SME Solution Architecture	1875	0	1875	18.8	0	18.8	0	7.5	1.875	25	100	807		External	Active												0	0	1					30		44
2568	2529	API Post Deployment Fixes - LOV Service	Task		01.01.05.02.00	218	100	0	11-Jan-2024	25-Jan-2024			11	11				1031.3	0	1031.3	20.6	0	20.6	0					0			Active												0	0	1					30		44
2569	2532	Dev General	Allocation		01.01.05.02.01	248			11-Jan-2024	25-Jan-2024			11	11			Developer General	1031.3	0	1031.3	20.6	0	20.6	0	7.5	1.875	25	50	808		External	Active												0	0	1					30		44
2570	2529	Testing Post Deployment - LOV Service	Task		01.01.05.03.00	218	100	0	26-Jan-2024	03-Feb-2024			6	6				1125	0	1125	11.3	0	11.3	0					0			Active												0	0	1					30		44
2571	2534	Tester EDC	Allocation		01.01.05.03.01	254			26-Jan-2024	03-Feb-2024			6	6			Tester Platforms and Datacenter	1125	0	1125	11.3	0	11.3	0	7.5	1.875	25	100	813		External	Active												0	0	1					30		44

2137	2100	Biometrics Info Sharing POC	Project		01.04.00.00.00	546	159	0	04-Apr-2024	17-Sep-2024			115	115				0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics Info Sharing POC							0	0	1							44
2138	2100	Biometrics – data sharing Phase 2	Project		01.05.00.00.00	620	195	0	04-Jun-2024	19-Nov-2024			117	117			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics – data sharing Phase 2							0	0	1							44
2139	2100	Is Employee Validation	Project		01.06.00.00.00	688	191	0	25-Jul-2024	09-Jan-2025			117	117			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Is Employee Validation							0	0	1							44
2140	2100	Legacy Biographic daata sharing	Project		01.07.00.00.00	756	196	0	03-Oct-2024	20-Mar-2025			119	119				0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Legacy Biographic daata sharing							0	0	1							44
2141	2100	Biometrics - Infosharing Phase 1	Project		01.08.00.00.00	836	182	0	07-Nov-2024	24-Apr-2025			120	120			Carmai	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Biometrics - Infosharing Phase 1							0	0	1							44
2142	2100	Birth Certification Validation	Project		01.09.00.00.00	898	154	0	16-Dec-2024	02-Jun-2025			120	120			Michael	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Birth Certification Validation							0	0	1							44
2143	2100	Facial Recognition FRS	Project		01.10.00.00.00	960	186	0	06-Feb-2025	24-Jul-2025			121	121			Yves	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Facial Recognition FRS							0	0	1							44
2144	2100	Portfolio Project Compliance	Project		01.11.00.00.00	1064	157	0	07-Apr-2025	20-Sep-2025			120	120			Yves	0	0	0	0	0	0	0				0	0			Active				OAG Replacement Project	Portfolio Project Compliance							0	0	1							44
Import Data
Format

## Field Formats
Field Formats					Current Form Names : PF1, PF2, PJ1, PJ2, PJ3, SPJ1, Task1, Task2, ALLOC1, DOC1, DOC1, other1, other2, tbform
ID	MD Sheet	DataType	ID	TBCore Sht	DataType
0	tbMDID	text	0	tbID	text			Dynamic Field Helper
1	tbMDName	text	1	tbSelfKey2	text			Preconfigured FOCD Form Fields. Instructions: Copy and paste into Fields Sheet to suit.
2	tbMDProjectType	text	2	tbCoordTop	number			UID	Coord Top	Coord Left	Width	Name	Type	Title	Form Name	Label	Picklist	Show In Form	Store Name	not used	not used	not used	not used
3	tbMDPortfolio	text	3	tbCoordLeft	number			1	130	10	350	tbMDID	NoPicklist	Item ID		UID		Yes	tbMetaData
4	tbMDProgram	text	4	tbHierarchyOrder	number			2	200	10		tbMDName	NoPicklist	Please enter name or title		Portfolio Title		Yes	tbMetaData
5	tbMDExecutiveSummary	text	5	tbName	text			3	270	10		tbMDProjectType	WithPicklist	Is this a Program, Project or Sub-project?		Project Type	Project Type	Yes	tbMetaData
6	tbMDGate	date	6	tbType	text			4	340	10		tbMDPortfolio	WithPicklist	Please enter the name of the Portfolio this belongs to		Investment Portfolio	Portfolios	Yes	tbMetaData
7	tbMDDeliveryManager	text	7	tbL1	text			5	410	10		tbMDProgram	WithPicklist	Enter Program name if applicable		Program	Programs	No	tbMetaData
8	tbMDBusinessAdvisor	text	8	tbL2	text			6	480	10		tbMDExecutiveSummary	NoPicklist	Please enter summary status of the initiative		Executive Summary			tbMetaData
9	tbMDBusinessOwner	text	9	tbL3	text			7	130	10	350	tbMDID	NoPicklist	Item ID		UID2		Yes	tbMetaData
10	tbMDEstimationClass	text	10	tbL4	text			8	200	10	350	tbMDName	NoPicklist	Please enter name or title		Portfolio Title2		Yes	tbMetaData
11	tbMDROMEstimate	text	11	tbL5	text			9	270	10	350	tbMDProjectType	WithPicklist	Is this a Program, Project or Sub-project?		Project Type2	Project Type	Yes	tbMetaData
12	tbMDInvestmentCategory	text	12	tbOwner	text			10	340	10	350	tbMDPortfolio	WithPicklist	Please enter the name of the Portfolio this belongs to		Investment Portfolio2	Portfolios	Yes	tbMetaData
13	tbMDInvestmentInitiative	text	13	tbStart	text			11	410	10	350	tbMDProgram	WithPicklist	Enter Program name if applicable		Program2	Programs	No	tbTimebars
14	tbMDInvestmentObjective	text	14	tbFinish	date			13	970	10	350	tbMDInvestmentCategory	WithPicklist			Investment Category	Investment Category		tbMetaData
15	tbMDInvestmentStrategy	text	15	tbDuration	text			14	1040	10	350	tbMDInvestmentInitiative	WithPicklist			Investment Initiative	Investment Initiative		tbMetaData
16	tbMDPriorityStrategic	text	16	tbAStart	text			15	1110	10	350	tbMDInvestmentObjective	WithPicklist			Investment Objective	Investment Objective		tbMetaData
17	tbMDCustomerID	text	17	tbAFinish	text			16	850	10	350	tbMDInvestmentStrategy	WithPicklist			Investment Strategy	Investment Strategy		tbMetaData
18	tbMDAzureID	text	18	tbRemainingDuration	number			17	900	10	350	tbMDPriorityStrategic	WithPicklist			Primary Strategic Priority	Primary Strategic Priority		tbMetaData
19	tbMDNameShort	text	19	tbResID	text			18	950	10	350	tbMDCustomerID	NoPicklist					tbMetaData
20	tbMDProjectNumber	text	20	tbCalendar	number			19	1000	10	350	tbMDAzureID	NoPicklist					tbMetaData
21	tbMDDescription	text	21	tbPercentTimeOn	number			20	1050	10	350	tbMDNameShort	NoPicklist					tbMetaData
22	tbMDNotes	text	22	tbWork	number			21	1100	10	350	tbMDProjectNumber	NoPicklist			Project Number			tbMetaData
23	tbMDExtLink1	text	23	tbAWork	number			22	440	10	350	tbMDDescription	NoPicklist	Please enter just few lines not a thesis		Brief Description		Yes	tbMetaData
24	tbMDExtSystemID1	text	24	tbWorkRemaining	number			23	520	10	350	tbMDNotes	Editor			General Notes		Yes	tbMetaData
25	tbMDSortOrder	number	25	tbPercentComplete	number			24	1250	10	350	tbMDExtLink1	NoPicklist					tbMetaData
26	tbMDtbLastModified	date	26	tbCost	number			25	1300	10	350	tbMDExtSystemID1	NoPicklist					tbMetaData
27	tbMDPriority	text	27	tbAcost	number			26	1350	10	350	tbMDSortOrder	NoPicklist					tbMetaData
28	tbMDStatus	text	28	tbCostRemaining	number			27	1050	10	350	tbMDtbLastModified	NoPicklist					tbMetaData
29	tbMDState	text	29	tbPayRate	number			28	1090	10	350	tbMDPriority	WithPicklist			Priority	Priority		tbMetaData
30	tbMDSeverity	text	30	tbCostType	text			29	1130	10	350	tbMDStatus	WithPicklist			Status	Project Status		tbMetaData
31	tbMDStage	text	31	tbCostID	text			30	1170	10	350	tbMDState	WithPicklist			State	State		tbMetaData
32	tbMDPhase	text	32	tbConstraintType	text			31	1210	10	350	tbMDSeverity	NoPicklist					tbMetaData
33	tbMDCategory	text	33	tbConstraintDate	date			32	1250	10	350	tbMDStage	WithPicklist			Stage	Stage		tbMetaData
34	tbMDHealth	text	34	tbFloat	number			33	1290	10	350	tbMDPhase	WithPicklist			Phase	Phase		tbMetaData
35	tbMDResponsibility	text	35	tbFreeFloat	number			34	1330	10	350	tbMDCategory	WithPicklist			Category	Category		tbMetaData
36	tbMDDepartment	text	36	tbExpHoursPerWeek	number			35	1370	10	350	tbMDHealth	WithPicklist					tbMetaData
37	tbMDExSponsor	text	37	canvasNo	number			36	1410	10	350	tbMDResponsibility	WithPicklist			Responsibility	Responsibility		tbMetaData
38	tbMDPM	text	38	tbCustomerID	text			37	1450	10	350	tbMDDepartment	WithPicklist			Department	Deparment		tbMetaData
39	tbMDShowIn	text	39	tbMetaDataID	text			38	1490	10	350	tbMDExSponsor	WithPicklist			Exec Sponsor			tbMetaData
40	tbMDYesNoSelector	text	40	tbBLID	text			39	1530	10	350	tbMDPM	WithPicklist			PM			tbMetaData
41	tbMDProduct	text	41	tbPredecessor	text			40	1570	10	350	tbMDShowIn	WithPicklist					tbMetaData
42	tbMDContact	text	42	tbAzureID	text			41	1610	10	350	tbMDYesNoSelector	WithPicklist					tbMetaData
43	tbMDWBS	text	43	tbCoordRight	text			42	1650	10	350	tbMDProduct	WithPicklist			Product	Product		tbMetaData
44	tbMDWeighting	number	44	tbBarColor	text			43	1690	10	350	tbMDContact	WithPicklist			Product Contact			tbMetaData
45	tbMDLocation	text	45	tbTextColor	text			44	1730	10	350	tbMDWBS	WithPicklist			WBS	WBS		tbMetaData
46	tbMDPrimarySkill	text	46	kbCoordLeft	number			45	1770	10	350	tbMDWeighting	WithPicklist					tbMetaData
47	tbMDPrimaryRole	text	47	kbCoordTop	number			46	1810	10	350	tbMDLocation	WithPicklist					tbMetaData
48	tbMDOther2	text	48	focdItemCoordLeft	number			47	1850	10	350	tbMDPrimarySkill	WithPicklist					tbMetaData
49	tbMDOther3	text	49	focdItemCoordTop	number			48	1890	10	350	tbMDPrimaryRole	WithPicklist					tbMetaData
50	tbMDOther4	text	50	tbCountry	text			49	1930	10	350	tbMDOther2	NoPicklist					tbMetaData
51	canvasNo	number	51	tbCompany	text			50	1970	10	350	tbMDOther3	NoPicklist					tbMetaData
52	tbMDProgActivityAlignment	text	52	tbLanguage	text			51	2010	10	350	tbMDOther4	NoPicklist					tbMetaData
53	tbMDBackgroundInfo	text	53	tbPriority	text			52	2050	10	350	canvasNo	NoPicklist					tbMetaData
54	tbMDConsequence	text	54	tbStatus	text			53	2090	10	350	tbMDProgActivityAlignment	WithPicklist					tbMetaData
55	tbMDExpectedBenfits	text	55	tbStep	text			54	2130	10	350	tbMDBackgroundInfo	Editor			Backround Info			tbMetaData
56	tbMDProblemOpportunity	text	56	tbStepStatus	text			55	2170	10	350	tbMDConsequence	Editor			Consequences of Inaction			tbMetaData
57	tbMDCapabilitiesNeeded	text	57	tbState	text			56	2210	10	350	tbMDExpectedBenefits	Editor			Expected Benefits			tbMetaData
58	tbMDSeniorLevelCommittment	text	58	tbWfReasonNote	text			57	2250	10	350	tbMDProblemOpportunity	Editor			Problem Opportunity			tbMetaData
59	tbMDSprintName	text	59	tbStage	text			58	2290	10	350	tbMDCapabilitiesNeeded	Editor			Capabilities Needed			tbMetaData
60	tbMDStakeholderDescription	text	60	tbPhase	text			59	2330	10	350	tbMDSeniorLevelCommittment	Editor					tbMetaData
61	tbMDHealthCost	text	61	tbPine	number			60	2370	10	350	tbMDSprintName	NoPicklist					tbMetaData
62	tbMDHealthHours	text	62	tbBalsam	number			61	2410	10	350	tbMDStakeholderDescription	NoPicklist			Stakeholder Description			tbMetaData
63	tbMDHealthIssues	text	63	tbFir	number			62	2450	10	350	tbMDHealthCost	WithPicklist			Health Cost	Health Indicators		tbMetaData
64	tbMDHealthOverall	text	64	tbSpruce	number			63	2490	10	350	tbMDHealthHours	NoPicklist					tbMetaData
65	tbMDHealthRisk	text	65	tbArea	number			64	2530	10	350	tbMDHealthIssues	WithPicklist			Health Issues	Health Indicators		tbMetaData
66	tbMDHealthSchedule	text	66	tbSize	number			65	2570	10	350	tbMDHealthOverall	WithPicklist			Health Overall	Health Indicators		tbMetaData
67	tbMDHealthScope	text	67	tbPercent2	number			66	2610	10	350	tbMDHealthRisk	WithPicklist			Health Risk	Health Indicators		tbMetaData
68	tbMDBenefitCostRatio	number	68	tbVolume	number			67	2650	10	350	tbMDHealthSchedule	WithPicklist			Health Schedule	Health Indicators		tbMetaData
69	tbMDConstraintsAssumptions	text	69	tbT1	text			68	2690	10	350	tbMDHealthScope	WithPicklist			Health Scope	Health Indicators		tbMetaData
70	tbMDContractNumber	text	70	tbT2	text			69	2730	10	350	tbMDBenefitCostRatio	NoPicklist			Benefit/Cost Ratio			tbMetaData
71	tbMDCostBenefitAnalysis	text	71	tbT3	text			70	2770	10	350	tbMDConstraintsAssumptions	Editor			Constraints And Assumptions			tbMetaData
72	tbMDEcnomicValueAdded	number	72	tbT4	text			71	2810	10	350	tbMDContractNumber	NoPicklist			Contract Number			tbMetaData
73	tbMDInternalRateOfReturn	number	73	tbT5	text			72	2850	10	350	tbMDCostBenefitAnalysis	Editor					tbMetaData
74	tbMDNetPresentValue	number	74	tbTaskParent	text			73	2890	10	350	tbMDEcnomicValueAdded	NoPicklist			Ecnomic Value Added			tbMetaData
75	tbMDOpportunityCost	number					74	2930	10	350	tbMDInternalRateOfReturn	NoPicklist			Internal Rate Of Return			tbMetaData
76	tbMDOrgManager	text					75	2970	10	350	tbMDNetPresentValue	NoPicklist			Return			tbMetaData
77	tbMDPaybackPeriod	number					76	3010	10	350	tbMDOpportunityCost	NoPicklist			Opportunity Cost			tbMetaData
78	tbMDRiskVsSizeAndComplexity	text					77	3050	10	350	tbMDOrgManager	WithPicklist			Org Manager			tbMetaData
79	tbMDSize	text					78	3090	10	350	tbMDPaybackPeriod	NoPicklist			Payback Period			tbMetaData
80	tbMDStageApprover	text					79	3130	10	350	tbMDRiskVsSizeAndComplexity	WithPicklist			Risk Vs Size And Complexity	Risk Vs Size		tbMetaData
81	tbMDSunkCosts	number					80	3170	10	350	tbMDSize	WithPicklist			Size	Size		tbMetaData
82	tbMDWrittenBy	text					81	3210	10	350	tbMDStageApprover	WithPicklist			Stage Approver			tbMetaData
83	tbMDPrimaryLineOfBusiness	text					82	3250	10	350	tbMDSunkCosts	NoPicklist			Sunk Costs			tbMetaData
84	tbMDNotesWorkflow	text					83	3290	10	350	tbMDWrittenBy	NoPicklist					tbMetaData
85	tbMDSyncNotes	text					84	3330	10	350	tbMDPrimaryLineOfBusiness	WithPicklist			Primary Line Of Business	Primary Line Of Business		tbMetaData
86	tbMDSponsoringDepartment	text					85	550	10	350	tbMDNotesWorkflow	WithPicklist			Workflow Notes		No	tbMetaData
87	tbMDPrimaryContact	text					86	3410	10	350	tbMDSyncNotes	NoPicklist					tbMetaData
88	tbMDContactNumber	text					87	3450	10	350	tbMDSponsoringDepartment	WithPicklist			Sponsoring Department	Sponsoring Department		tbMetaData
89	tbMDResponsibleTeam	text					88	3490	10	350	tbMDPrimaryContact	WithPicklist			Primary Contact			tbMetaData
90	tbMDNotesProject	text					89	3530	10	350	tbMDContactNumber	NoPicklist	Enter numbers or text or both		Contact Info			tbMetaData
91	tbMDOther5	text					90	3570	10	350	tbMDResponsibleTeam	WithPicklist			Responsible Team	Resonsible Teams		tbMetaData
92	tbMDOther6	text					91	3610	10	350	tbMDNotesProject	NoPicklist					tbMetaData
93	tbMDOther7	text					92	3650	10	350	tbMDOther5	NoPicklist					tbMetaData
94	tbMDOther8	text					93	3690	10	350	tbMDOther6	NoPicklist					tbMetaData
95	tbMDOther9	text					94	3730	10	350	tbMDOther7	NoPicklist					tbMetaData
96	tbMDOther10	text					95	3770	10	350	tbMDOther8	NoPicklist					tbMetaData
97	tbMDOther11	text					96	3810	10	350	tbMDOther9	NoPicklist					tbMetaData
98	tbMDOther12	text					97	3850	10	350	tbMDOther10	NoPicklist					tbMetaData
99	tbMDRefID	text					98	3890	10	350	tbMDOther11	NoPicklist					tbMetaData
				99	3930	10	350	tbMDOther12	NoPicklist					tbMetaData
				100	3970	10	350	tbMDRefID	NoPicklist					tbMetaData
				101	100	10	350		Band			Business Case		Yes	tbMetaData
				102	530	10	350	tbName	NoPicklist	Name of Timebar		Timebar Name		Yes	tbTimebars
				103	570	10	350	tbType	NoPicklist	Type of Timebar (Pf, Project Etc)		Type		Yes	tbTimebars
				104	620	10	350	tbL1	WithPicklist	Level 1, Portfolio		Portfolio Name	Portfolios	Yes	tbTimebars
				105	700	10	350	tbL2	NoPicklist	Level 2, Project or Program		L2 Description		Yes	tbTimebars

## Log
2024-12-30 14:19:46	The CSV Imported Successfully to AdminPanel
2024-12-30 14:19:55	The CSV Imported Successfully to Timebars
2024-12-30 14:21:29	The CSV Imported Successfully to MetaData
2024-12-30 14:22:27	The CSV Imported Successfully to MetaData
2024-12-30 15:38:00	The CSV Imported Successfully to Timebars
2024-12-30 15:38:08	The CSV Imported Successfully to MetaData
2024-12-30 15:38:32	Merge Operation Started!
2024-12-30 15:38:32	Double Title Found in 'MetaData'!
2024-12-30 15:38:32	Double Title Found in 'MetaData'!
2024-12-30 15:38:32	The record with UID 'A008' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 100.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 100.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A008' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID 'A013' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 88.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 4, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 59, Decision: Consider Terminating | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Improve our core products): 90.00,Project Score: 88.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 4, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 59, Decision: Consider Terminating |'
2024-12-30 15:38:32	The record with UID 'A013' updated from 'Timebars'! Details: Field['Cost'] :: '26484.4' ----> '552000'
2024-12-30 15:38:32	The record with UID 'A012' updated from 'MetaData'! Details: Field['Description'] :: 'Enabling an employee experience that is simple, relevant and caring.' ----> 'The <strong>Digital Desktop Transformation</strong> project is closely aligned, emphasizing the modernization of employee workstations through digital tools, cloud integration, and streamlined user interfaces. This initiative is designed to enhance productivity, collaboration, and user experience by providing a cohesive and efficient digital workspace.'
2024-12-30 15:38:32	The record with UID 'A026' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 68.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 0, Work Avg Score: 100,Final Score: 75, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 68.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 0, Work Avg Score: 100,Final Score: 75, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A026' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:32	The record with UID 'A011' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'This is my Brief Description' ----> 'The <strong>Core Operations Program</strong> is a strategic initiative designed to enhance the efficiency, reliability, and scalability of our organization’s core operations. This program focuses on optimizing workflows, integrating advanced technologies, and standardizing processes across departments to support the growing demands of our business. By addressing operational bottlenecks and improving resource utilization, the program aims to drive sustained performance improvements and reduce operational risks.'
2024-12-30 15:38:32	The record with UID 'A011' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:32	The record with UID 'A009' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'A strategic initiative to ensure Northern Wireless Inc. has integrated access to Company Information that is fit for purpose and is supported by the appropriate Governance.' ----> 'The <strong>Continuous Improvement Transformation</strong> and <strong>Digital Desktop Transformation</strong> projects are interrelated initiatives aimed at driving operational excellence and employee productivity. Continuous Improvement lays the foundation by streamlining workflows and promoting agility, while Digital Desktop Transformation equips employees with modern tools and a seamless digital workspace to execute these enhanced processes effectively. Together, these projects create a synergy that empowers the workforce, optimizes resource utilization, and positions the organization for sustained innovation and growth.'
2024-12-30 15:38:32	The record with UID 'A007' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'Upgrade the collaboration sites in conjunction with business owners.' ----> 'The <strong>Business Continuity Management</strong> project is a strategic initiative to safeguard the organization against operational disruptions. By creating a robust framework that includes risk analysis, contingency plans, and recovery strategies, this project ensures the company’s ability to continue delivering critical services during crises. This proactive approach not only mitigates risks but also enhances stakeholder trust, operational stability, and long-term resilience, ensuring the company is prepared for any eventuality.'
2024-12-30 15:38:32	The record with UID 'A007' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '0'
2024-12-30 15:38:32	The record with UID 'A010' updated from 'MetaData'! Details: Field['Executive Summary'] :: 'This program shall roll up all investments regarding our buildings and office space.' ----> 'The <strong>Constant Internal Delivery Enablement</strong> project is designed to streamline the execution of internal initiatives by building a robust framework for delivery excellence. By standardizing processes, optimizing resource utilization, and adopting proven methodologies, this project will ensure timely and high-quality outcomes for internal projects. This initiative not only improves operational efficiency but also fosters a culture of continuous improvement, enabling the organization to respond quickly and effectively to internal needs and strategic objectives.'
2024-12-30 15:38:32	The record with UID 'A017' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 58.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 93, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 58.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 93, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A017' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A020' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 65.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 65.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A020' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A023' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 87.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Attract and retain the best people): 100.00,Project Score: 87.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A023' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:32	The record with UID 'A024' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 69.38DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 70, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Improve our core products): 90.00,Project Score: 69.38DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 70, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A024' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:32	The record with UID 'A018' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A027' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 77.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Accelerate Time-to-Market): 70.00,Project Score: 77.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A027' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '340000'
2024-12-30 15:38:32	The record with UID 'A033' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 62.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 62.50DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 100, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A033' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:32	The record with UID 'A019' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A019' updated from 'Timebars'! Details: Field['Cost'] :: '49937.6' ----> '0'
2024-12-30 15:38:32	The record with UID 'A036' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A021' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 38.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 38.13DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 85, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A022' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 46.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 50, Work Avg Score: 0,Final Score: 55, Decision: Consider Terminating | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Innovation): 40.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 46.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 0,Cost Avg Score: 50, Work Avg Score: 0,Final Score: 55, Decision: Consider Terminating |'
2024-12-30 15:38:32	The record with UID 'A031' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |'
2024-12-30 15:38:32	The record with UID 'A029' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A030' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue | ' ----> 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue |'
2024-12-30 15:38:32	The record with UID 'A002' updated from 'Timebars'! Details: Field['Cost'] :: '352875' ----> '5548000'
2024-12-30 15:38:32	The record with UID '16114' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID '16156' updated from 'Timebars'! Details: Field['Cost'] :: '28312.5' ----> '604000'
2024-12-30 15:38:32	The record with UID '16115' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.02.01.00.00' ----> '02.03.01.00.00'
2024-12-30 15:38:32	The record with UID '16157' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.02.01.01.00' ----> '02.03.01.01.00'
2024-12-30 15:38:32	The record with UID '16157' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '382500'
2024-12-30 15:38:32	The record with UID '16117' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.03.01.00.00' ----> '01.02.01.00.00'
2024-12-30 15:38:32	The record with UID '16117' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:32	The record with UID '16159' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.03.01.01.00' ----> '01.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16159' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '608000'
2024-12-30 15:38:33	The record with UID '16118' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.04.01.00.00' ----> '02.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16160' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.04.01.01.00' ----> '02.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16160' updated from 'Timebars'! Details: Field['Cost'] :: '48750' ----> '375000'
2024-12-30 15:38:33	The record with UID '16126' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.05.01.00.00' ----> '01.03.01.00.00'
2024-12-30 15:38:33	The record with UID '16126' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:33	The record with UID '16168' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.05.01.01.00' ----> '01.03.01.01.00'
2024-12-30 15:38:33	The record with UID '16168' updated from 'Timebars'! Details: Field['Cost'] :: '9937.5' ----> '220000'
2024-12-30 15:38:33	The record with UID '16127' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.06.01.00.00' ----> '01.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16127' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:33	The record with UID '16169' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.06.01.01.00' ----> '01.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16169' updated from 'Timebars'! Details: Field['Cost'] :: '11812.5' ----> '248000'
2024-12-30 15:38:33	The record with UID '16128' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.07.01.00.00' ----> '01.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16128' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:33	The record with UID '16170' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.07.01.01.00' ----> '01.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16170' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '532000'
2024-12-30 15:38:33	The record with UID '16133' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.08.01.00.00' ----> '01.06.01.00.00'
2024-12-30 15:38:33	The record with UID '16133' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:33	The record with UID '16175' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.08.01.01.00' ----> '01.06.01.01.00'
2024-12-30 15:38:33	The record with UID '16175' updated from 'Timebars'! Details: Field['Cost'] :: '21562.5' ----> '468000'
2024-12-30 15:38:33	The record with UID 'TT-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.00.00.00' ----> '03.02.00.00.00'
2024-12-30 15:38:33	The record with UID '16135' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.01.00.00' ----> '02.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16177' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.01.01.00' ----> '02.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16177' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '318750'
2024-12-30 15:38:33	The record with UID 'BS-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.09.00.00.00' ----> '02.05.00.00.00'
2024-12-30 15:38:33	The record with UID '16137' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.01.00.00' ----> '01.07.01.00.00'
2024-12-30 15:38:33	The record with UID '16137' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID '16179' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.01.01.00' ----> '01.07.01.01.00'
2024-12-30 15:38:33	The record with UID '16179' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID 'TT-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.00.00.00' ----> '03.03.00.00.00'
2024-12-30 15:38:33	The record with UID '16148' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.01.00.00' ----> '03.01.01.00.00'
2024-12-30 15:38:33	The record with UID '16190' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.01.01.00' ----> '03.01.01.01.00'
2024-12-30 15:38:33	The record with UID '16190' updated from 'Timebars'! Details: Field['Cost'] :: '22500' ----> '450000'
2024-12-30 15:38:33	The record with UID 'BS-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.10.00.00.00' ----> '01.07.00.00.00'
2024-12-30 15:38:33	The record with UID 'BS-2024-003' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '232000'
2024-12-30 15:38:33	The record with UID '16152' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.01.00.00' ----> '03.02.01.00.00'
2024-12-30 15:38:33	The record with UID '16194' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.12.01.01.00' ----> '03.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16194' updated from 'Timebars'! Details: Field['Cost'] :: '20437.5' ----> '412500'
2024-12-30 15:38:33	The record with UID 'TT-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.00.00.00' ----> '03.04.00.00.00'
2024-12-30 15:38:33	The record with UID '16153' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.01.00.00' ----> '03.03.01.00.00'
2024-12-30 15:38:33	The record with UID '16195' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.13.01.01.00' ----> '03.03.01.01.00'
2024-12-30 15:38:33	The record with UID '16195' updated from 'Timebars'! Details: Field['Cost'] :: '16500' ----> '326250'
2024-12-30 15:38:33	The record with UID 'NP-2024-008' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.11.00.00.00' ----> '03.01.00.00.00'
2024-12-30 15:38:33	The record with UID '16154' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.01.00.00' ----> '03.04.01.00.00'
2024-12-30 15:38:33	The record with UID '16196' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '01.14.01.01.00' ----> '03.04.01.01.00'
2024-12-30 15:38:33	The record with UID '16196' updated from 'Timebars'! Details: Field['Cost'] :: '19125' ----> '390000'
2024-12-30 15:38:33	The record with UID '16116' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.00.00' ----> '02.06.01.00.00'
2024-12-30 15:38:33	The record with UID '16158' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.01.00' ----> '02.06.01.01.00'
2024-12-30 15:38:33	The record with UID '16158' updated from 'Timebars'! Details: Field['Cost'] :: '24750' ----> '498750'
2024-12-30 15:38:33	The record with UID '16119' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.00.00' ----> '01.11.01.00.00'
2024-12-30 15:38:33	The record with UID '16119' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '552000'
2024-12-30 15:38:33	The record with UID '16161' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.01.00' ----> '01.11.01.01.00'
2024-12-30 15:38:33	The record with UID '16161' updated from 'Timebars'! Details: Field['Cost'] :: '26062.5' ----> '552000'
2024-12-30 15:38:33	The record with UID '16120' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.00.00' ----> '01.12.01.00.00'
2024-12-30 15:38:33	The record with UID '16120' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16162' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.01.00' ----> '01.12.01.01.00'
2024-12-30 15:38:33	The record with UID '16162' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2024-12-30 15:38:33	The record with UID '16121' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.00.00' ----> '02.07.01.00.00'
2024-12-30 15:38:33	The record with UID '16163' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.01.00' ----> '02.07.01.01.00'
2024-12-30 15:38:33	The record with UID '16163' updated from 'Timebars'! Details: Field['Cost'] :: '20437.5' ----> '405000'
2024-12-30 15:38:33	The record with UID '16129' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.00.00' ----> '01.13.01.00.00'
2024-12-30 15:38:33	The record with UID '16129' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16171' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.01.00' ----> '01.13.01.01.00'
2024-12-30 15:38:33	The record with UID '16171' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2024-12-30 15:38:33	The record with UID '16132' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.00.00' ----> '02.08.01.00.00'
2024-12-30 15:38:33	The record with UID '16174' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.01.00' ----> '02.08.01.01.00'
2024-12-30 15:38:33	The record with UID '16174' updated from 'Timebars'! Details: Field['Cost'] :: '22500' ----> '450000'
2024-12-30 15:38:33	The record with UID '16134' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.00.00' ----> '02.09.01.00.00'
2024-12-30 15:38:33	The record with UID '16176' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.01.00' ----> '02.09.01.01.00'
2024-12-30 15:38:33	The record with UID '16176' updated from 'Timebars'! Details: Field['Cost'] :: '10875' ----> '217500'
2024-12-30 15:38:33	The record with UID '16113' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.01.01.00.00' ----> '02.01.01.00.00'
2024-12-30 15:38:33	The record with UID '16155' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.01.01.01.00' ----> '02.01.01.01.00'
2024-12-30 15:38:33	The record with UID '16155' updated from 'Timebars'! Details: Field['Cost'] :: '30750' ----> '656000'
2024-12-30 15:38:33	The record with UID '16122' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.02.01.00.00' ----> '02.02.01.00.00'
2024-12-30 15:38:33	The record with UID '16164' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.02.01.01.00' ----> '02.02.01.01.00'
2024-12-30 15:38:33	The record with UID '16164' updated from 'Timebars'! Details: Field['Cost'] :: '16125' ----> '348000'
2024-12-30 15:38:33	The record with UID '16123' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.03.01.00.00' ----> '01.08.01.00.00'
2024-12-30 15:38:33	The record with UID '16123' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '340000'
2024-12-30 15:38:33	The record with UID '16165' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.03.01.01.00' ----> '01.08.01.01.00'
2024-12-30 15:38:33	The record with UID '16165' updated from 'Timebars'! Details: Field['Cost'] :: '16125' ----> '340000'
2024-12-30 15:38:33	The record with UID '16125' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.04.01.00.00' ----> '03.05.01.00.00'
2024-12-30 15:38:33	The record with UID '16167' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.04.01.01.00' ----> '03.05.01.01.00'
2024-12-30 15:38:33	The record with UID '16167' updated from 'Timebars'! Details: Field['Cost'] :: '19312.5' ----> '390000'
2024-12-30 15:38:33	The record with UID '16131' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.05.01.00.00' ----> '02.10.01.00.00'
2024-12-30 15:38:33	The record with UID '16173' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.05.01.01.00' ----> '02.10.01.01.00'
2024-12-30 15:38:33	The record with UID '16173' updated from 'Timebars'! Details: Field['Cost'] :: '18187.5' ----> '371250'
2024-12-30 15:38:33	The record with UID 'NP-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.00.00.00' ----> '03.06.00.00.00'
2024-12-30 15:38:33	The record with UID '16136' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.01.00.00' ----> '01.09.01.00.00'
2024-12-30 15:38:33	The record with UID '16136' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '460000'
2024-12-30 15:38:33	The record with UID '16178' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.01.01.00' ----> '01.09.01.01.00'
2024-12-30 15:38:33	The record with UID '16178' updated from 'Timebars'! Details: Field['Cost'] :: '21937.5' ----> '460000'
2024-12-30 15:38:34	The record with UID 'NP-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.00.00.00' ----> '03.07.00.00.00'
2024-12-30 15:38:34	The record with UID '16138' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.01.00.00' ----> '01.10.01.00.00'
2024-12-30 15:38:34	The record with UID '16138' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '604000'
2024-12-30 15:38:34	The record with UID '16180' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.01.01.00' ----> '01.10.01.01.00'
2024-12-30 15:38:34	The record with UID '16180' updated from 'Timebars'! Details: Field['Cost'] :: '28500' ----> '604000'
2024-12-30 15:38:34	The record with UID 'NP-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.00.00.00' ----> '03.08.00.00.00'
2024-12-30 15:38:34	The record with UID '16139' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.01.00.00' ----> '02.11.01.00.00'
2024-12-30 15:38:34	The record with UID '16181' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.01.01.00' ----> '02.11.01.01.00'
2024-12-30 15:38:34	The record with UID '16181' updated from 'Timebars'! Details: Field['Cost'] :: '30937.5' ----> '615000'
2024-12-30 15:38:34	The record with UID 'BS-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.06.00.00.00' ----> '01.09.00.00.00'
2024-12-30 15:38:34	The record with UID 'BS-2024-002' updated from 'Timebars'! Details: Field['Cost'] :: '26484.4' ----> '460000'
2024-12-30 15:38:34	The record with UID '16140' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.01.00.00' ----> '02.12.01.00.00'
2024-12-30 15:38:34	The record with UID '16182' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.01.01.00' ----> '02.12.01.01.00'
2024-12-30 15:38:34	The record with UID '16182' updated from 'Timebars'! Details: Field['Cost'] :: '60187.5' ----> '558750'
2024-12-30 15:38:34	The record with UID 'NP-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.00.00.00' ----> '03.09.00.00.00'
2024-12-30 15:38:34	The record with UID '16141' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.01.00.00' ----> '03.06.01.00.00'
2024-12-30 15:38:34	The record with UID '16183' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.10.01.01.00' ----> '03.06.01.01.00'
2024-12-30 15:38:34	The record with UID '16183' updated from 'Timebars'! Details: Field['Cost'] :: '48375' ----> '967500'
2024-12-30 15:38:34	The record with UID 'BS-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.07.00.00.00' ----> '01.10.00.00.00'
2024-12-30 15:38:34	The record with UID 'BS-2024-004' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '604000'
2024-12-30 15:38:34	The record with UID '16142' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.01.00.00' ----> '03.07.01.00.00'
2024-12-30 15:38:34	The record with UID '16184' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.11.01.01.00' ----> '03.07.01.01.00'
2024-12-30 15:38:34	The record with UID '16184' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '318750'
2024-12-30 15:38:34	The record with UID 'BS-2024-005' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.08.00.00.00' ----> '02.11.00.00.00'
2024-12-30 15:38:34	The record with UID '16143' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.01.00.00' ----> '03.08.01.00.00'
2024-12-30 15:38:34	The record with UID '16185' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.12.01.01.00' ----> '03.08.01.01.00'
2024-12-30 15:38:34	The record with UID '16185' updated from 'Timebars'! Details: Field['Cost'] :: '16312.5' ----> '318750'
2024-12-30 15:38:34	The record with UID 'BS-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.09.00.00.00' ----> '02.12.00.00.00'
2024-12-30 15:38:34	The record with UID '16145' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.01.00.00' ----> '03.09.01.00.00'
2024-12-30 15:38:34	The record with UID '16187' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '03.13.01.01.00' ----> '03.09.01.01.00'
2024-12-30 15:38:34	The record with UID '16187' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '761250'
2024-12-30 15:38:34	The record with UID '16166' updated from 'Timebars'! Details: Field['Cost'] :: '7312.5' ----> '281250'
2024-12-30 15:38:34	The record with UID '16130' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.02.01.00.00' ----> '02.13.01.00.00'
2024-12-30 15:38:34	The record with UID '16172' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.02.01.01.00' ----> '02.13.01.01.00'
2024-12-30 15:38:34	The record with UID '16172' updated from 'Timebars'! Details: Field['Cost'] :: '20062.5' ----> '405000'
2024-12-30 15:38:34	The record with UID 'NP-2024-004' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.00.00.00' ----> '04.02.00.00.00'
2024-12-30 15:38:34	The record with UID '16144' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.01.00.00' ----> '04.02.01.00.00'
2024-12-30 15:38:34	The record with UID '16186' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.03.01.01.00' ----> '04.02.01.01.00'
2024-12-30 15:38:34	The record with UID '16186' updated from 'Timebars'! Details: Field['Cost'] :: '25875' ----> '517500'
2024-12-30 15:38:34	The record with UID 'TT-2024-001' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.00.00.00' ----> '04.05.00.00.00'
2024-12-30 15:38:34	The record with UID '16146' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.01.00.00' ----> '04.03.01.00.00'
2024-12-30 15:38:34	The record with UID '16188' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.01.01.00' ----> '04.03.01.01.00'
2024-12-30 15:38:34	The record with UID '16188' updated from 'Timebars'! Details: Field['Cost'] :: '24750' ----> '502500'
2024-12-30 15:38:34	The record with UID 'TT-2024-002' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.00.00.00' ----> '04.06.00.00.00'
2024-12-30 15:38:34	The record with UID '16147' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.01.00.00' ----> '04.04.01.00.00'
2024-12-30 15:38:34	The record with UID '16189' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.01.01.00' ----> '04.04.01.01.00'
2024-12-30 15:38:34	The record with UID '16189' updated from 'Timebars'! Details: Field['Cost'] :: '14250' ----> '288750'
2024-12-30 15:38:34	The record with UID 'TT-2024-003' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.00.00.00' ----> '04.07.00.00.00'
2024-12-30 15:38:34	The record with UID '16149' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.01.00.00' ----> '04.05.01.00.00'
2024-12-30 15:38:34	The record with UID '16191' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.06.01.01.00' ----> '04.05.01.01.00'
2024-12-30 15:38:34	The record with UID '16191' updated from 'Timebars'! Details: Field['Cost'] :: '10125' ----> '202500'
2024-12-30 15:38:34	The record with UID 'NP-2024-006' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.04.00.00.00' ----> '04.03.00.00.00'
2024-12-30 15:38:34	The record with UID '16150' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.01.00.00' ----> '04.06.01.00.00'
2024-12-30 15:38:34	The record with UID '16192' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.07.01.01.00' ----> '04.06.01.01.00'
2024-12-30 15:38:34	The record with UID '16192' updated from 'Timebars'! Details: Field['Cost'] :: '11437.5' ----> '232500'
2024-12-30 15:38:34	The record with UID 'NP-2024-007' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.05.00.00.00' ----> '04.04.00.00.00'
2024-12-30 15:38:34	The record with UID '16151' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.01.00.00' ----> '04.07.01.00.00'
2024-12-30 15:38:34	The record with UID '16193' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '04.08.01.01.00' ----> '04.07.01.01.00'
2024-12-30 15:38:34	The record with UID '16193' updated from 'Timebars'! Details: Field['Cost'] :: '60750' ----> '322500'
2024-12-30 15:38:34	Merge Operation Finished!
2025-01-03 15:47:23	The CSV Imported Successfully to MetaData
2025-01-03 15:57:56	The CSV Imported Successfully to MetaData
2025-01-04 15:44:04	The CSV Imported Successfully to Timebars
2025-01-04 15:44:39	The CSV Imported Successfully to Timebars
2025-01-05 16:27:22	The CSV Imported Successfully to AdminPanel
2025-01-05 16:27:29	The CSV Imported Successfully to Timebars
2025-01-05 16:27:46	The CSV Imported Successfully to MetaData
2025-01-05 16:31:31	The CSV Imported Successfully to AdminPanel
2025-01-05 16:31:37	The CSV Imported Successfully to Timebars
2025-01-05 16:31:46	The CSV Imported Successfully to MetaData
2025-01-05 16:35:56	The CSV Imported Successfully to AdminPanel
2025-01-05 16:36:05	The CSV Imported Successfully to Timebars
2025-01-05 16:36:13	The CSV Imported Successfully to MetaData
2025-01-05 16:36:33	The CSV Imported Successfully to Resources
2025-01-05 16:38:59	The CSV Imported Successfully to AdminPanel
2025-01-05 16:39:04	The CSV Imported Successfully to Timebars
2025-01-05 16:39:13	The CSV Imported Successfully to MetaData
2025-01-05 16:39:33	The CSV Imported Successfully to Resources
2025-01-05 16:44:05	The CSV Imported Successfully to AdminPanel
2025-01-05 16:44:14	The CSV Imported Successfully to Timebars
2025-01-05 16:44:23	The CSV Imported Successfully to MetaData
2025-01-05 16:44:29	The CSV Imported Successfully to Resources
2025-01-27 13:55:09	The CSV Imported Successfully to AdminPanel
2025-01-27 13:55:18	The CSV Imported Successfully to Timebars
2025-01-27 13:55:27	The CSV Imported Successfully to MetaData
2025-01-27 13:55:53	The CSV Imported Successfully to Resources
2025-01-27 13:56:05	The CSV Imported Successfully to Fields
2025-01-27 14:03:46	The CSV Imported Successfully to Fields
2025-01-27 14:23:17	The CSV Imported Successfully to Timebars
2025-01-27 14:23:24	The CSV Imported Successfully to MetaData
2025-01-27 14:23:39	The CSV Imported Successfully to Fields
2025-02-14 13:37:55	The CSV Imported Successfully to AdminPanel
2025-02-14 13:38:01	The CSV Imported Successfully to Timebars
2025-02-14 13:38:09	The CSV Imported Successfully to MetaData
2025-02-14 13:38:22	The CSV Imported Successfully to Resources
2025-02-21 15:12:06	The CSV Imported Successfully to AdminPanel
2025-02-21 15:12:12	The CSV Imported Successfully to Timebars
2025-02-21 15:12:18	The CSV Imported Successfully to MetaData
2025-02-21 15:17:43	The CSV Imported Successfully to AdminPanel
2025-02-21 15:17:48	The CSV Imported Successfully to Timebars
2025-02-21 15:17:54	The CSV Imported Successfully to MetaData
2025-02-21 15:25:12	The CSV Imported Successfully to AdminPanel
2025-02-21 15:25:18	The CSV Imported Successfully to Timebars
2025-02-21 15:25:27	The CSV Imported Successfully to MetaData
2025-02-28 10:08:09	The CSV Imported Successfully to Fields
2025-03-12 16:20:51	The CSV Imported Successfully to Timebars
2025-03-12 16:20:59	The CSV Imported Successfully to MetaData
2025-03-12 16:21:24	The CSV Imported Successfully to AdminPanel
2025-03-12 16:30:28	The CSV Imported Successfully to Fields
2025-03-19 15:24:03	The CSV Imported Successfully to AdminPanel
2025-03-19 15:24:59	The CSV Imported Successfully to Timebars
2025-03-19 15:25:08	The CSV Imported Successfully to MetaData
2025-03-19 15:36:08	The CSV Imported Successfully to AdminPanel
2025-03-19 15:36:39	The CSV Imported Successfully to Timebars
2025-03-19 15:36:49	The CSV Imported Successfully to MetaData
2025-03-19 15:46:27	The CSV Imported Successfully to AdminPanel
2025-03-19 15:46:50	The CSV Imported Successfully to Timebars
2025-03-19 15:46:58	The CSV Imported Successfully to MetaData
2025-03-19 15:51:03	Merge Operation Started!
2025-03-19 15:51:03	Double Title Found in 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A002' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A008' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16114' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16156' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A011' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16117' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16159' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A023' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16126' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16168' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A024' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16127' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16169' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A026' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16128' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16170' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A033' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16133' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16175' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'BS-2024-003' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16137' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16179' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A020' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16123' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16165' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'BS-2024-002' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16136' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16178' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'BS-2024-004' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16138' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16180' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A013' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16119' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16161' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A017' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16120' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16162' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A027' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16129' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID '16171' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:04	The record with UID 'A0021' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.00.00.00.00' ----> '01.00.00.00.00'
2025-03-19 15:51:04	The record with UID 'A0021' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '5896000'
2025-03-19 15:51:04	The record with UID 'A007' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Source Cloud services for our Core products): 25.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 42.50DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 46, State Warning! Awaiting Input,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A007' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '660000'
2025-03-19 15:51:04	The record with UID '16113' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.00.00' ----> '01.01.01.00.00'
2025-03-19 15:51:04	The record with UID '16113' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '660000'
2025-03-19 15:51:04	The record with UID '16155' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.01.01.01.00' ----> '01.01.01.01.00'
2025-03-19 15:51:04	The record with UID '16155' updated from 'Timebars'! Details: Field['Cost'] :: '656000' ----> '660000'
2025-03-19 15:51:04	The record with UID 'A019' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Grow the Business): 100.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 75.00DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 50, Work Avg Score: 100,Final Score: 88, Decision: Continue |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A019' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '348000'
2025-03-19 15:51:04	The record with UID '16122' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.00.00' ----> '01.02.01.00.00'
2025-03-19 15:51:04	The record with UID '16122' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '348000'
2025-03-19 15:51:04	The record with UID '16164' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.02.01.01.00' ----> '01.02.01.01.00'
2025-03-19 15:51:04	The record with UID 'A009' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 59.38DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 75, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 46, State null,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A009' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '412000'
2025-03-19 15:51:04	The record with UID '16115' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.00.00' ----> '01.03.01.00.00'
2025-03-19 15:51:04	The record with UID '16115' updated from 'Timebars'! Details: Field['Cost'] :: '37875' ----> '412000'
2025-03-19 15:51:04	The record with UID '16157' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.03.01.01.00' ----> '01.03.01.01.00'
2025-03-19 15:51:04	The record with UID '16157' updated from 'Timebars'! Details: Field['Cost'] :: '382500' ----> '412000'
2025-03-19 15:51:04	The record with UID 'A012' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Faster response to new business opportunities): 75.00,Objective Score: (Modernize the Business): 50.00,Strategy Score: (Build Recurring Revenue Streams): 50.00,Project Score: 48.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 50, Work Avg Score: 100,ROM Estimate Score: 100,Class Estimate Score: 50,Final Score: 50, State null,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A012' updated from 'Timebars'! Details: Field['Cost'] :: '48750' ----> '396000'
2025-03-19 15:51:04	The record with UID '16118' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.00.00' ----> '01.04.01.00.00'
2025-03-19 15:51:04	The record with UID '16118' updated from 'Timebars'! Details: Field['Cost'] :: '48750' ----> '396000'
2025-03-19 15:51:04	The record with UID '16160' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.04.01.01.00' ----> '01.04.01.01.00'
2025-03-19 15:51:04	The record with UID '16160' updated from 'Timebars'! Details: Field['Cost'] :: '375000' ----> '396000'
2025-03-19 15:51:04	The record with UID 'BS-2024-001' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Drive Contract Renewals): 20.00,Project Score: 73.75DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 75,Final Score: 50, State null,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'BS-2024-001' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2025-03-19 15:51:04	The record with UID '16135' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.00.00' ----> '01.05.01.00.00'
2025-03-19 15:51:04	The record with UID '16135' updated from 'Timebars'! Details: Field['Cost'] :: '15937.5' ----> '340000'
2025-03-19 15:51:04	The record with UID '16177' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.05.01.01.00' ----> '01.05.01.01.00'
2025-03-19 15:51:04	The record with UID '16177' updated from 'Timebars'! Details: Field['Cost'] :: '318750' ----> '340000'
2025-03-19 15:51:04	The record with UID 'A010' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Improve employee skills): 62.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Reduce waste): 30.00,Project Score: 63.13' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A010' updated from 'Timebars'! Details: Field['Cost'] :: '26320' ----> '528000'
2025-03-19 15:51:04	The record with UID '16116' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.00.00' ----> '01.06.01.00.00'
2025-03-19 15:51:04	The record with UID '16116' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '528000'
2025-03-19 15:51:04	The record with UID '16158' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.06.01.01.00' ----> '01.06.01.01.00'
2025-03-19 15:51:04	The record with UID '16158' updated from 'Timebars'! Details: Field['Cost'] :: '498750' ----> '528000'
2025-03-19 15:51:04	The record with UID 'A018' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Productivity Tools): 60.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Ensure compliance): 80.00,Project Score: 66.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A018' updated from 'Timebars'! Details: Field['Cost'] :: '31360' ----> '436000'
2025-03-19 15:51:04	The record with UID '16121' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.00.00' ----> '01.07.01.00.00'
2025-03-19 15:51:04	The record with UID '16121' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '436000'
2025-03-19 15:51:04	The record with UID '16163' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.07.01.01.00' ----> '01.07.01.01.00'
2025-03-19 15:51:04	The record with UID '16163' updated from 'Timebars'! Details: Field['Cost'] :: '405000' ----> '436000'
2025-03-19 15:51:04	The record with UID 'A031' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Digital Transformation): 20.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 35.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 25,Cost Avg Score: 100, Work Avg Score: 100,Final Score: 78, Decision: Review |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A031' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '480000'
2025-03-19 15:51:04	The record with UID '16132' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.08.01.00.00' ----> '01.08.01.00.00'
2025-03-19 15:51:04	The record with UID '16132' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '480000'
2025-03-19 15:51:04	The record with UID '16174' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.08.01.01.00' ----> '01.08.01.01.00'
2025-03-19 15:51:04	The record with UID '16174' updated from 'Timebars'! Details: Field['Cost'] :: '450000' ----> '480000'
2025-03-19 15:51:04	The record with UID 'A036' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Improve product reliability): 50.00,Objective Score: (Transform the Business): 25.00,Strategy Score: (Increase share of market): 40.00,Project Score: 48.75DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 75, Decision: Review |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A036' updated from 'Timebars'! Details: Field['Cost'] :: '24968.8' ----> '240000'
2025-03-19 15:51:04	The record with UID '16134' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.09.01.00.00' ----> '01.09.01.00.00'
2025-03-19 15:51:04	The record with UID '16134' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '240000'
2025-03-19 15:51:04	The record with UID '16176' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.09.01.01.00' ----> '01.09.01.01.00'
2025-03-19 15:51:04	The record with UID '16176' updated from 'Timebars'! Details: Field['Cost'] :: '217500' ----> '240000'
2025-03-19 15:51:04	The record with UID 'A030' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Our Core Products): 80.00,Initiative Score: (Build AI/ML Capabilities): 87.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Server more customers): 10.00,Project Score: 50.63DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 100,Cost Avg Score: 100, Work Avg Score: 50,Final Score: 95, Decision: Continue |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'A030' updated from 'Timebars'! Details: Field['Cost'] :: '16031.3' ----> '388000'
2025-03-19 15:51:04	The record with UID '16131' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.10.01.00.00' ----> '01.10.01.00.00'
2025-03-19 15:51:04	The record with UID '16131' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '388000'
2025-03-19 15:51:04	The record with UID '16173' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.10.01.01.00' ----> '01.10.01.01.00'
2025-03-19 15:51:04	The record with UID '16173' updated from 'Timebars'! Details: Field['Cost'] :: '371250' ----> '388000'
2025-03-19 15:51:04	The record with UID 'BS-2024-005' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Improve productivity with Agile Teams): 37.50,Objective Score: (Transform the Business): 25.00,Strategy Score: (Reduce waste): 30.00,Project Score: 48.13DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 50,Cost Avg Score: 100, Work Avg Score: 100,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 40, State null,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'BS-2024-005' updated from 'Timebars'! Details: Field['Cost'] :: '31360' ----> '656000'
2025-03-19 15:51:04	The record with UID '16139' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.11.01.00.00' ----> '01.11.01.00.00'
2025-03-19 15:51:04	The record with UID '16139' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '656000'
2025-03-19 15:51:04	The record with UID '16181' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.11.01.01.00' ----> '01.11.01.01.00'
2025-03-19 15:51:04	The record with UID '16181' updated from 'Timebars'! Details: Field['Cost'] :: '615000' ----> '656000'
2025-03-19 15:51:04	The record with UID 'BS-2024-006' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Support moden digital workplace): 12.50,Objective Score: (Grow the Business): 100.00,Strategy Score: (Server more customers): 10.00,Project Score: 55.63DECISION ANALYSIS NEW PROJECTS - Risk Complexity Score: 25,Cost Avg Score: 0, Work Avg Score: 0,ROM Estimate Score: 0,Class Estimate Score: 50,Final Score: 14, State null,Financial Metrics: 0. |' ----> 'Not Assessed'
2025-03-19 15:51:04	The record with UID 'BS-2024-006' updated from 'Timebars'! Details: Field['Cost'] :: '61441' ----> '588000'
2025-03-19 15:51:04	The record with UID '16140' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.12.01.00.00' ----> '01.12.01.00.00'
2025-03-19 15:51:04	The record with UID '16140' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '588000'
2025-03-19 15:51:05	The record with UID '16182' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.12.01.01.00' ----> '01.12.01.01.00'
2025-03-19 15:51:05	The record with UID '16182' updated from 'Timebars'! Details: Field['Cost'] :: '558750' ----> '588000'
2025-03-19 15:51:05	The record with UID 'A029' updated from 'MetaData'! Details: Field['Decision Notes'] :: 'STRATEGIC PRIORITY ANALYSIS - Category Score: (Business Systems): 100.00,Initiative Score: (Strengthen Cybersecurity Infrastructure): 100.00,Objective Score: (Run the Business): 75.00,Strategy Score: (Server more customers): 10.00,Project Score: 71.25DECISION ANALYSIS IN FLIGHT PROJECTS -Health Score: 12, Risk Complexity Score: 75,Cost Avg Score: 100, Work Avg Score: 0,Final Score: 83, Decision: Continue |' ----> 'Not Assessed'
2025-03-19 15:51:05	The record with UID 'A029' updated from 'Timebars'! Details: Field['Cost'] :: '5062.5' ----> '424000'
2025-03-19 15:51:05	The record with UID '16130' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.13.01.00.00' ----> '01.13.01.00.00'
2025-03-19 15:51:05	The record with UID '16130' updated from 'Timebars'! Details: Field['Cost'] :: '0' ----> '424000'
2025-03-19 15:51:05	The record with UID '16172' updated from 'MetaData'! Details: Field['Hierarchy Order'] :: '02.13.01.01.00' ----> '01.13.01.01.00'
2025-03-19 15:51:05	The record with UID '16172' updated from 'Timebars'! Details: Field['Cost'] :: '405000' ----> '424000'
2025-03-19 15:51:05	The record with UID 'A0022' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-008' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16148' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16190' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-004' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16152' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16194' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-005' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16153' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16195' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-006' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16154' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16196' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'A022' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16125' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16167' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-001' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16141' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16183' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-002' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16142' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16184' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-003' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16143' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16185' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-005' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16145' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16187' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'A0023' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'A021' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16124' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16166' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-004' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16144' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16186' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-006' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16146' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16188' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'NP-2024-007' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16147' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16189' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-001' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16149' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16191' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-002' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16150' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16192' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID 'TT-2024-003' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16151' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	The record with UID '16193' does not exist in 'Timebars' and 'MetaData'!
2025-03-19 15:51:05	Merge Operation Finished!
2025-03-20 16:31:51	The CSV Imported Successfully to TBMDJoined
2025-03-23 15:52:09	The CSV Imported Successfully to AdminPanel
2025-03-23 15:52:21	The CSV Imported Successfully to Timebars
2025-03-23 15:52:27	The CSV Imported Successfully to MetaData
2025-03-23 15:54:50	The CSV Imported Successfully to TBMDJoined
2025-03-23 15:55:07	The CSV Imported Successfully to Resources
2025-03-23 16:01:12	The CSV Imported Successfully to Timebars
2025-03-26 14:59:09	The CSV Imported Successfully to Timebars
2025-03-26 14:59:27	The CSV Imported Successfully to MetaData
2025-03-26 15:26:51	The CSV Imported Successfully to AdminPanel
2025-03-26 15:27:32	The CSV Imported Successfully to TBMDJoined
2025-03-27 14:05:58	The CSV Imported Successfully to TBMDJoined
2025-03-27 14:16:43	The CSV Imported Successfully to TBMDJoined
2025-03-27 14:36:45	The CSV Imported Successfully to TBMDJoined
2025-04-07 17:03:42	The CSV Imported Successfully to Timebars
2025-04-07 17:03:51	The CSV Imported Successfully to MetaData
2025-04-07 17:11:03	The CSV Imported Successfully to AdminPanel
2025-04-07 17:11:10	The CSV Imported Successfully to Timebars
2025-04-07 17:11:21	The CSV Imported Successfully to MetaData
2025-04-07 17:11:33	The CSV Imported Successfully to TBMDJoined
2025-04-13 11:45:21	The CSV Imported Successfully to AdminPanel
2025-04-13 11:45:28	The CSV Imported Successfully to Timebars
2025-04-13 11:45:38	The CSV Imported Successfully to MetaData
2025-04-13 11:48:37	The CSV Imported Successfully to TBMDJoined
2025-04-13 12:06:21	The CSV Imported Successfully to Timebars
2025-04-13 12:06:42	The CSV Imported Successfully to MetaData
2025-04-13 12:21:53	The CSV Imported Successfully to Timebars
2025-04-13 12:23:49	The CSV Imported Successfully to Resources
2025-04-13 12:24:07	The CSV Imported Successfully to MetaData
2025-04-13 12:24:19	The CSV Imported Successfully to Timebars
2025-04-18 15:41:30	The CSV Imported Successfully to AdminPanel
2025-04-18 15:43:31	The CSV Imported Successfully to AdminPanel
2025-04-18 15:43:36	The CSV Imported Successfully to Timebars
2025-04-18 15:43:44	The CSV Imported Successfully to MetaData
2025-04-18 15:44:43	The CSV Imported Successfully to Resources
2025-04-18 15:54:04	The CSV Imported Successfully to AdminPanel
2025-04-18 15:54:09	The CSV Imported Successfully to Timebars
2025-04-18 15:54:16	The CSV Imported Successfully to MetaData
2025-04-18 15:57:58	The CSV Imported Successfully to AdminPanel
2025-04-18 15:58:04	The CSV Imported Successfully to Timebars
2025-04-18 15:58:10	The CSV Imported Successfully to MetaData
2025-04-18 16:07:22	The CSV Imported Successfully to AdminPanel
2025-04-18 16:07:27	The CSV Imported Successfully to Timebars
2025-04-18 16:07:50	The CSV Imported Successfully to MetaData
2025-04-18 16:47:32	The CSV Imported Successfully to AdminPanel
2025-04-18 16:47:38	The CSV Imported Successfully to Timebars
2025-04-18 16:47:48	The CSV Imported Successfully to MetaData
2025-04-22 13:00:19	The CSV Imported Successfully to AdminPanel
2025-04-22 13:00:54	The CSV Imported Successfully to Timebars
2025-04-22 13:01:40	The CSV Imported Successfully to MetaData
2025-04-22 13:30:14	The CSV Imported Successfully to AdminPanel
2025-04-22 13:30:31	The CSV Imported Successfully to Timebars
2025-04-22 13:30:56	The CSV Imported Successfully to MetaData
2025-04-22 13:33:46	The CSV Imported Successfully to MetaData
2025-04-22 13:49:39	The CSV Imported Successfully to AdminPanel
2025-04-22 13:49:44	The CSV Imported Successfully to Timebars
2025-04-22 13:49:51	The CSV Imported Successfully to MetaData
2025-04-24 09:38:53	The CSV Imported Successfully to Fields
2025-04-24 09:39:30	The CSV Imported Successfully to Fields
2025-04-25 13:46:27	The CSV Imported Successfully to AdminPanel
2025-04-25 13:46:33	The CSV Imported Successfully to Timebars
2025-04-25 13:46:49	The CSV Imported Successfully to MetaData
2025-04-29 15:52:23	The CSV Imported Successfully to AdminPanel
2025-04-29 15:52:27	The CSV Imported Successfully to Timebars
2025-04-29 15:52:34	The CSV Imported Successfully to MetaData
2025-04-29 16:07:35	The CSV Imported Successfully to Timebars
2025-04-29 16:07:43	The CSV Imported Successfully to MetaData
2025-05-02 16:25:29	The CSV Imported Successfully to AdminPanel
2025-05-02 16:25:35	The CSV Imported Successfully to Timebars
2025-05-02 16:25:57	The CSV Imported Successfully to MetaData
2025-05-06 13:12:34	The CSV Imported Successfully to AdminPanel
2025-05-06 13:12:45	The CSV Imported Successfully to Timebars
2025-05-06 13:12:58	The CSV Imported Successfully to MetaData
2025-05-06 13:13:19	The CSV Imported Successfully to Fields
2025-05-06 13:16:34	The CSV Imported Successfully to Timebars
2025-05-06 13:16:43	The CSV Imported Successfully to MetaData
2025-05-07 09:13:31	The CSV Imported Successfully to AdminPanel
2025-05-07 09:13:52	The CSV Imported Successfully to Timebars
2025-05-07 09:14:12	The CSV Imported Successfully to MetaData
2025-05-07 09:38:27	The CSV Imported Successfully to AdminPanel
2025-05-07 09:38:51	The CSV Imported Successfully to Timebars
2025-05-07 09:39:04	The CSV Imported Successfully to MetaData
2025-05-07 09:45:47	The CSV Imported Successfully to AdminPanel
2025-05-07 09:45:51	The CSV Imported Successfully to Timebars
2025-05-07 09:46:11	The CSV Imported Successfully to MetaData
2025-05-07 09:54:55	The CSV Imported Successfully to AdminPanel
2025-05-07 09:55:22	The CSV Imported Successfully to Timebars
2025-05-07 09:55:38	The CSV Imported Successfully to MetaData
2025-05-14 08:46:52	The CSV Imported Successfully to AdminPanel
2025-05-14 08:46:59	The CSV Imported Successfully to Timebars
2025-05-14 08:47:08	The CSV Imported Successfully to MetaData
2025-05-14 08:49:35	The CSV Imported Successfully to Resources
2025-05-15 08:17:14	The CSV Imported Successfully to AdminPanel
2025-05-15 08:17:20	The CSV Imported Successfully to Timebars
2025-05-15 08:17:28	The CSV Imported Successfully to MetaData
2025-05-15 08:17:37	The CSV Imported Successfully to Baseline
2025-05-18 11:33:19	The CSV Imported Successfully to AdminPanel
2025-05-18 11:33:59	The CSV Imported Successfully to Timebars
2025-05-18 11:34:07	The CSV Imported Successfully to MetaData
2025-05-18 11:35:12	The CSV Imported Successfully to Timebars
2025-05-18 11:35:27	The CSV Imported Successfully to MetaData
2025-05-18 11:36:20	The CSV Imported Successfully to Baseline
2025-05-18 11:36:30	The CSV Imported Successfully to Timebars
2025-05-18 11:41:12	The CSV Imported Successfully to Timebars
2025-06-06 07:54:30	The CSV Imported Successfully to AdminPanel
2025-06-06 07:54:36	The CSV Imported Successfully to Timebars
2025-06-06 07:54:46	The CSV Imported Successfully to MetaData
2025-06-06 09:06:57	The CSV Imported Successfully to Timebars
2025-06-11 13:54:27	The CSV Imported Successfully to Timebars
2025-06-11 13:54:36	The CSV Imported Successfully to MetaData
2025-06-11 13:56:18	The CSV Imported Successfully to AdminPanel
2025-06-22 11:58:00	The CSV Imported Successfully to AdminPanel
2025-06-22 11:58:05	The CSV Imported Successfully to Timebars
2025-06-22 11:58:13	The CSV Imported Successfully to MetaData
2025-06-26 12:13:02	The CSV Imported Successfully to AdminPanel
2025-06-26 12:13:12	The CSV Imported Successfully to Timebars
2025-06-26 12:13:24	The CSV Imported Successfully to MetaData
2025-07-16 11:46:00	The CSV Imported Successfully to AdminPanel
2025-07-16 11:46:08	The CSV Imported Successfully to Timebars
2025-07-16 11:46:18	The CSV Imported Successfully to MetaData
2025-07-16 12:04:24	The CSV Imported Successfully to AdminPanel
2025-07-16 12:04:31	The CSV Imported Successfully to Timebars
2025-07-16 12:04:43	The CSV Imported Successfully to MetaData
2025-07-16 12:06:33	The CSV Imported Successfully to Timebars
2025-07-16 12:06:46	The CSV Imported Successfully to MetaData
2025-07-16 12:12:02	The CSV Imported Successfully to AdminPanel
2025-07-16 12:12:10	The CSV Imported Successfully to Timebars
2025-07-16 12:12:17	The CSV Imported Successfully to MetaData
Clear Log!

## TEMP
tbMDID	tbMDParent	tbMDName	tbMDTypes	tbMDSubtype	tbMDHierarchy	tbMDProduct	tbMDNotesProject	tbMDDescription	tbMDExecutiveSummary	tbMDPriority	tbMDStatus	tbMDHealth	tbMDState	tbMDStage	tbMDPhase	tbMDGate	tbMDCategory	tbMDIssueCategory	tbMDEscalationLevel	tbMDProjectNumber	tbMDPM	tbMDExSponsor	tbMDNotes	tbMDPrimaryContact	tbMDDepartment	tbMDHealthOverall	tbMDHealthScope	tbMDHealthCost	tbMDHealthIssues	tbMDHealthRisk	tbMDHealthSchedule	tbMDHealthHours	tbMDProjectType	tbMDRiskVsSizeAndComplexity	tbMDROMEstimate	tbMDEstimationClass	tbMDSize	tbMDInvestmentCategory	tbMDInvestmentInitiative	tbMDInvestmentObjective	tbMDInvestmentStrategy	tbMDYesNoSelector	tbMDPriorityStrategic	tbMDCostbarsScore	tbMDFinancialScore	tbMDDecisionStrategic	tbMDDecisionNotes	tbMDPrimaryLineOfBusiness	tbMDSponsoringDepartment	tbMDContact	tbMDContactNumber	tbMDResponsibleTeam	tbMDBusinessAdvisor	tbMDDeliveryManager	tbMDOrgManager	tbMDBenefitCostRatio	tbMDEcnomicValueAdded	tbMDInternalRateOfReturn	tbMDSunkCosts	tbMDNetPresentValue	tbMDOpportunityCost	tbMDPaybackPeriod	tbMDOther2	tbMDBusinessOwner	tbMDBackgroundInfo	tbMDStakeholderDescription	tbMDProblemOpportunity	tbMDOptionsAnalysis	tbMDConsequence	tbMDKeyDependencies	tbMDValueProposition	tbMDSuccessCriteria	tbMDDecisionsRequired	tbMDKeyRecommendations	tbMDMarketAnalysis	tbMDPortfolioImpactAnalysis	tbMDKeyProjectMetrics	tbMDObjectivesAndScope	tbMDExpectedBenefits	tbMDCapabilitiesNeeded	tbMDImplementationApproach	tbMDConstraintsAssumptions	tbMDCostBenefitAnalysis	tbMDSeniorLevelCommitment	tbMDNextSteps	tbMDWrittenBy	tbMDVersion	tbMDBCaseDateApproved	tbMDWBS	tbMDWeighting	tbMDLocation	tbMDResID	tbMDPrimarySkill	tbMDPrimaryRole	tbMDResponsibility	tbMDExtSystemID1	tbMDSyncNotes	tbMDStageApprover	tbMDSprintName	tbMDExtLink1	tbMDOther3	canvasNo	tbMDRefID	tbMDSortOrder	tbMDtbLastModified	tbMDShowIn	tbMDCustomerID	tbMDAzureID	tbMDNameShort	tbMDNotesWorkflow	tbMDContractNumber	tbMDPortfolio	tbMDProgram	tbMDProgActivityAlignment	tbMDSeverity	tbMDContingency	tbMDMitigationPlan	tbMDMitigationStatus	tbMDProbability	tbMDImpact	tbMDScore	tbMDRiskCategory	tbMDRiskResponseStrategy	tbMDContingencyPlan	tbMDTriggerEvent	tbMDEarlyWarningIndicators	tbMDOther4	tbMDOther5	tbMDOther6	tbMDOther7	tbMDOther8	tbMDOther9	tbMDOther10	tbMDOther11	tbMDOther12	tbMDPrerequisitesChecklist	tbMDScheduleCommentary	tbMDBudgetCommentary	tbMDScopeCommentary	tbMDResourceCommentary	tbMDFinancialCommentary	id
20		Small New interface between System A and System B	Project	Task	01.00.00.00.00	SAP ERP System	Currently in process of sizing the backlog items.	Small sprint to design and build and API for an interface between two systems.		Normal	on_track	On schedule					Cat 1			SPR01					Sales and Marketing	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed	Not Assessed																			Ryan Tower		Procurement		Manager of IT																																									Chris Java											Dashboard																																				21520
22	20	Understand the business needs	Task	Task	01.01.00.00.00																																																																																																		20																																							21521
24	20	Establish a list of transactions needed	Task	Task	01.02.00.00.00																																																																																																		20																																							21522
26	20	Determine API architecture system A	Task	Task	01.03.00.00.00																																																																																																		20																																							21523
28	20	Determine API architecture system B	Task	Task	01.04.00.00.00																																																																																																		20																																							21524
30	20	Produce a list of data itmes in the first transaction	Task	Task	01.05.00.00.00																																																																																																		20																																							21525
32	20	Determine source of each data item in system A	Task	Task	01.06.00.00.00																																																																																																		20																																							21526
34	20	Determine source of each data item in system A	Task	Task	01.07.00.00.00																																																																																																		20																																							21527
36	20	Produce an overall system architecture diagram	Task	Task	01.08.00.00.00																																																																																																		20																																							21528
38	20	Calculate needed bandwidth	Task	Task	01.09.00.00.00																																																																																																		20																																							21529
38r	20	Only one resource has the skillset needed.	Task	Risk	01.10.00.00.00																																																																																																		20																																							21530
38i	20	Dev environment is not ready.	Task	Issue	01.11.00.00.00																																																																																																		20																																							21531
40		Demo backlog: Engineering Tools	Project	Task	02.00.00.00.00																																																																																																																																									21532
41	40	Work Item 10	Task	Risk	02.01.00.00.00																																																																																																		40																																							21533
42	40	Work Item 11	Task	Issue	02.02.00.00.00																																																																																																		40																																							21534
44	40	Work Item 12	Task	Task	02.03.00.00.00																																																																																																		40																																							21535
46	40	Work Item 13	Task	Task	02.04.00.00.00																																																																																																		40																																							21536
48	40	Work Item 14	Task	Task	02.05.00.00.00																																																																																																		40																																							21537
50		Demo backlog: Building Services	Project	Task	03.00.00.00.00																																																																																																																																									21538
51	50	Work Item 15	Task	Task	03.01.00.00.00																																																																																																		50																																							21539
52	50	Work Item 16	Task	Task	03.02.00.00.00																																																																																																		50																																							21540
54	50	Work Item 17	Task	Task	03.03.00.00.00																																																																																																		50																																							21541
56	50	Work Item 18	Task	Risk	03.04.00.00.00																																																																																																		50																																							21542
58	50	Work Item 19	Task	Issue	03.05.00.00.00																																																																																																		50																																							21543
60	50	Work Item 20	Task	Task	03.06.00.00.00																																																																																																		50																																							21544
27702	20	CR-01	Task	CR	01.12.00.00.00					Normal			Active																															0																																																										1					44																																			21545
27703	20	My New Risk	Task	Risk	01.13.00.00.00					Normal																																		0																																																										1					44																																			21546
27704	20	My New Issues	Task	Issue	01.14.00.00.00					Normal	New		Active																															0																																																										1					44																																			21547